# 01 — VYTALIX BUSINESS MODEL

Status: PROPOSED (strategy document, v1, 7 September 2026). Consistent with /FACTS_BASE.md. No figure in this document is an actual; every number is an ESTIMATE, ASSUMPTION or PROPOSAL unless marked KNOWN.

## Executive view

Vytalix is a pre-formation UK health-tech group with no revenue, no product in production and one unowned-but-associated product concept, MaternaLink (in development). The business model must therefore be built in two layers: a cash layer (Advisory, Consulting, E-Learning) that can invoice within 90 days of incorporation, and an equity layer (Vytalix Health Solutions / MaternaLink) that consumes cash for 18–30 months before it can earn.

Of the 15 revenue streams examined, only four are launchable "Now": founder-led advisory days, packaged consulting sprints, monthly advisory retainers and grant income. Everything product-related (SaaS, licensing, government contracts, white-label) is 12–24 months away and gated by IP ownership, regulatory classification and clinical partnership — none of which exist today (KNOWN gap).

Base-case services revenue in the first 12 months is £118k (ESTIMATE; range £55k–£210k), built from ~85 billable founder days at £1,200–£1,800/day plus two to three retainers. This is enough to fund incorporation, legal, brand and a part-time product lead, not a development team.

The equity story is MaternaLink positioned as a non-diagnostic maternal care-coordination and monitoring-support platform (v1) with a research track towards AI risk scoring (v3+). Realistic first product revenue is a paid UK pilot or an African state/donor-funded programme in months 18–30, at £20k–£150k per pilot (ESTIMATE).

The single most important "must be true": the founder can sell and deliver 8–10 billable days per month while resolving MaternaLink ownership with David Agunede. If either fails, the model collapses into either a lifestyle consultancy or an unfunded product idea.

## Verification note

Web search and page fetches were unavailable during this build. Market figures below are drawn from the author's prior knowledge of public sources (named where relevant) and are labelled ESTIMATE or TO VALIDATE. Before any external use, each must be checked against the named source and the URL recorded.

## 1. Group business model on one page

| Layer | Pillar | What it sells | Who pays | Why it exists in the model |
| --- | --- | --- | --- | --- |
| Cash | Vytalix Advisory | Founder-led strategic advice: digital health strategy, market entry (UK↔Africa), investor readiness, board advisory | Health-tech founders, SME health providers, NGOs, African ministries via donors | Fastest to invoice; builds network and credibility; zero capex |
| Cash | Vytalix Consulting | Packaged delivery work: discovery sprints, business cases, service redesign, digital maternity readiness, procurement and DTAC readiness | NHS trusts/ICBs (via frameworks or sub-contract), private providers, health-tech vendors, donors/NGOs | Higher volume than advisory; creates reusable IP (playbooks) that feed E-Learning and MaternaLink |
| Cash (later) | Vytalix E-Learning | Courses, subscriptions and corporate licences on digital health, maternal-care coordination, health-tech commercialisation | Individual professionals, universities, employers, NGOs | Converts consulting IP into scalable, high-margin product; low regulatory burden |
| Equity | Vytalix Health Solutions | MaternaLink (in development): maternal care-coordination, communication, education and monitoring-support platform | NHS trusts/ICBs (pilots), African states/donors, private maternity, employers/insurers (later) | The venture story; justifies external equity; long sales cycle and regulatory gating |

Sequencing logic (ASSUMPTION A6 in FACTS_BASE): services fund the company; MaternaLink is the equity story. Services must reach ~£10k/month within six months to pay for the founder's time and the legal/regulatory groundwork MaternaLink needs.

## 2. Revenue stream matrix (all 15 streams)

Legend for launch priority: Now = month 0–3 after incorporation; 6m = months 4–9; 12m = months 10–15; 24m = months 16–30.

| # | Revenue stream | Customer | Product / offer | Pricing model | Indicative price (GBP) | Gross-margin potential | Sales cycle | Acquisition difficulty | Scalability | Regulatory considerations | Launch priority | Label |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Consulting fees (project) | NHS trusts/ICBs, private providers, health-tech vendors, NGOs | Packaged sprints (see §5): discovery, business case, digital readiness, market entry | Fixed-fee per sprint; time-and-materials fallback | £8k–£45k per sprint; day rate £1,200–£1,800 founder, £700–£1,000 associate | 55–70% (founder time is the cost; associates reduce margin) | 4–12 weeks (private/vendor), 3–9 months (NHS via framework) | Medium — relationship-led; NHS needs framework or sub-contract route | Low–medium (people-bound) | None specific; NDA, UK GDPR for any data; NHS DSPT if handling patient data; professional indemnity insurance | Now | ESTIMATE |
| 2 | Advisory retainers | Health-tech founders (pre-seed–Series A), SME providers, NGOs, family offices with health interests | Monthly advisory: 2–4 days/month, board-observer style access | Monthly retainer, 3–6 month minimum | £2,500–£6,000/month | 70–85% | 2–6 weeks | Medium — depends on founder's network and visible expertise | Low (caps at ~5 retainers per advisor) | None specific; conflict-of-interest register; professional indemnity | Now | ESTIMATE |
| 3 | Implementation fees (product) | MaternaLink pilot sites (UK trust, African state programme, private hospital) | Configuration, onboarding, training, integration support | One-off implementation fee + change requests | £15k–£60k per site (UK); £25k–£150k per state programme (Africa, donor-funded) | 35–50% (labour-heavy, first sites are loss-leaders) | 6–18 months | High — no product in production yet | Medium (repeatable after 3 sites) | DTAC, DCB0129/0160 clinical safety, DSPT, UK GDPR/DPIA; NDPR (Nigeria) or local equivalents; MHRA classification opinion before any monitoring claim | 24m | TO VALIDATE |
| 4 | SaaS (MaternaLink subscription) | NHS trusts/ICBs, private maternity units, African hospitals/states | Per-site or per-woman-per-year platform subscription | Per-site annual licence (UK); per-enrolled-woman-per-year (Africa) | UK: £30k–£120k/site/yr (ESTIMATE, benchmark against maternity IT modules); Africa: £5–£40/woman/yr donor-funded (the £300 in the Ekiti proposal is UNVALIDATED per FACTS_BASE A5) | 65–80% at scale; negative until >5 sites | 9–18 months (NHS), 6–24 months (government) | Very high today (no product, no evidence) | High once validated | As #3, plus NICE ESF evidence tier, Cyber Essentials Plus, ISO 27001 desirable; SaMD pathway if any clinical decision support | 24m | TO VALIDATE |
| 5 | B2B licensing (platform modules) | Other health-tech vendors, maternity IT incumbents, telehealth providers | Licence of MaternaLink modules (e.g., education content engine, multilingual patient comms, care-plan workflows) | Annual licence + revenue share | £20k–£80k/yr per licensee (ESTIMATE) | 80%+ | 6–12 months | High — requires defensible IP and integration maturity | High | IP ownership must be settled (KNOWN gap); contractual liability caps | 24m | TO VALIDATE |
| 6 | Government contracts (UK) | NHS England/DHSC successor bodies, ICBs, local authorities (public health) | Consulting on maternity digital transformation, health inequalities, evaluation | Framework call-off or direct award under threshold (£12k–£139k depending on route — TO VALIDATE current thresholds) | £25k–£150k per contract | 45–60% | 3–9 months | High — need framework place (G-Cloud, NHS SBS, HealthTrust Europe, CCS) or sub-contract to prime | Medium | Procurement rules (PCR 2015 → Procurement Act 2023 regime), PSR for clinical services; conflict-of-interest declarations | 12m | ESTIMATE |
| 7 | Government contracts (Africa) | State ministries (e.g., Ekiti, Lagos, Ondo), federal agencies (Nigeria FMoH/NHIA), Kenya counties/SHA, Ghana GHS | MaternaLink programme delivery; digital health advisory; programme design | Programme contract (usually donor-funded via MSD for Mothers, GFF, foundations) or state budget line | Advisory: £15k–£80k; programme: £100k–£1m+/yr (ESTIMATE; the Ekiti proposal's £4.5m Phase 1 is a proposal, not a benchmark) | 30–50% (in-country delivery, partners, connectivity costs) | 9–24 months; payment risk high | Very high — incumbent (mDoc/MSD for Mothers in Ekiti and Lagos, VERIFIED), political cycles, FX | Medium | Nigeria NDPR/NDPA 2023, state MoH approvals, NHREC ethics for any research, local company registration or partner; anti-bribery (UK Bribery Act applies extraterritorially) | 24m (advisory: 12m) | TO VALIDATE |
| 8 | Enterprise contracts | Private hospital groups (HCA UK, Spire, Nuffield, Circle), pharma medical-affairs teams, insurers | Multi-year consulting + product bundles | Master services agreement with SOWs | £50k–£300k/yr | 50–65% | 6–12 months | High — need references | Medium | Pharma: ABPI Code compliance; insurers: FCA-regulated distribution if any product bundling | 12m | ESTIMATE |
| 9 | E-learning courses (B2C/B2B2C) | Midwives, nurses, doctors, health-tech professionals, students (UK, Nigeria, Kenya, Ghana) | Self-paced courses (see §6): "Digital Maternity Essentials", "Health-Tech Commercialisation for Founders", "Care Coordination in Low-Resource Settings" | Per-course one-off | £49–£299 (UK); £10–£40 PPP-adjusted (Africa) | 85–90% after content cost | Days–weeks | Medium — content marketing, partnerships with professional bodies | Very high | No accreditation claimed until CPD provider approval obtained (TO VALIDATE, e.g., CPD Certification Service; RCM/RCOG endorsement is a separate, long process); consumer law (CRA 2015) refunds; VAT on digital services | 6m | ESTIMATE |
| 10 | Corporate training | NHS trusts (maternity units, digital teams), private providers, NGOs, health-tech scale-ups | Half-day/1-day workshops, cohort programmes | Per-cohort fixed fee | £2,500–£6,000 per workshop; £15k–£40k per cohort programme | 60–75% | 4–12 weeks | Medium | Medium | Same as #9; NHS trusts may require training to be mapped to HEE/NHS England frameworks (TO VALIDATE) | 6m | ESTIMATE |
| 11 | Subscriptions (E-Learning / community) | Individual professionals; small clinics | All-access library + monthly live clinics | Monthly/annual | £12–£29/month individual; £490–£990/yr small team (5 seats) | 80–90% | Days | Medium–high (churn) | Very high | Consumer contract rules; auto-renewal transparency | 12m | ESTIMATE |
| 12 | Technology licensing (IP) | Universities/research groups, other vendors | Licence of algorithms/data models from R&D track (MIS concept) — only after validation | Upfront + royalty | Not priceable today | 90%+ | 12–24 months | Very high — no validated IP exists | High | Requires ethics approval, data-sharing agreements, MHRA SaMD pathway, patent/trade-secret strategy | 24m+ | TO VALIDATE |
| 13 | White-label | Insurers, telecoms (MTN/Airtel/Safaricom health propositions), private hospital groups, NGOs | Branded instance of MaternaLink patient-facing layer | Set-up fee + per-user/yr | £25k–£75k set-up + £2–£8/user/yr (ESTIMATE) | 60–75% | 9–18 months | High | High | Data-controller/processor split must be explicit; telecom partners require local data residency (Nigeria, Kenya) | 24m | TO VALIDATE |
| 14 | Strategic partnerships (revenue-sharing) | Health Innovation Networks, consultancies (as sub-contractor), pharma programmes, NGOs | Co-delivered programmes; referral fees; joint bids | Revenue share 10–30% or sub-contract day rates | £10k–£100k per programme | 40–60% | 3–9 months | Medium | Medium | Bribery Act / referral-fee transparency; NHS conflict-of-interest guidance | 6m | ESTIMATE |
| 15 | Grants and institutional funding | Innovate UK (Smart, Biomedical Catalyst), NIHR i4i / AI programmes, SBRI Healthcare, Wellcome, Grand Challenges (Gates/GCC), MSD for Mothers, FCDO-funded programmes, UKRI | Non-dilutive funding for MaternaLink R&D and evaluation | Grant (typically 50–70% of eligible costs for SMEs; some 100%) | £25k (feasibility) to £500k–£1m (collaborative R&D); realistic year-1 target £50k–£150k | n/a (cost recovery; match funding required) | 3–9 months from call to award | High — competitive (single-digit to ~20% success rates ESTIMATE), needs incorporated entity, clinical partner and track record | Medium | Eligibility requires UK-registered company; NIHR requires NHS partner; ethics/HRA approval for studies; state-aid/subsidy control rules | Now (prepare) / 6m (first award realistic) | ESTIMATE |

### Reading the matrix — the three-tier launch order

| Tier | Streams | Cumulative 12-month revenue potential (ESTIMATE) | Why this order |
| --- | --- | --- | --- |
| Tier 1 (Now) | #1 consulting, #2 retainers, #15 grants (preparation) | £55k–£210k | Cash and credibility; no product needed |
| Tier 2 (6–12m) | #9 courses, #10 corporate training, #14 partnerships, #6 UK public contracts, #8 enterprise | +£20k–£90k | Convert consulting IP and network into repeatable revenue |
| Tier 3 (24m) | #3, #4, #5, #7, #11, #12, #13 (all product) | £0 in year 1; £50k–£400k in year 2–3 if pilots land | Gated by IP ownership, regulation, evidence, funding |

## 3. Unit economics per stream (ESTIMATES with assumptions)

All figures in GBP, pre-tax, excluding founder salary unless stated. Founder opportunity cost is treated as £600/day (ASSUMPTION: equivalent of a £120k salary over 200 working days) for margin calculations where the founder delivers.

| Stream | Unit | Price | Direct cost per unit | Gross margin | Contribution per unit | Key assumption |
| --- | --- | --- | --- | --- | --- | --- |
| Founder advisory day | 1 day | £1,500 (mid) | £600 founder cost + £50 travel/tools | 57% | £850 | Utilisation 40–50% in year 1 (85–100 billable days) |
| Associate consulting day | 1 day | £900 | £450–£550 (contractor day rate) | 39–50% | £350–£450 | Associates only engaged when a project is signed (no bench) |
| Discovery sprint (2 weeks) | 1 sprint | £14,000 | 8 founder days (£4,800) + 2 associate days (£1,000) + expenses £500 | 55% | £7,700 | 10 founder days of which 2 are unbilled sales/prep |
| Advisory retainer | 1 month | £4,000 | 2.5 founder days (£1,500) | 63% | £2,500 | Retainers include some "unbilled" responsiveness — 2.5 days is realistic for a 2-day contract |
| E-learning course (self-paced) | 1 sale | £149 | Content amortised (£12k build / 400 sales = £30) + platform & payment fees (£15) | 70% (rising to 88% after 400 sales) | £104 | Course platform (e.g., Teachable/Thinkific-class) at ~£100–£150/month; conversion 2–3% of landing-page traffic |
| Corporate workshop (1 day) | 1 workshop | £4,000 | 1.5 founder days (£900) + materials £150 | 74% | £2,950 | 15–25 participants; delivered on-site or virtual |
| Subscription | 1 subscriber-month | £19 | £3 platform + £2 content refresh | 74% | £14 | Churn 6–8%/month → LTV ≈ £190; CAC must be < £60 |
| MaternaLink UK site licence (future) | 1 site-year | £60,000 | Hosting £4k, support 0.3 FTE £15k, clinical safety officer time £5k | 60% | £36,000 | Only valid after ≥3 sites; first sites will be negative |
| MaternaLink Africa programme (future) | 1 enrolled woman-year | £15 (donor-funded, ESTIMATE) | SMS/WhatsApp £2.50, CHW support share £4, hosting/support £3 | 37% | £5.50 | Requires 20k+ women to cover a £110k fixed team; the £300/woman/year Ekiti figure is not used |
| Grant | 1 award | £100,000 | Match funding 30% (£30k) + 15 days bid-writing (£9k) | n/a | Net cash +£61k, plus funded R&D | Success rate 15–20% → expected value per bid ≈ £12k–£15k; write ≥4 bids/year |

Break-even for the services business (ESTIMATE): fixed monthly costs of £4,500 (founder minimum draw £3,000, tools/insurance/accountancy/subscriptions £1,500) require ~£7,500 revenue/month at 60% gross margin — i.e., 5 founder billable days or 2 retainers per month.

## 4. Twelve-month revenue build — services business

ASSUMPTIONS: incorporation in month 1; founder available 4 days/week for Vytalix; first invoice month 2; associates only on signed work; no product revenue. Three scenarios.

### 4.1 Named service packages used in the build

| Code | Package | Price | Founder days | Target buyer |
| --- | --- | --- | --- | --- |
| A1 | Founder-led advisory day | £1,200–£1,800 (model uses £1,500) | 1 | Any |
| A2 | Advisory retainer (2 days/month, 3-month minimum) | £4,000/month | 2.5 | Health-tech founders, NGOs, SME providers |
| C1 | Digital Health Discovery Sprint (2 weeks) | £14,000 | 8 | Trusts, private providers, vendors |
| C2 | Business Case & Funding Sprint (3 weeks) | £18,000 | 10 | Trusts, ICB programmes, NGOs |
| C3 | Digital Maternity Readiness Review (4 weeks) | £24,000 | 12 | Maternity units, private maternity |
| C4 | UK Market-Entry Playbook for Health-Tech (4 weeks) | £22,000 | 10 | Non-UK vendors entering NHS |
| C5 | Africa Market-Entry & Partner Scan (4 weeks) | £20,000 | 10 | UK/EU health-tech, NGOs |
| C6 | DTAC & Evidence Readiness Sprint (3 weeks) | £15,000 | 8 | Health-tech vendors |
| C7 | Grant & Investor Readiness Sprint (2 weeks) | £9,500 | 6 | Founders |
| C8 | Health Inequalities & Maternity Outcomes Review (5 weeks) | £28,000 | 14 | Trusts, ICBs, charities |
| T1 | Corporate workshop (1 day) | £4,000 | 1.5 | Any |
| E1 | E-learning course sale | £149 | — | Individuals |

### 4.2 Base case (ESTIMATE): £118k services revenue, months 1–12

| Month | Activity | Revenue (£) | Cumulative (£) | Founder billable days |
| --- | --- | --- | --- | --- |
| 1 | Incorporate, brand, website, 30 outreach conversations, 2 proposals | 0 | 0 | 0 |
| 2 | 3 advisory days (A1) sold via network; 1 retainer (A2) signed | 8,500 | 8,500 | 5.5 |
| 3 | Retainer continues; C7 sprint for a health-tech founder | 13,500 | 22,000 | 8.5 |
| 4 | Retainer; C1 discovery sprint (private provider or vendor) | 18,000 | 40,000 | 10.5 |
| 5 | Retainer; 2nd retainer starts; 2 advisory days | 11,000 | 51,000 | 7 |
| 6 | 2 retainers; T1 workshop; sub-contract 4 days to a larger consultancy (A1 at £1,200) | 16,800 | 67,800 | 10.5 |
| 7 | 2 retainers; C6 DTAC sprint | 23,000 | 90,800 | 13 |
| 8 | 2 retainers (one ends); 3 advisory days | 12,500 | 103,300 | 8 |
| 9 | 1 retainer; first e-learning course launched (20 sales); T1 workshop | 10,980 | 114,280 | 4 |
| 10 | 1 retainer; grant bid writing (unbilled); 30 course sales | 8,470 | 122,750 | 2.5 |
| 11 | 1 retainer; C3 readiness review starts (50% milestone) | 16,000 | 138,750 | 8.5 |
| 12 | Retainer; C3 completes; 40 course sales | 21,960 | 160,710 | 8.5 |

The table above is the upside of the base case if every listed engagement lands. Applying a 73% probability-weighting to project work and 90% to retainers (ASSUMPTION reflecting typical pre-revenue conversion) gives the base case of ~£118k. Founder billable days: ~87 over the year (utilisation ~42% of 208 available days), leaving ~120 days for sales, MaternaLink, fundraising and grant writing — which is the real constraint.

### 4.3 Scenario range

| Scenario | 12-month services revenue | Assumptions | Cash implication |
| --- | --- | --- | --- |
| Downside | £55k | 1 retainer for 6 months, 2 sprints, 20 advisory days, no e-learning | Founder cannot draw a salary; MaternaLink work stalls; must decide by month 6 whether to take employment |
| Base | £118k | As §4.2 probability-weighted | Covers founder draw of £3k/month, legal/IP (£8–12k), brand/web (£5k), insurance/accountancy (£3k); ~£20k surplus toward MaternaLink |
| Upside | £210k | 3 concurrent retainers by month 6, one NHS/ICB C8 review via sub-contract, e-learning at 150 sales | Funds a part-time product lead (£30k) and a clinical safety officer contract; positions for Innovate UK match |

Sensitivity (ESTIMATE): each additional retainer adds ~£36k/year; each 10-point change in founder utilisation changes revenue by ~£30k; a 20% day-rate change moves revenue ~£18k.

## 5. Vytalix Consulting — service catalogue

Positioning: "The digital-health strategy boutique that has worked on both sides of the UK–Africa corridor." (PROPOSED; this claim is only usable once the founder's credentials and first engagements support it — TO VALIDATE against the founder's CV.)

| # | Offer | Problem it solves | Deliverables | Duration | Price (fixed) | Ideal buyer | Proof required to sell |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Digital Health Discovery Sprint | "We know we need digital but not what, for whom, or what it costs" | Problem framing, user/stakeholder interviews (10–15), option appraisal, 90-day roadmap | 2 weeks | £14,000 | Private provider, NHS service line, vendor | Founder track record; a sample deck |
| 2 | Business Case & Funding Sprint | Need an HM Treasury Green Book-style or board-ready case | Strategic/economic/commercial/financial/management case, benefits model, funding routes | 3 weeks | £18,000 | NHS programme lead, charity, NGO | Familiarity with Green Book five-case model |
| 3 | Digital Maternity Readiness Review | Maternity units facing digital record adoption, CNST Maternity Incentive Scheme data actions, CQC findings | Current-state map, gap analysis vs Three Year Delivery Plan and MSDS requirements, prioritised plan | 4 weeks | £24,000 | Head of Midwifery, Maternity Digital Lead, Divisional Director | Clinical advisor (midwife/obstetrician) on the team (TO RECRUIT) |
| 4 | UK Market-Entry Playbook | Non-UK health-tech wants NHS customers and does not understand ICBs, DTAC, procurement | NHS structure brief, buyer map, regulatory/assurance checklist (DTAC, DCB0129, DSPT, MHRA), pricing benchmarks, 12-month plan | 4 weeks | £22,000 | US/EU/African health-tech scale-up | Case examples; an NHS-experienced associate |
| 5 | Africa Market-Entry & Partner Scan | UK/EU vendor or NGO wants to enter Nigeria/Kenya/Ghana | Country scorecard, regulatory brief (NDPA, NAFDAC where relevant, SHA/NHIA), partner long-list, entry model options | 4 weeks | £20,000 | Health-tech, NGO, foundation | In-country associate network (TO BUILD) |
| 6 | DTAC & Evidence Readiness Sprint | Vendor blocked by NHS assurance | DTAC self-assessment, clinical safety case skeleton (DCB0129), DSPT plan, NICE ESF evidence-tier mapping | 3 weeks | £15,000 | Health-tech vendor | Contracted Clinical Safety Officer |
| 7 | Grant & Investor Readiness Sprint | Founder needs a fundable narrative and a grant pipeline | Investor deck review/rewrite, financial model sanity check, grant calendar (Innovate UK, NIHR, SBRI), 3 bid outlines | 2 weeks | £9,500 | Pre-seed/seed founder | Founder's own fundraising experience; grant wins would strengthen later |
| 8 | Health Inequalities & Maternity Outcomes Review | Trust/ICB must respond to MBRRACE-UK disparities, CQC or Ockenden-style findings | Data review, listening exercise with service users (via community partners), equity action plan, measurement framework | 5 weeks | £28,000 | Trust, ICB, maternity charity | Community-partner relationships (e.g., with organisations like Five X More — no relationship claimed) |
| 9 | Fractional Chief Digital/Strategy Officer | Organisation needs senior capacity without a hire | 4–6 days/month embedded | 6 months | £5,500–£8,000/month | Scale-up, private provider, NGO | Founder seniority; references |
| 10 | Programme Evaluation Lite | Donor/NGO needs an evaluation of a digital health programme | Theory of change, indicators, mixed-methods review, report | 6 weeks | £26,000 | NGO, foundation, state programme | Evaluation methodology; partner with a university group for rigour |

Catalogue rules: (a) fixed price, fixed scope, written change control; (b) 50% on signing for engagements under £20k, 40/30/30 milestones above; (c) every engagement produces at least one anonymised, reusable asset (template, checklist, benchmark) that feeds E-Learning; (d) no engagement is accepted that would create a conflict with MaternaLink's future customers without disclosure.

## 6. Vytalix E-Learning model

### 6.1 Product ladder

| Tier | Product | Format | Price | Launch | Label |
| --- | --- | --- | --- | --- | --- |
| Free | "Digital maternity in 10 minutes" primers, newsletter, webinars | Video/email | £0 | Month 6 | PROPOSED |
| Courses | 1. Digital Maternity Essentials for Midwives and Maternity Teams; 2. Health-Tech Commercialisation in the NHS; 3. Care Coordination in Low-Resource Maternal Health Settings; 4. Grants and Investor Readiness for Health-Tech Founders | Self-paced, 3–6 hours, quizzes, downloadable templates | £49–£299 (UK); £10–£40 regional pricing (Nigeria, Kenya, Ghana) | Courses 2 and 4 in month 9 (lowest clinical risk, founder-authored); courses 1 and 3 in month 12–15 (need clinical co-authors) | ESTIMATE |
| Subscription | All-access library + monthly live clinic + community | Monthly/annual | £19/month, £190/year | Month 12 | ESTIMATE |
| Corporate licence | Seat-based access + one live workshop per year | Annual | £2,500 (10 seats), £9,000 (50 seats), £25,000 (250 seats) | Month 12 | ESTIMATE |
| University licence | Course embedded in midwifery/public health/health informatics programmes | Annual per programme | £3,000–£8,000 | Month 15–18 | TO VALIDATE (universities usually want co-authorship or accreditation) |
| Co-branded (NGO/partner) | Localised course for a programme's health workers | Project fee + per-learner | £15k–£40k + £5–£15/learner | Month 18 | TO VALIDATE |

### 6.2 Economics (ESTIMATE)

Content build: £8k–£15k per course (founder time 8–12 days + clinical co-author fee £2–4k + video/edit £2k).

Platform: £1,200–£2,400/year; payment fees ~3%.

Year-1 (from launch month 9) target: 150–250 course sales (£20k–£35k), 2 corporate licences (£5k–£12k). Year-2 target: £80k–£150k, of which 40% corporate.

Gross margin after content amortisation: 70–88%.

### 6.3 Accreditation caveats (must be respected in all copy)

Vytalix holds no accreditation and must not claim CPD accreditation, RCM/RCOG/NMC endorsement or university credit. Language: "designed to support continuing professional development"; "certificate of completion" only.

Route to accreditation (TO VALIDATE): (1) CPD Certification Service or similar independent CPD accreditor — typically weeks to months and a fee per course; (2) partner with a university for credit-bearing modules; (3) RCM/RCOG endorsement processes are institution-specific and slow. Budget £3k–£8k and 6–9 months.

Clinical content must have a named clinical author and reviewer, a review date and a disclaimer that content does not replace local clinical guidance.

In Nigeria/Kenya/Ghana, professional councils (e.g., Nursing and Midwifery Council of Nigeria; Nursing Council of Kenya) have their own CPD-point rules — do not imply CPD points until an accreditation is granted (TO VALIDATE).

## 7. MaternaLink revenue logic (equity layer) — stated conservatively

| Horizon | Milestone | Revenue type | Indicative value | Gate |
| --- | --- | --- | --- | --- |
| Months 0–6 | IP ownership resolved; product re-based to v1 (non-diagnostic care-coordination); prototype audited | None | £0 | Agreement with David Agunede (see 02_GROUP_STRUCTURE.md) |
| Months 6–12 | Clinical advisory board formed; DTAC self-assessment; DPIA; design partner (1 UK maternity unit or 1 African facility) signed as unpaid or grant-funded pilot | Grant (Innovate UK/NIHR/SBRI/foundation) | £50k–£150k | Incorporated entity; clinical partner letter |
| Months 12–24 | Paid pilot(s) | Implementation + pilot licence | £20k–£150k per pilot | Evidence from design partner; DCB0129 safety case |
| Months 24–36 | Scale contracts | SaaS / programme contracts | £150k–£600k ARR (ESTIMATE if 3–5 UK sites or 1 state programme) | Outcome evidence; NICE ESF tier; local partner in Africa |

No forecast beyond this is credible today. The Ekiti proposal's £4.5m/£9m/£36m phases (VERIFIED as a proposal only) are excluded from all plans until there is a signed contract or written funding commitment.

## 8. "What must be true" — validation list

| # | Assumption to validate | How to test | By when | Owner | Kill/pivot signal |
| --- | --- | --- | --- | --- | --- |
| 1 | Founder can win 8–10 billable days/month within 90 days | 30 outreach conversations, 6 proposals, 2 signed in 90 days | Month 3 | Founder | <1 signed engagement by month 3 → reduce to part-time, seek fractional role |
| 2 | Buyers accept £1,200–£1,800/day for founder-led work | Test three price points in proposals; record objections | Month 3 | Founder | Consistent push to <£900 → reposition as associate-led and cut costs |
| 3 | MaternaLink IP can be brought into Vytalix on acceptable terms | Structured negotiation with David Agunede, solicitor-led | Month 2 | Founder + solicitor | No agreement by month 4 → build product freshly under Vytalix or drop MaternaLink from the equity story |
| 4 | A UK maternity unit will act as unpaid design partner | 10 approaches via Health Innovation Networks, clinical advisors, LinkedIn | Month 9 | Founder + clinical advisor | Zero interest → focus product on Africa/private first |
| 5 | The prototype is safe and usable enough to demo | Independent technical and security review of the Vercel prototype; confirm no real patient data held | Month 2 | CTO/contractor | Real patient data without lawful basis → stop, remediate, document |
| 6 | Government/donor willingness to pay per woman in Nigeria is materially above £5–£15/yr | Interviews with MSD for Mothers programme leads, state MoH digital leads, GFF country teams; compare to mDoc's public programme scale | Month 9 | Founder | WTP < cost → Africa is a donor-funded evidence market, not a revenue market |
| 7 | A grant can be won within 12 months | Submit ≥4 bids (Innovate UK Smart, SBRI Healthcare, NIHR i4i Connect, one foundation) | Month 12 | Founder | 0/4 → rely on services + angels; reduce R&D scope |
| 8 | E-learning can acquire learners at CAC < £60 | £1,000 paid + organic test around course 2 | Month 10 | Founder | CAC > £150 → B2B-only distribution |
| 9 | The Vytalix name is clearable | UK IPO, EUIPO, USPTO searches; solicitor opinion | Month 1 | Founder + IP adviser | Conflict with VITALIX LTD / Vytalyx Inc. → rename before brand spend |
| 10 | SEIS/EIS advance assurance is obtainable | Application post-incorporation | Month 2–3 | Accountant | Refusal → restructure or reduce angel expectations |

## Priorities / Risks / Next actions

Priorities (next 90 days)

Incorporate, clear the name, obtain SEIS/EIS advance assurance, open bank account, insure (PI £1m, PL) — prerequisites for invoicing.

Sell Tier-1 services: 30 conversations, 6 proposals, 2 signed (target £15k booked by day 90).

Resolve MaternaLink IP with David Agunede (term sheet by day 60).

Write the first grant bid (Innovate UK Smart or SBRI Healthcare) with a clinical partner letter of support — even an unsuccessful bid creates reusable material.

Build the two founder-authored e-learning courses in parallel with consulting (evenings/low-utilisation weeks).

Risks

Founder bandwidth: services, product, fundraising and grants compete for the same 200 days. Mitigation: hard cap of 10 billable days/month; hire a part-time product lead only from services surplus or grant.

Credibility gap: no references, no incorporated entity. Mitigation: sub-contract to established consultancies for first NHS work; publish two thought-leadership pieces per month.

Naming/trademark conflict: could void brand spend. Mitigation: clear before spending on brand.

Regulatory creep: any drift of MaternaLink toward "risk prediction" makes it a medical device and freezes revenue. Mitigation: v1 scope statement signed off by clinical advisor and kept in the product charter.

Concentration: one or two retainers could be >50% of revenue. Mitigation: no client >40% of trailing 6-month revenue by month 9.

Next actions (owner: founder unless stated)

Day 0–14: name clearance; incorporation; accountant; SEIS/EIS application; PI insurance quotes.

Day 0–30: service catalogue one-pagers (10); price list; proposal template; 30-name target list from 06_CUSTOMER_SEGMENTS.md.

Day 14–60: solicitor engaged on IP options (see 02_GROUP_STRUCTURE.md §3); technical audit of the prototype.

Day 30–90: first two engagements delivered; first grant bid drafted; clinical advisor recruited.

Month 6 review: compare actuals to base case; decide on associate bench and e-learning launch date.