# 18 — VYTALIX 90-DAY EXECUTION PLAN (Mon 14 September – Sat 12 December 2026)

Owner: Founder (CEO/COO) · Status: PROPOSED · Version: 1.0 (8 September 2026) · Day 1 = Monday 14 September 2026 · Governed by: /FACTS_BASE.md · Related: /docs/00_MASTER_AUDIT.md (problems and immediate actions), /docs/16_ORGANISATION_AND_SOPS.md (SOPs referenced by number), /docs/17_FOUNDER_OPERATING_SYSTEM.md (rituals and KPI definitions), /docs/19_FIRST_30_DAYS.md (day-by-day detail for Days 1–30), /docs/20_DECISION_FRAMEWORK.md (scoring used at the gates), /investors/ (CRM, call lists, outreach engine)

## Executive view

Ninety days to move Vytalix from an audit score of 11/100 (pre-formation) to 35–40 (formed, trading, evidenced enough to open investor conversations honestly). Four phases: Foundation (Days 1–7), Commercial infrastructure (Days 8–30), Investor acquisition and market validation (Days 31–60), Product and commercial launch (Days 61–90).

Four decision gates control the plan: Incorporate (decide Day 1, execute by Day 12), IP resolution with David Agunede (heads of terms Day 7, signed Day 30, hard stop Day 60), MaternaLink re-scope (adopt the non-diagnostic v1 intended-use statement Day 3), Ekiti go/no-go (Day 60, after a status call, an mDoc conversation and a two-state scorecard). No investor outreach begins until gates 1–3 are closed — the pre-conditions in /investors/OUTREACH_ENGINE.md.

Revenue is the first priority throughout: the sales quota (40 contacts, 20 conversations, 5 discovery calls, 2 proposals per week) starts Day 8, the first signed engagement is due Day 30, three by Day 90, £15k–£30k contracted (ESTIMATE range, not a forecast).

The investor phase uses the assets already built in /investors/: 253 researched investors, a Top 25 with per-investor scripts, four call lists and an 18-stage pipeline. Target by Day 90: 125 contacted, 10 meetings, 2 active discussions, one grant bid submitted — with £0 received assumed in the base case.

Cash cost of the 90 days is £9k–£19k (ESTIMATE: legal, trademark, incorporation, insurance, tooling, CSO, prototype audit, report design), against £15k–£30k contracted revenue if the sales targets hold. 62 actions are listed with owner, calendar deadline, dependency, expected outcome, KPI and priority (P0 = the plan fails without it; P1 = the phase fails without it; P2 = valuable, movable).

## 1. Calendar and phase map

| Phase | Days | Dates | Theme | Exit criteria (all must be true) |
| --- | --- | --- | --- | --- |
| 1 Foundation | 1–7 | Mon 14 – Sun 20 Sept | Stop the bleeding: IP, name, claims, entity decision, operating rhythm | Standstill letter signed; heads of terms sent; name decision made; claims retired; intended-use adopted; CRM live; 40 first touches sent |
| 2 Commercial infrastructure | 8–30 | Mon 21 Sept – Tue 13 Oct | Entity, bank, insurance, ICO, contracts; sales engine at full quota; website; first engagement; prototype audit; data room v1 | Incorporated; IP deed signed; first SOW signed; prototype audit report; data room v1; SEIS/EIS application submitted; first board meeting held |
| 3 Investor acquisition + market validation | 31–60 | Wed 14 Oct – Thu 12 Nov | Outreach to Call Lists 1–2; 15 UK discovery interviews; Ekiti/mDoc/state scorecard; advisory board; CSO; trademark filed; report 1 drafted | 75 investors contacted, 4+ meetings; 15 UK interviews done; 2 advisers signed; CSO engaged; Ekiti go/no-go decided; trademark filed |
| 4 Product + commercial launch | 61–90 | Fri 13 Nov – Sat 12 Dec | Call List 3; report 1 published; webinar; DPIA v0.1 and safety-case skeleton; MVP build decision; grant bid; Cyber Essentials; Q1 2027 plan | 3 SOWs signed; 10 investor meetings; report published; Cyber Essentials certified; MVP build/no-build decision minuted; audit ≥ 35 |

Week numbering used below: Week 1 = 14–20 Sept … Week 13 = 7–12 Dec.

## 2. Decision gates

| Gate | Decision | Decide by | Inputs required | Options and the default | Owner / approver | Consequence of "no" or slippage |
| --- | --- | --- | --- | --- | --- | --- |
| G-A Incorporate | Incorporate "Vytalix Group Ltd" (or reserve name) in England and Wales now | Decision Mon 14 Sept (Day 1); execute by Fri 25 Sept (Day 12) | Trademark/Companies House knock-out result (Day 5); accountant appointed; registered office; share capital decision | (i) Incorporate with "Vytalix" if clearance is clean or low-risk — default; (ii) incorporate under a reserve name and trade as Vytalix pending attorney opinion; (iii) delay — not acceptable beyond Day 12 | Founder; solicitor advises on name risk | Every downstream item (bank, ICO, insurance, SEIS/EIS, contracts, grants, investor outreach) slips day-for-day |
| G-B IP resolution | Documented title or exclusive licence to MaternaLink IP; David Agunede's role defined | Heads of terms Sun 20 Sept (Day 7); signed deed Tue 13 Oct (Day 30); hard stop Thu 12 Nov (Day 60) | IP audit questionnaire; prototype audit (Day 30); solicitor draft; standstill letter (Week 1) | (1) Assignment for vested equity — default; (2) exclusive licence with option to acquire — fallback; (3) no agreement by Day 60 → clean-room rebuild of v1, no use of his materials or the "Maternal Link" name (/docs/02_GROUP_STRUCTURE.md §3; /docs/15_LEGAL_AND_REGULATORY.md §8.3) | Founder; solicitor; board minutes the outcome | Until signed: MaternaLink is described as "a concept Vytalix is developing with a collaborator"; no investor pitch names it as owned |
| G-C MaternaLink re-scope | Adopt the v1 intended-use statement (non-diagnostic care-coordination); retire the 2025 AI claims externally; move the AI risk score to a v3 research track | Wed 16 Sept (Day 3) | /docs/04_MATERNALINK_PRODUCT_STRATEGY.md §21.1; FACTS_BASE A4 | Adopt — default; the alternative (keep predictive positioning) requires MHRA SaMD pathway, data and ethics that do not exist, and is scored KILL-now in /docs/20_DECISION_FRAMEWORK.md | Founder; recorded in the decision log; ratified at first board meeting | Regulatory and diligence exposure persists; every deck and post is unusable |
| G-D Ekiti go/no-go | Continue, re-scope or stop the Ekiti State conversation; choose partner / differentiate / move state | Thu 12 Nov (Day 60) | Ekiti status call (by Day 26); mDoc complementarity conversation (by Day 55); two-state scorecard (Oyo, Kano or as scored; by Day 55); IP outcome (G-B); decision-framework score | (a) Re-scoped partner-aware pilot option offered to Ekiti if the ministry identifies a gap and mDoc is open to complementarity; (b) move state with an NGO/donor cohort — default if (a) fails; (c) stop Nigeria government work for 2 quarters and prioritise NGO cohorts. The £4.5m/£300-per-woman proposal is not restated under any option | Founder; advisory board #4 consulted; board approves any government proposal (reserved matter) | Without a decision the Nigeria story stays an unvalidated proposal in investor diligence |

Gate reporting: each gate is a row in the strategic-projects tracker and a line in the Friday review (§5 of the founder OS).

## 3. Phase 1 — Foundation (Days 1–7, Mon 14 – Sun 20 September 2026)

| # | Task | Owner | Deadline | Dependency | Expected outcome | KPI | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Install the operating rhythm: calendar blocks, daily log, decision log, both CSVs live | Founder | Mon 14 Sept | None | Every later action has a home and a review date | Friday review completed 18 Sept | P0 |
| 1.2 | Name clearance: UK IPO, EUIPO, USPTO and Companies House knock-out searches on "Vytalix"; brief a trademark attorney; shortlist two reserve names | Founder → attorney | Fri 18 Sept | None | Written clearance memo: proceed / proceed with risk / change | Memo received; decision logged | P0 |
| 1.3 | Incorporation decision (G-A): entity name, registered office, share capital, sole director; shortlist and instruct accountant | Founder | Mon 14 Sept (decision); Fri 18 Sept (accountant instructed) | 1.2 for final name | Ready to file the day clearance lands | Accountant engagement letter signed | P0 |
| 1.4 | David Agunede conversation: role, intent, authorship of code/decks, Ekiti status; send IP audit questionnaire; propose mutual standstill and confidentiality letter (60 days) | Founder | Conversation Wed 16 Sept; standstill signed Fri 18 Sept | None | Facts established; no third-party dealings on MaternaLink during negotiation | Standstill signed; questionnaire returned | P0 |
| 1.5 | Draft and send IP heads of terms (Option 1 assignment-for-equity as the opening position; Option 2 fallback) | Founder → solicitor | Sun 20 Sept (Day 7) | 1.4; solicitor instructed Fri 18 Sept | Written terms on the table before Day 8 | Heads of terms sent; response date agreed | P0 |
| 1.6 | Instruct a fixed-fee start-up solicitor: founder IP assignment, David Agunede deed, MSA/SOW/NDA review, name-risk opinion | Founder | Fri 18 Sept | 1.2, 1.3 | Legal bench in place | Engagement letter; fee cap £4k–£9k (ESTIMATE) | P0 |
| 1.7 | Adopt MaternaLink v1 intended-use statement (G-C); retire the 2025 deck and £36m headline from all external use; label every asset "in development" | Founder | Wed 16 Sept (Day 3) | None | Claims exposure removed | Zero external artefacts with retired claims | P0 |
| 1.8 | Prepare the first-10-investor-call pack (Top 25 list re-read, one-pager outline, objections table) — preparation only, no outreach | Founder | Fri 18 Sept | None | Ready to move the day pre-conditions close | Pack drafted; 10 names with verified routes | P1 |
| 1.9 | Create HubSpot Free CRM; import pipeline stages and fields; build the 150-contact ICP list (S1/S2) with source URLs | Founder | CRM Tue 15 Sept; list Fri 18 Sept | None | Sales engine can run from Week 2 | 150 contacts with source URLs | P0 |
| 1.10 | Send the first 40 outreach touches (E1/L1 templates); rewrite the founder LinkedIn profile; publish Post 1 | Founder | Fri 18 Sept | 1.9; 1.7 | First conversations booked; stage-honest public presence | 40 touches; ≥ 3 replies by Day 10 | P0 |
| 1.11 | Reserve domain and social handles for the chosen name (post clearance); set up Google Workspace on the domain | Founder | Fri 18 Sept (or within 24 h of clearance) | 1.2 | Professional email before first proposal | Domain live; email working | P1 |
| 1.12 | Finance baseline: confirm founder capital available (TO CONFIRM); open a ring-fenced founder account pending the company account; 13-week cash-flow v0 | Founder | Fri 18 Sept | None | Runway known | Cash-flow v0 exists; capital figure logged | P1 |
| 1.13 | Time allocation rule adopted (≥ 70% Vytalix); Kemek Enterprise declared in the conflicts register | Founder | Mon 14 Sept | None | Focus risk controlled | Weekly time audit line | P1 |
| 1.14 | Weekend (19–20 Sept): read-only — review the week, prepare Week 2 plan; no outreach | Founder | Sun 20 Sept | — | Rested; Week 2 planned | Weekly plan written | P2 |

## 4. Phase 2 — Commercial infrastructure (Days 8–30, Mon 21 September – Tue 13 October 2026)

| # | Task | Owner | Deadline | Dependency | Expected outcome | KPI | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1 | File incorporation (digital, £100); founder IP assignment signed the same day; statutory registers opened | Founder + accountant + solicitor | Target Wed 23 Sept; hard deadline Fri 25 Sept (Day 12) | G-A; 1.2 | Legal entity exists | Certificate of incorporation | P0 |
| 2.2 | Open business bank account; Xero live; Corporation Tax registration | Founder + accountant | Fri 2 Oct (Day 19) | 2.1 | Can invoice and receive funds | Account open; first reconciliation | P0 |
| 2.3 | ICO registration (Tier 1, £52); legitimate-interests assessment for outreach; privacy notice drafted | Founder | Fri 2 Oct | 2.1 | Lawful CRM and newsletter | ICO reference number | P0 |
| 2.4 | Professional indemnity and public liability insurance bound (before first paid engagement) | Founder → broker | Fri 2 Oct | 2.1 | Insured to deliver | Policy schedule | P0 |
| 2.5 | Sales engine at full weekly quota from Week 3: 40 contacts, 20 conversations, 5 discovery calls, 2 proposals (SOP 01) | Founder | Weekly from Mon 28 Sept | 1.9, 1.10 | Pipeline forming | Weekly quota met 3/3 weeks | P0 |
| 2.6 | First 5 discovery calls held; 2 proposals sent | Founder | Sun 27 Sept (Day 14) | 2.5 | First real buyer feedback on packages | 5 calls; 2 proposals | P0 |
| 2.7 | MSA, SOW, NDA and contractor agreement templates sent to solicitor; pre-incorporation engagements (if any) on personal contract with novation clause | Founder → solicitor | Fri 25 Sept (sent); Fri 9 Oct (returned) | 1.6 | Contract-ready | Templates approved | P0 |
| 2.8 | First signed engagement (target: A1 advisory days or C7 sprint); first invoice raised the same day | Founder | Tue 13 Oct (Day 30) | 2.5–2.7, 2.4 | Revenue exists; break-even path visible | 1 SOW; £3k–£10k (ESTIMATE) | P0 |
| 2.9 | Pricing re-base memo: services price list confirmed; MaternaLink indicative range £6–£40/woman/year platform layer (ESTIMATE) replaces the £300 figure in every document; cost-to-serve model v0 | Founder | Mon 5 Oct (Day 22) | G-C | Credible pricing for Nigeria and UK conversations | Memo adopted; old figure absent from all materials | P1 |
| 2.10 | Prototype audit of the Vercel dashboard: authorship, licences, secrets, data held, security posture (SOP 08; product strategy §25); engage fractional CTO for the audit | Founder + fractional CTO | Tue 13 Oct (Day 30) | 1.4 (access); standstill | Reuse vs rebuild decision; no real data risk | Audit report; pass / conditions / fail | P0 |
| 2.11 | IP deed and shareholders' agreement executed with David Agunede (G-B), or licence fallback documented | Founder + solicitor | Tue 13 Oct (Day 30) | 1.5; 2.10 | Vytalix can say what it owns | Signed deed; cap table updated | P0 |
| 2.12 | Website v1 published from /website with legal pages (privacy, cookies, terms); newsletter tool selected with double opt-in | Founder | Site Fri 9 Oct; newsletter Fri 2 Oct | 1.11; 2.1; 2.3 | Conversion surface exists | Site live; forms tested; 300 sessions Month 1 | P1 |
| 2.13 | Content cadence: 3 posts/week; company page live after name decision; content calendar tracking | Founder | Continuous; page live by Fri 25 Sept | 1.2 | Visibility for sales and investors | 12 posts/month; 500 relevant followers | P1 |
| 2.14 | Ekiti status call: learn the outcome of the March 2026 proposal; log facts only; no new offer made | Founder (with David Agunede if agreed under standstill) | Fri 9 Oct (Day 26) | 1.4 | Facts for G-D | Call held; status logged as KNOWN | P1 |
| 2.15 | Advisory-board recruitment starts: shortlist 12 names across the six profiles; 6 approaches sent (obstetrics/midwifery and regulatory/CSO first) | Founder | Fri 9 Oct | 2.1 (options need a company) | Credibility pipeline | 6 approaches; 3 conversations booked | P1 |
| 2.16 | Data room v1 index and one-pager drafted; deck v1 (stage-honest); financial model summary from /finance/Vytalix_Financial_Model_3yr.xlsx | Founder | Fri 9 Oct | G-C; 2.11 for the IP summary | Investor pre-condition (4) met | Data room index complete; one-pager v1 | P0 |
| 2.17 | SEIS/EIS advance-assurance application drafted with accountant; submitted as soon as an identified prospective investor exists (TO VALIDATE HMRC expectation) | Founder + accountant | Drafted Fri 9 Oct; submitted by Tue 13 Oct | 2.1 | Pre-condition (5) met ("applied for") | Application submitted | P0 |
| 2.18 | Policy set adopted at first board meeting: conflicts, anti-bribery, data protection, clinical claims sign-off, delegated authorities; SOPs adopted; independent NED search started | Founder | Tue 13 Oct (Day 30) | 2.1 | Governance is a credibility asset | Minutes; policies signed | P1 |
| 2.19 | UK discovery interview recruitment: 30-name list (midwives, digital maternity leads, private providers, charities) and consent form; first 4 interviews held | Founder | List Fri 2 Oct; 4 interviews by Tue 13 Oct | 1.7 | Home-market validation begins | 4 interviews logged | P1 |
| 2.20 | Grant calendar check: Innovate UK Smart, SBRI Healthcare, NIHR i4i, Grand Challenges Canada — open calls, eligibility, deadlines (TO VALIDATE each) | Founder | Fri 9 Oct | 2.1 | Bid/no-bid list for Phase 3–4 | Calendar with ≥ 1 eligible call | P2 |
| 2.21 | Virtual assistant brief written; engage if admin > 8 hrs/week for 2 weeks | Founder | Fri 16 Oct (decision) | Time audit | Founder time protected | VA engaged or trigger not met (logged) | P2 |
| 2.22 | First monthly close (partial Month 0/1) and audit re-score | Founder + accountant | Wed 14 Oct | 2.2 | Score trend starts | Score logged (target ≥ 20) | P1 |

## 5. Phase 3 — Investor acquisition + market validation (Days 31–60, Wed 14 October – Thu 12 November 2026)

Pre-condition check on Wed 14 Oct: incorporated (2.1) · IP heads of terms signed and deed executed or licence documented (2.11) · 2025 claims retired (1.7) · one-pager and data room v1 (2.16) · SEIS/EIS submitted (2.17). If any is open, Phase 3 investor tasks (3.1–3.6) wait; market-validation tasks (3.7 onwards) proceed.

| # | Task | Owner | Deadline | Dependency | Expected outcome | KPI | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Log pre-conditions as met in the decision log; solicitor sign-off on deck disclaimers and financial-promotion wording (/investors/OUTREACH_ENGINE.md §9) | Founder + solicitor | Wed 14 Oct (Day 31) | Phase 2 exits | Outreach is lawful and truthful | Sign-off recorded | P0 |
| 3.2 | Re-verify Call List 1 (Top 25, /investors/CALL_LISTS.md): team pages, mandates, routes; update "Last Verified" in /investors/VYTALIX_INVESTOR_CRM.csv | Founder / VA | Fri 16 Oct | 3.1 | No stale outreach | 25/25 re-verified | P0 |
| 3.3 | Call List 1 outreach (Weeks 6–7): phone-first where a verified public number exists; per-investor scripts in /investors/OUTREACH_TOP25.md; cadence call → email → +4 → +10 → +21 | Founder | Fri 30 Oct (Day 47) | 3.2 | First investor conversations | 25 contacted; ≥ 3 meetings booked | P0 |
| 3.4 | Call List 2 (Next 50) outreach (Weeks 8–9) | Founder | Thu 12 Nov (Day 60) | 3.3 | Pipeline breadth | 50 contacted; ≥ 2 further meetings | P1 |
| 3.5 | Investor meetings run to the 30-minute structure; written answer to every objection within 48 h; referral ask in every meeting; monthly investor update starts (first: Thu 5 Nov) | Founder | Continuous | 3.3 | Meetings convert to second meetings | 4 meetings held; 2 second meetings; 4 referrals | P0 |
| 3.6 | Weekly CRM regeneration (python3 investors/build_crm.py) and Investment KPI rows updated | Founder / VA | Every Friday | 3.3 | Dashboard reflects reality | 100% weekly | P1 |
| 3.7 | UK discovery interviews: 15 completed (midwives, digital maternity leads, private providers, charities); synthesis note feeding PRD personas and report 1 | Founder | Thu 12 Nov (Day 60) | 2.19 | Home-market validation evidence | 15 interviews; synthesis published internally | P0 |
| 3.8 | mDoc complementarity conversation (one exploratory call; no claimed relationship; wording per partnership rules) | Founder | Fri 6 Nov (Day 54) | 2.14; G-C | Facts on partner / differentiate | Call held; outcome logged | P1 |
| 3.9 | Two-state scorecard (market doc §2.1; candidates Oyo, Kano or as scored) with desk research and 3 in-country conversations each (NGOs, teaching hospitals, SPHCDA contacts through public routes) | Founder (+ advisory board #4 if appointed) | Fri 6 Nov | 2.9 | Move-state option evidenced | Scorecard complete; ≥ 6 conversations | P1 |
| 3.10 | Ekiti go/no-go (G-D) decided and minuted; if "re-scoped pilot option", a one-page partner-aware option (LGA pilot, ≤ £0.5m/year envelope, £6–£40/woman/year platform layer, 12-month evaluation, defined exit) drafted for board approval before sending | Founder; board | Thu 12 Nov (Day 60) | 2.14, 3.8, 3.9, G-B | Nigeria story is a decision, not a hope | Decision logged; option (if any) board-approved | P0 |
| 3.11 | Advisory board: 2 members signed (target profiles #1/#2 clinical and #5 regulatory/CSO); 2 more at "agreed in principle" | Founder | Thu 12 Nov | 2.15 | Credibility and clinical sign-off capacity | 2 letters of appointment | P0 |
| 3.12 | Clinical Safety Officer identified (Day 45) and engaged (Day 60); hazard log opened; regulatory qualification opinion commissioned | Founder | Identified Wed 28 Oct; engaged Thu 12 Nov | 2.18 | Clinical governance exists | CSO engagement letter; hazard log v0 | P0 |
| 3.13 | Trademark application filed (UK classes 9, 41, 42, 44; £205 + £60/class) for the cleared name | Founder → attorney | Wed 28 Oct (Day 45) | 1.2; 2.1 | Brand protected | Filing receipt | P1 |
| 3.14 | Sales engine continues at quota; second signed engagement; first engagement delivered to SOP 06 standard (kick-off ≤ 3 days, first value ≤ 10 days) | Founder | 2nd SOW by Fri 6 Nov | 2.5–2.8 | Revenue compounding; a reference forming | 2 SOWs cumulative; NPS ≥ 8 on first delivery | P0 |
| 3.15 | Report 1 ("The State of Digital Maternal Care Coordination: UK and Nigeria, 2026"): interviews (from 3.7) complete; draft written | Founder | Draft Fri 13 Nov | 3.7 | Credibility anchor for Phase 4 | Draft ≥ 20 pages; n ≥ 15 interviews | P1 |
| 3.16 | Grant bid: decide bid/no-bid on the best-fit open call (2.20) using the decision framework; start writing if "bid" | Founder | Decision Fri 23 Oct; writing from Mon 26 Oct | 2.1; 3.12 (clinical partner may be needed) | Non-dilutive path opened | Bid/no-bid minuted | P1 |
| 3.17 | Newsletter issue 1 sent (fortnightly thereafter); article 1 published | Founder | Fri 23 Oct | 2.12 | Nurture list grows | 100 subscribers by Day 60 | P2 |
| 3.18 | PRD sign-off review with CSO and clinical adviser; line-crossing check on every Must requirement | Founder + CSO + adviser | Thu 12 Nov | 3.11, 3.12 | PRD credible to a buyer and a regulator | PRD v0.2 signed off | P1 |
| 3.19 | Cyber Essentials self-assessment started; password manager, MFA and device encryption confirmed on every account | Founder | Thu 12 Nov | 2.1 | Security baseline | Self-assessment in progress | P2 |
| 3.20 | Monthly close (Month 1) and audit re-score; management report; board meeting 2 | Founder + accountant; board | Thu 5 Nov; board Tue 10 Nov | 2.22 | Score trend visible | Score ≥ 27 (target) | P1 |

## 6. Phase 4 — Product + commercial launch (Days 61–90, Fri 13 November – Sat 12 December 2026)

| # | Task | Owner | Deadline | Dependency | Expected outcome | KPI | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 | Call List 3 (Next 75) outreach (Weeks 10–12); referrals from Lists 1–2 worked first | Founder | Fri 4 Dec (Day 82) | 3.4 | Investor pipeline at target breadth | 125 contacted cumulative; 10 meetings cumulative | P1 |
| 4.2 | Second meetings and data-room diligence: Q&A log; 48-hour answers; advisers introduced with consent | Founder | Continuous | 3.5 | 2 active investment discussions | 2 at "Due Diligence" or "Investment Discussion" | P0 |
| 4.3 | Report 1 designed (freelance, £1k–£2k ESTIMATE) and published on the website with download form; PR pitch to 3 relevant outlets | Founder + designer | Publish Fri 20 Nov (Week 10); PR by Fri 27 Nov | 3.15 | Authority asset live | 150 downloads by Day 90; 1 earned mention | P1 |
| 4.4 | Webinar 1 delivered (Tue 17 Nov, 12:30–13:15 UK; TO VALIDATE diary) from the report findings | Founder | Tue 17 Nov | 3.15 | Lead generation and clinician recruitment | 60 registrations; 40% attendance | P2 |
| 4.5 | Third signed engagement; £15k–£30k contracted cumulative (ESTIMATE); first testimonial with written consent | Founder | Fri 11 Dec (Day 89) | 3.14 | Services business is real | 3 SOWs; 1 testimonial | P0 |
| 4.6 | DPIA v0.1 for MaternaLink v1; clinical safety case skeleton; security policy set P0 items adopted | Founder + CSO + DPO (fractional, if engaged) | Fri 4 Dec | 3.12, 3.18 | Gates G2/G3 progressing | DPIA v0.1; safety-case skeleton | P1 |
| 4.7 | MVP build decision minuted: build (funded), build-lite (bootstrapped internal alpha within a defined budget), or wait — scored with /docs/20_DECISION_FRAMEWORK.md; if "build", engineering plan and budget from /product/MATERNALINK_MVP_SPEC.md approved | Founder; board | Tue 8 Dec (Day 86) | G-B; 2.10; 4.6; funding status | Product path is a decision with a budget | Decision and budget minuted | P0 |
| 4.8 | Design-partner pipeline: 5 organisations at "brief sent" or later (UK trusts/private maternity; Nigeria NGO cohort); 1 at LOI drafting | Founder | Fri 11 Dec | 3.7, 3.10 | Pilot conversations exist for Q1 2027 | 5 briefs; 1 LOI in drafting | P1 |
| 4.9 | Grant bid submitted (if 3.16 = bid) | Founder (+ clinical partner letter if required) | Per call deadline; internal target Fri 4 Dec | 3.16 | Non-dilutive option exercised | 1 bid submitted | P1 |
| 4.10 | Advisory board at 4 members; first advisory-board meeting held | Founder | Fri 11 Dec | 3.11 | Governance visible to investors | 4 letters; minutes | P1 |
| 4.11 | Cyber Essentials certified; DSPT registration opened; DTAC evidence-pack skeleton | Founder | Fri 11 Dec | 3.19 | Assurance baseline for pilots | Certificate; DSPT account | P2 |
| 4.12 | Independent NED appointed (or two candidates at final stage) | Founder | Fri 11 Dec | 2.18 | Board of two | Appointment letter or shortlist | P2 |
| 4.13 | Nigeria: execute the G-D outcome — send the board-approved re-scoped option to Ekiti, or open the move-state conversations with the top-scored state and an implementing NGO | Founder (+ David Agunede per agreed role) | Fri 27 Nov | 3.10 | Nigeria path active | 1 option sent or 3 new-state conversations | P1 |
| 4.14 | E-Learning: waitlist page live; two course outlines drafted; no build (year-2 revenue per decision framework) | Founder | Fri 11 Dec | 2.12 | Year-2 pipeline seeded | 50 waitlist sign-ups | P2 |
| 4.15 | Monthly close (Month 2) and audit re-score; investor update; board meeting 3 | Founder + accountant; board | Fri 4 Dec; board Tue 8 Dec | 3.20 | Trend to ≥ 35 | Score ≥ 32 (target) | P1 |
| 4.16 | Quarter review (first quarterly ritual): 90-day scorecard; Q1 2027 plan with owners and dates; hiring triggers checked; decision-framework re-score | Founder | Sat 12 Dec (Day 90), finalised week of Mon 14 Dec | All | Next 90 days planned from evidence | Q1 plan issued; audit ≥ 35 | P0 |

## 7. Ninety-day scorecard (what "done" looks like on Sat 12 December 2026)

| Dimension | Day 1 (VERIFIED) | Day 90 target (PROPOSED) | Evidence |
| --- | --- | --- | --- |
| Legal entity | None | Vytalix Group Ltd (or cleared name) incorporated; bank; ICO; insurance; policies; NED shortlist | Certificates; registers; minutes |
| IP | Undocumented | IP deed executed (or licence documented); prototype audited; trademark filed | Signed deed; audit report; filing receipt |
| Claims | Over-claimed 2025 deck in circulation | All external materials stage-honest; intended-use adopted; CSO engaged; hazard log open | Claims-check log; CSO letter |
| Revenue | £0 | 3 signed engagements; £15k–£30k contracted (ESTIMATE); 1 testimonial | SOWs; invoices |
| Investors | 253 researched, 0 contacted | 125 contacted; 10 meetings; 2 active discussions; SEIS/EIS applied; 1 grant bid | CRM dashboard |
| Market validation | 0 UK conversations; Ekiti status unknown | 15 UK interviews; Ekiti status known and G-D decided; mDoc conversation held; two-state scorecard | Synthesis note; decision log |
| Product | Concept + unaudited prototype | PRD v0.2 signed off; DPIA v0.1; safety-case skeleton; MVP build decision minuted; 5 design-partner briefs | PRD; DPIA; minutes |
| Credibility | None | 4 advisers; report 1 published; webinar delivered; website live; 1,500 relevant followers | Letters; report; analytics |
| Operating system | None | Weekly reviews 13/13; monthly closes 3/3; both CSVs current | /operations/reports/ |
| Audit score | 11 | 35–40 | Monthly re-score |

## 8. Ninety-day cash budget (ESTIMATE; excludes founder draw, which is £0 until trailing revenue ≥ £7.5k/month)

| Item | Phase | Low (£) | High (£) |
| --- | --- | --- | --- |
| Solicitor (IP deed, founder assignment, contracts, name opinion) | 1–2 | 4,000 | 9,000 |
| Trademark search and filing (attorney + fees, 4 classes) | 1, 3 | 800 | 2,000 |
| Incorporation, registered office, ICO, Companies House | 2 | 200 | 400 |
| Accountant (3 months) and Xero | 2–4 | 300 | 700 |
| Insurance (PI + PL, annual, paid up front or monthly) | 2 | 800 | 2,000 |
| Tooling (workspace, CRM, site, analytics, newsletter, scheduling) | 1–4 | 300 | 750 |
| Prototype audit (fractional CTO) | 2 | 1,000 | 2,500 |
| CSO (identification to Day 90, ~3 days) | 3–4 | 1,500 | 2,700 |
| Report 1 design and editing | 4 | 1,000 | 2,000 |
| Events, travel, misc. | 1–4 | 300 | 900 |
| Virtual assistant (if triggered, ~2 months) | 2–4 | 0 | 2,200 |
| Cyber Essentials | 4 | 300 | 600 |
| Total |  | 10,500 | 25,750 |

Funding: founder capital (TO CONFIRM) plus first engagement receipts. If founder capital is below £12k, defer the VA, report design and Cyber Essentials to Q1 2027 and hold the P0 items only.

## Priorities / Risks / Next actions

Priorities

Days 1–7 are about removing the four blockers (IP, name, claims, entity); nothing in Phases 3–4 is possible without them.

Revenue quota from Day 8 without exception; first SOW by Day 30, third by Day 90.

Investor outreach only after the pre-condition check on Day 31; quality of the first 25 conversations matters more than volume.

Ekiti is decided, not drifted: G-D on Day 60 with three inputs in hand.

Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| David Agunede declines assignment or delays past Day 30 | Medium | High | Licence fallback ready; Day 60 hard stop with clean-room rebuild; standstill letter prevents third-party dealings |
| Name clearance forces a rename | Medium | Medium | Two reserve names shortlisted Day 5; no paid brand assets before clearance; brand system rename-ready |
| Sales quota not met while legal work consumes Weeks 1–3 | High | High | Revenue block is the first block daily; legal work batched into the 11:15 block; VA trigger |
| Founder capital insufficient for the P0 bench | Medium | High | Budget §8 with a deferral list; first engagement deposit funds Phase 2 |
| Investor outreach starts before pre-conditions (temptation) | Medium | High | Pre-condition check is a logged decision; solicitor sign-off required |
| Kemek Enterprise demands exceed 30% | Medium | High | Weekly time audit; conflicts register; board visibility |

Next actions

| Action | Owner | Deadline |
| --- | --- | --- |
| Execute Day 1 of /docs/19_FIRST_30_DAYS.md (rhythm, name searches, incorporation decision, David Agunede meeting request, investor-call prep) | Founder | Mon 14 Sept 2026 |
| Standstill letter signed; heads of terms sent | Founder + solicitor | Fri 18 Sept / Sun 20 Sept 2026 |
| Incorporate | Founder + accountant | Fri 25 Sept 2026 (hard) |
| First signed engagement; IP deed executed; prototype audit; data room v1; SEIS/EIS submitted | Founder | Tue 13 Oct 2026 |
| Pre-condition check and investor outreach start | Founder + solicitor | Wed 14 Oct 2026 |
| Ekiti go/no-go | Founder; board | Thu 12 Nov 2026 |
| MVP build decision; 90-day scorecard; Q1 2027 plan | Founder; board | Tue 8 – Sat 12 Dec 2026 |