# 12 — VYTALIX PARTNERSHIP STRATEGY

Owner: Chief Strategy Officer · Status: PROPOSED v1 · Date: 8 September 2026 · Governing file: /FACTS_BASE.md (KNOWN / VERIFIED / ASSUMPTION / ESTIMATE / PROPOSED / TO VALIDATE apply throughout). Vytalix has no partners today — no MoU, LOI, contract, grant, membership or introduction with any organisation named in this document (VERIFIED absence, FACTS_BASE §1). Every organisation below is named as a public institution and a target; nothing here may be read, quoted or presented as a relationship. Every score is a desk ESTIMATE to be re-scored after first contact.

## Executive view

Partnerships are the route to market for everything Vytalix cannot buy or build alone: NHS access, clinical credibility, an African cohort, evidence, and non-dilutive money. A solo, pre-formation founder has no references; partners substitute for them. The plan therefore treats partnerships as the second commercial engine beside founder-led services, not as a corporate-development afterthought.

Twenty-five organisations were scored on seven weighted criteria (§3). The top tier for the next 12 months is a regional Health Innovation Network (86/100), Five X More (76), Africa's Talking (76), Society for Family Health Nigeria (74) and the DigitalHealth.London Accelerator (73) — organisations that are reachable by a solo founder, low-cost to engage and directly unlock either NHS introductions, community co-design, a Nigerian cohort or the messaging rail MaternaLink (in development) needs.

Three relationships are gated, not scored down: mDoc, MSD for Mothers and any government. mDoc is the funded incumbent in Ekiti (VERIFIED); MSD for Mothers funds it. Both are approached only with complementarity language, never with the March 2026 Ekiti proposal, and only after the MaternaLink IP question is settled (FACTS_BASE §1). Government relationships are pursued through implementing partners and donors, and an MoU is never described as a "government partnership".

Six partnership models are used (§4) and each has a default contract form and an economic rule: referral (fee-transparent, Bribery Act-safe), co-development (paid community partners, joint IP terms), distribution (revenue share 10–30%, ESTIMATE), data (controller/processor clarity, no individual data to insurers), research (co-applicant, shared authorship, ethics first), funding (grants where a UK entity and a clinical partner exist). Charities and community organisations are always paid for co-design; unpaid "endorsement" is never asked for.

The 12-month plan (§5) targets, by month 12: one Health Innovation Network programme place, two paid community co-design agreements, one university co-applicant agreement, one Nigerian implementing-partner LOI for a cohort, one messaging-gateway pilot account, one NHS design-partner conversation opened through a clinical adviser, and two joint grant bids submitted (PROPOSED). None of these is revenue in year 1; all of them are what an investor, a trust or a ministry will ask to see in year 2.

## 0. Method, definitions and rules of engagement

| Term | Meaning in this document |
| --- | --- |
| Partner | An organisation with which Vytalix has a written arrangement (LOI, MoU, agreement, programme place, grant award, sub-contract). Until a document exists, an organisation is a target, and a conversation is a conversation. |
| Ecosystem ring | Ring 1 = controls access to buyers or users; Ring 2 = confers credibility or evidence; Ring 3 = supplies money, rails or reach. Many organisations sit in two rings. |
| Model | One of six structures in §4: referral, co-development, distribution, data, research, funding (plus sub-contracting and content licensing as variants). |
| Score | Seven weighted criteria in §2; 0–100; ESTIMATE. |
| Horizon | Now (first contact within 90 days of incorporation); 6m; 12m; 24m+. |

Rules of engagement (apply to every outreach, deck, website page and investor conversation):

Never name an organisation as a partner, supporter, client, endorser or "in discussion" without a signed document or their written permission for the wording (FACTS_BASE §4).

Never restate the March 2026 Ekiti proposal (£4.5m / £300 per woman per year) to any organisation; it is UNVALIDATED and it is not Vytalix's document (FACTS_BASE §1).

Never approach a donor, ministry or NGO about MaternaLink (in development) until the IP relationship with David Agunede is documented (FACTS_BASE §1). Services and E-Learning partnerships are not gated.

Pay community organisations and charities for co-design, content and listening exercises; do not ask for endorsement, logos or unpaid advocacy.

Referral fees, commissions and revenue shares are written down, disclosed to the end customer where NHS conflict-of-interest guidance or the Bribery Act 2010 requires it, and never paid to public officials or their relatives. A partnership register (see §5.6) records every arrangement.

Contact details are taken only from public sources; where none exist, the CRM records NOT PUBLICLY AVAILABLE.

Every conversation is logged in the CRM within 24 hours with the next dated action (/docs/13_SALES_ENGINE.md discipline applies to partners as to customers).

## 1. Ecosystem map

Organisations are named as public institutions. "Role for Vytalix" is a proposal. The final column states which Vytalix pillar the relationship serves: Adv (Advisory), Con (Consulting), HS (Health Solutions — MaternaLink, in development), EL (E-Learning).

### 1.1 United Kingdom — NHS system and public bodies

| Partner class | Examples (institutions only) | What they control | Role for Vytalix (PROPOSED) | Ring | Pillar | Horizon |
| --- | --- | --- | --- | --- | --- | --- |
| NHS trusts (maternity services) | ~120 trusts in England provide maternity care (ESTIMATE; /docs/06_CUSTOMER_SEGMENTS.md §1.1) | Design-partner slots; Clinical Safety Officer sign-off (DCB0160); service-evaluation data; reference status | One unpaid design partner (one community midwifery team) for MaternaLink v1; consulting buyer for C3/C8 | 1, 2 | HS, Con | 12m (conversation), 24m+ (paid) |
| Integrated Care Boards / Local Maternity and Neonatal Systems (LMNS) | 42 ICBs in England, each hosting an LMNS (/docs/05_MARKET_STRATEGY.md §1.1) | Equity action plans; improvement budgets; programme sponsorship | Sub-contracted or direct C8 Health Inequalities Review; sponsor for a multi-trust design partnership | 1 | Con, HS | 12m |
| Maternity and Neonatal Voices Partnerships (MNVPs) | One per LMNS (structure TO VALIDATE locally) | The voice of service users in NHS maternity decisions | Listening-exercise partner for C8; co-design input for MaternaLink (paid for time) | 2 | Con, HS | 6m |
| Health Innovation Networks (HINs) | 15 in England, formerly AHSNs (count TO VALIDATE); e.g., Health Innovation Network South London, Health Innovation Manchester, Health Innovation Oxford and Thames Valley | Innovation programmes; trust introductions; real-world evaluation support; NHS market-access advice | Programme place → introductions → evaluation partner; also a quasi-competitor in advice (/docs/11_COMPETITIVE_INTELLIGENCE.md §4) | 1, 2 | HS, Con | Now |
| NIHR | Applied Research Collaborations (ARCs); Invention for Innovation (i4i); HealthTech Research Centres (HRCs); Research Design Service successor bodies (names TO VALIDATE) | Grant funding for NHS-partnered innovation; methodological support; evaluation credibility | Funding and evaluation route for the UK feasibility study (2027–28); requires an NHS partner and a UK entity | 2, 3 | HS | 6m (prepare), 12m (bid) |
| NHS England / DHSC bodies | Three Year Delivery Plan owners; digital maternity record standard; national maternity investigation (2025–26) | Policy pull; standards (PRSB digital maternity record) | Alignment, not partnership: design to the standard; respond to consultations | 2 | HS | 12m |
| NICE | Evidence Standards Framework (ESF) for digital health technologies | Evidence-tier expectations | Alignment target for the evidence plan; no partnership sought | 2 | HS | 12m |
| Professional bodies | Royal College of Midwives (RCM); Royal College of Obstetricians and Gynaecologists (RCOG) | Professional trust; content standards; CPD channels; conference access | Content-licensing conversation (RCOG patient information TO VALIDATE); CPD/E-Learning alignment; speaking slots | 2 | EL, HS | 6m |
| Accelerators and programmes | DigitalHealth.London Accelerator; NHS Clinical Entrepreneur Programme (eligibility TO VALIDATE); NHS Innovation Accelerator (later stage); SBRI Healthcare (funding competitions) | Cohort places; NHS mentors; investor and trust exposure | Apply once incorporated; use for introductions and credibility; SBRI as a funding route | 1, 2, 3 | HS, Adv | Now |
| Standards and interoperability | PRSB; HL7 UK / FHIR UK Core; NHS DTAC owners | Interoperability standards; assurance expectations | Design-to-standard; DTAC readiness for v1; integration (v2) | 2 | HS | 12m |

### 1.2 United Kingdom — private providers, charities, universities, insurers, employers

| Partner class | Examples (institutions only) | What they control | Role for Vytalix (PROPOSED) | Ring | Pillar | Horizon |
| --- | --- | --- | --- | --- | --- | --- |
| Private hospital groups and maternity units | HCA Healthcare UK (The Portland Hospital), Spire, Nuffield Health, Circle Health; the Kensington Wing and Lindo Wing (NHS private units) | Fast decisions; premium client experience budgets; fewer IG barriers | Consulting buyer (C1) and a faster MaternaLink pilot market (/docs/06_CUSTOMER_SEGMENTS.md §1.2–1.3); distribution partner for E-Learning to staff | 1 | Con, HS | 6m–12m |
| Maternal-health research charities | Tommy's; Wellbeing of Women; Sands; Bliss | Research funding; public trust; content | Research co-funding conversations; content signposting and licensing (never duplicate free information); joint events | 2, 3 | HS, EL | 6m |
| Advocacy and community organisations (Black maternal health, rights) | Five X More; Birthrights; Maternity Action; Black Mothers Matter-type community groups (TO VALIDATE current organisations); Best Beginnings (Baby Buddy app) | Community trust; lived-experience input; policy voice | Paid co-design, listening exercises and content review for MaternaLink and for C8 reviews; content signposting (Baby Buddy) | 2 | HS, Con | Now |
| Parenting and antenatal organisations | NCT | Antenatal education reach; parent trust | Content and distribution conversation for the woman-facing layer (later) | 1, 2 | HS, EL | 12m |
| Universities — maternal-health research groups | NPEU (University of Oxford); King's College London; University of Manchester; LSHTM MARCH Centre; City St George's, University of London (midwifery — TO VALIDATE current name); Liverpool School of Tropical Medicine (LSTM) for Africa evaluation | Methodology; ethics routes; NIHR/UKRI/Wellcome co-applications; students | Service-evaluation and feasibility-study partner (2027–28); v3 research-track partner; E-Learning licences and guest lectures | 2, 3 | HS, EL | 6m |
| Insurers and benefits platforms (UK) | Bupa; AXA Health; Vitality; Aviva | Employer maternity benefits; member communications | Discovery interviews only in 2026; benefit-bundle distribution 24m+ (/docs/04_MATERNALINK_PRODUCT_STRATEGY.md §14) | 1, 3 | HS | 24m+ |
| Employers and benefits consultancies | Large employers with DEI/maternity-return programmes; benefits consultancies | Workshop and E-Learning budgets | E-Learning and workshop distribution; no product claims | 1 | EL, Con | 6m |
| Consultancies (as primes) | PA Consulting; Carnall Farrar; Deloitte (/docs/11_COMPETITIVE_INTELLIGENCE.md §4) | NHS frameworks; large programmes | Sub-contract route for NHS consulting until Vytalix holds a framework place | 1 | Con | 6m |
| Technology vendors (UK maternity) | System C (BadgerNet Maternity); K2 Medical Systems; Magentus (Euroking) | The maternity record in most trusts; integration gateways | Integration-first posture (v2); "layer beside the record"; possible channel | 1 | HS | 12m |

### 1.3 Africa — governments, programmes, NGOs, rails

| Partner class | Examples (institutions only) | What they control | Role for Vytalix (PROPOSED) | Ring | Pillar | Horizon |
| --- | --- | --- | --- | --- | --- | --- |
| Nigeria — federal | Federal Ministry of Health and Social Welfare; National Primary Health Care Development Agency (NPHCDA); National Health Insurance Authority (NHIA); digital-health governance bodies (current names TO VALIDATE) | National digital-health strategy; PHC standards; insurance rules | Alignment and registration; no early partnership sought | 2 | HS | 12m |
| Nigeria — state | Ekiti State Ministry of Health (one prior conversation by David Agunede, outcome unknown); Lagos State MoH (works with mDoc); candidate states Oyo, Kano, Ondo, Osun, Kwara (/docs/05_MARKET_STRATEGY.md §2.1); State Primary Health Care Development Agencies (SPHCDAs); state health insurance agencies | LGA access; CHEW workforce; data ownership; budget lines (usually donor-backed) | Pilot host via an implementing partner; MoU → pilot agreement → contract sequence (/docs/04_MATERNALINK_PRODUCT_STRATEGY.md §12) | 1 | HS, Adv | 12m–24m+ |
| Kenya | Ministry of Health; county health departments (47); Social Health Authority (SHA) — maternity coverage under transition (TO VALIDATE) | County procurement; facility networks | Second African market (months 18–36); county or NGO programme | 1 | HS | 24m+ |
| Ghana | Ghana Health Service; National Health Insurance Authority | Centralised buyer | "Prepare, do not enter" until 2028 | 1 | HS | 24m+ |
| Incumbent programmes (complement, not compete) | mDoc (Digital Mom Project, Ekiti and Lagos, funded by MSD for Mothers — VERIFIED); Jacaranda Health (PROMPTS, Kenya); Helium Health (facility records, Nigeria) | Enrolled women; provider networks; donor goodwill | Complementarity conversations (facility-side coordination, handover, CHEW workflow); integration-ready posture with Helium | 1, 2 | HS | Now (conversation), 12m (agreement) |
| Implementing NGOs — Nigeria | Society for Family Health Nigeria; Wellbeing Foundation Africa; Nigeria Health Watch (convenor/advocacy, not implementer); Pathfinder International Nigeria; Jhpiego Nigeria | Cohorts in LGAs; CHEW training; donor reporting; ethics routes (NHREC/state) | The fastest route to a cohort: programme-licence host; joint grant applicant; evaluation co-author (/docs/04_MATERNALINK_PRODUCT_STRATEGY.md §13) | 1, 2 | HS, Con | 6m |
| Implementing NGOs — Kenya and regional | Amref Health Africa; Living Goods; Jacaranda Health; Population Services Kenya (TO VALIDATE current structure) | CHW networks; county relationships | Kenya entry partner (2027–28) | 1 | HS | 24m+ |
| International NGOs and technical agencies | Jhpiego; PATH; MSI Reproductive Choices; Population Council; Save the Children | Large maternal-health programmes; digital-health technical leadership (PATH); country offices | Sub-contract, joint bids, programme licence; evaluation credibility | 1, 2 | HS, Con | 6m–12m |
| Multilateral programmes | WHO (Digital Adaptation Kit for antenatal care; SMART guidelines); UNFPA (maternal health and innovation calls); UNICEF (Office of Innovation, country programmes); World Bank Global Financing Facility (GFF) | Standards; funding windows; ministry influence | Design to WHO ANC digital adaptation kit; UNFPA/UNICEF innovation calls (eligibility TO VALIDATE); GFF-financed state plans as budget context | 2, 3 | HS | 6m (alignment), 12m (calls) |
| Bilateral development organisations | FCDO (UK-funded health programmes and research); GIZ; USAID (restructured into the US State Department in 2025 — funding landscape TO VALIDATE); Global Affairs Canada via Grand Challenges Canada | Programme funding through primes; research calls | Sub-contract to primes; FCDO-funded research consortia via UK universities | 3 | HS, Con | 12m |
| Foundations and corporate programmes | MSD for Mothers (funds mDoc — VERIFIED); Gates Foundation / Grand Challenges; Children's Investment Fund Foundation (CIFF); Wellcome; ELMA Philanthropies; Aliko Dangote Foundation; TY Danjuma Foundation (Nigeria; fit TO VALIDATE) | Non-dilutive funding; programme partnerships | Grant applications with an NGO or university lead; MSD for Mothers approached only with complementarity to its existing grantee | 3 | HS | 6m (prepare), 12m (bid) |
| Telecoms and messaging rails | MTN Nigeria / MTN Foundation; Airtel Africa; Safaricom (M-Pesa; M-TIBA health-payments platform with CarePay); Africa's Talking; Termii; Twilio; Vodafone Foundation | SMS/USSD/WhatsApp/voice rails; sender-ID and DND compliance; zero-rating; health propositions | Gateway account (Now); telco bundle/white-label channel (24m+, /docs/01_BUSINESS_MODEL.md stream #13) | 3 | HS | Now (gateway), 24m+ (telco) |
| Insurers and HMOs — Africa | Nigeria: AXA Mansard Health, Hygeia HMO, Reliance Health, Leadway Health; state health insurance agencies; Kenya: Jubilee Health, Britam, SHA | Enrolled women with a financial interest in ANC adherence and facility delivery | Engagement-fee pricing with aggregate adherence dashboards; no individual clinical data; 24m+ | 1, 3 | HS | 24m+ |
| Banks and development finance | Access Bank (women's banking programmes), Standard Chartered (community programmes), First Bank — CSR fit TO VALIDATE; British International Investment (BII); IFC | CSR budgets; later-stage capital | Opportunistic CSR co-funding of a cohort; DFI conversations only at Series A | 3 | HS | 24m+ |
| Diaspora and convening bodies | Nigerian and Kenyan clinician associations in the UK (e.g., MANSAG-type associations — TO VALIDATE); Nigeria Health Watch (Future of Health conference) | Trusted introductions; convening platforms | Advisory-board sourcing; speaking; warm introductions to state and NGO leaders | 1, 2 | HS, Adv | Now |

### 1.4 Reading the map

Only four classes are reachable and useful in the next 90 days without an entity or IP resolution: Health Innovation Networks and accelerators (applications), community organisations (paid co-design for services work), messaging gateways (a developer account) and diaspora/convening bodies (introductions).

Every African government relationship runs through a Ring 1 implementing partner or a Ring 3 funder; Vytalix does not approach a ministry alone (/docs/04_MATERNALINK_PRODUCT_STRATEGY.md §12.1).

Two incumbents (mDoc, Jacaranda) are partner targets first and competitors second; the test is one documented conversation each before any further product spend in their markets (/docs/11_COMPETITIVE_INTELLIGENCE.md Priorities).

## 2. Partnership scoring framework (PROPOSED)

Seven criteria; weights sum to 100; each criterion scored 1–5 (5 = most favourable); score = Σ(weight × criterion score) ÷ 5, giving 0–100. Cost and risk are scored inversely (5 = low cost, low risk).

| # | Criterion | Weight | What "5" means | What "1" means |
| --- | --- | --- | --- | --- |
| 1 | Strategic value | 20 | Unlocks a gate in the plan (NHS design partner, African cohort, evidence, IP-safe content) that nothing else unlocks | Nice to have; no gate opened |
| 2 | Revenue potential (24 months) | 15 | Direct fees, sub-contract days or programme licence ≥ £50k (ESTIMATE) | £0 and no plausible path |
| 3 | Credibility conferred | 15 | Named association would change a trust's, donor's or investor's view immediately | Unknown to buyers and investors |
| 4 | Access (can the founder reach a decision-maker within 30 days?) | 15 | Public application route or founder-level contact; answers in weeks | Requires an introduction Vytalix does not have; institutional gatekeeping |
| 5 | Time-to-value | 15 | Signed document or programme place within 3 months | 12+ months to any document |
| 6 | Cost to engage (inverse) | 10 | Under 3 founder days and < £1k to reach a decision | > 20 founder days, match funding, travel or legal cost > £10k |
| 7 | Risk (inverse) | 10 | No IP, reputational, dependency or conflict risk | Dependency on a competitor's goodwill, IP exposure, political or payment risk |

Gates applied before scoring is used (a "no" on any gate pauses outreach regardless of score):

| Gate | Applies to | Condition to pass |
| --- | --- | --- |
| G1 — Entity | Any signed document; any grant | Vytalix incorporated, bank account, professional indemnity in place |
| G2 — IP | Any conversation about MaternaLink (in development) | Written agreement with David Agunede on MaternaLink IP (FACTS_BASE §1) |
| G3 — Claims | Any external material | Intended-use statement adopted; 2025 deck retired externally (FACTS_BASE A4) |
| G4 — Conflict | Any competitor or incumbent | Conflict register entry; partner-first wording approved (§5.5) |
| G5 — Payment integrity | Any government, official or referral arrangement | Bribery Act 2010 check; written fee terms; no payments to officials |

Services and E-Learning partnerships pass G1 and G3 only. Scores are re-run after every first meeting; a partner that fails two consecutive next actions drops one tier.

## 3. Scored long-list — 25 target partner organisations

All 25 are real, publicly identifiable organisations. No relationship exists with any of them (VERIFIED absence). Scores are desk ESTIMATES (criteria 1–7 as numbered in §2; the last two are inverse). Model codes refer to §4. Pillar codes as in §1.

| Rank | Organisation | Class | 1 Strat (20) | 2 Rev (15) | 3 Cred (15) | 4 Access (15) | 5 Time (15) | 6 Cost (10) | 7 Risk (10) | Score | Model | Pillar | Gate | Horizon |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Health Innovation Network (one regional HIN first; e.g., South London or Manchester) | UK innovation body | 5 | 2 | 5 | 5 | 4 | 5 | 4 | 86 | Referral, Research | HS, Con | G1 | Now |
| 2 | Five X More | UK advocacy (Black maternal health) | 5 | 1 | 5 | 4 | 4 | 4 | 3 | 76 | Co-development (paid) | HS, Con | G1, G3 | Now |
| 3 | Africa's Talking | Messaging gateway (Kenya, pan-African) | 4 | 2 | 2 | 5 | 5 | 5 | 4 | 76 | Distribution (rail) | HS | G2 | Now |
| 4 | Society for Family Health Nigeria | Implementing NGO | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 74 | Distribution, Funding, Research | HS, Con | G1, G2 | 6m |
| 5 | DigitalHealth.London Accelerator | Accelerator | 4 | 2 | 4 | 4 | 3 | 4 | 5 | 73 | Referral | HS, Adv | G1 | Now |
| 6 | Nigeria Health Watch | Convenor / advocacy | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 71 | Referral, Co-development (content) | HS, Adv | G1 | Now |
| 7 | MSD for Mothers | Corporate programme funder | 5 | 4 | 5 | 2 | 2 | 3 | 3 | 71 | Funding | HS | G1, G2, G4 | 12m |
| 8 | Jhpiego | International NGO | 5 | 4 | 5 | 2 | 2 | 3 | 3 | 71 | Distribution, Research, Funding | HS, Con | G1, G2 | 12m |
| 9 | Birthrights | UK rights charity | 4 | 1 | 4 | 4 | 4 | 4 | 4 | 71 | Co-development (paid) | HS, Con | G1, G3 | Now |
| 10 | NPEU, University of Oxford | University research unit | 5 | 2 | 5 | 2 | 2 | 3 | 4 | 67 | Research | HS | G1, G2 | 6m |
| 11 | NIHR (ARC, i4i, HealthTech Research Centres) | Research funder | 4 | 3 | 5 | 2 | 2 | 3 | 4 | 66 | Funding, Research | HS | G1, G2 | 12m |
| 12 | mDoc (Digital Mom Project) | Incumbent (Ekiti, Lagos) | 5 | 2 | 3 | 3 | 3 | 4 | 2 | 65 | Co-development / Distribution (complementarity) | HS | G2, G4 | Now (conversation) |
| 13 | Tommy's | UK research charity | 4 | 1 | 5 | 2 | 3 | 4 | 4 | 65 | Co-development (content), Research | HS, EL | G1, G3 | 6m |
| 14 | Royal College of Midwives | Professional body | 4 | 2 | 5 | 2 | 2 | 4 | 4 | 65 | Co-development (content), Distribution (E-Learning) | EL, HS | G1 | 6m |
| 15 | UNFPA (Nigeria and Kenya country offices) | Multilateral | 4 | 3 | 5 | 2 | 2 | 3 | 3 | 64 | Funding | HS | G1, G2 | 12m |
| 16 | PATH | International NGO (digital health) | 4 | 3 | 5 | 2 | 2 | 3 | 3 | 64 | Research, Distribution | HS | G1, G2 | 12m |
| 17 | King's College London | University | 4 | 2 | 4 | 3 | 2 | 3 | 4 | 63 | Research, Distribution (E-Learning) | HS, EL | G1 | 6m |
| 18 | Jacaranda Health | Incumbent (Kenya) | 4 | 2 | 4 | 3 | 2 | 4 | 3 | 63 | Co-development (complementarity) | HS | G2, G4 | 6m (conversation) |
| 19 | LSHTM MARCH Centre | University research centre | 4 | 2 | 4 | 2 | 2 | 3 | 4 | 60 | Research | HS | G1, G2 | 6m |
| 20 | Gates Foundation / Grand Challenges | Foundation | 4 | 4 | 5 | 1 | 1 | 2 | 3 | 59 | Funding | HS | G1, G2 | 12m |
| 21 | Wellbeing of Women | UK research charity | 3 | 2 | 4 | 2 | 2 | 4 | 4 | 58 | Funding (research), Co-development | HS | G1 | 12m |
| 22 | System C (BadgerNet Maternity) | UK EPR vendor | 4 | 3 | 3 | 2 | 2 | 3 | 3 | 58 | Data (integration), Distribution | HS | G2 | 12m |
| 23 | MSI Reproductive Choices | International NGO | 3 | 3 | 4 | 2 | 2 | 3 | 3 | 57 | Distribution, Funding | HS, Con | G1, G2 | 12m |
| 24 | FCDO (UK-funded health programmes) | Bilateral funder | 3 | 3 | 4 | 2 | 1 | 2 | 3 | 52 | Funding (via primes) | HS, Con | G1 | 12m–24m+ |
| 25 | MTN Nigeria / MTN Foundation | Telecom | 3 | 3 | 3 | 1 | 1 | 3 | 3 | 48 | Distribution (bundle/white-label) | HS | G2 | 24m+ |

Watch list (next ten, not yet scored; re-score at month 6): HCA Healthcare UK (private maternity pilot market); Helium Health (integration in Nigerian private hospitals); Safaricom / M-TIBA (Kenya rails); Wellbeing Foundation Africa (Nigerian maternal-health NGO); Amref Health Africa (Kenya); Best Beginnings (Baby Buddy content signposting); K2 Medical Systems and Magentus (EPR integration); AXA Mansard Health or Hygeia HMO (Nigeria HMO discovery); Bupa or AXA Health (UK benefits discovery); Innovate UK and SBRI Healthcare (funders rather than partners — tracked in /docs/08_FINANCIAL_MODEL.md grant calendar).

### 3.1 Reading the ranking

| Tier | Organisations | Why | What happens in the next 90 days |
| --- | --- | --- | --- |
| Tier 1 — engage now (score ≥ 70) | HIN, Five X More, Africa's Talking, SFH Nigeria, DigitalHealth.London, Nigeria Health Watch, MSD for Mothers, Jhpiego, Birthrights | Reachable, cheap, and each opens a gate | Applications (HIN, DHL); paid co-design proposals (Five X More, Birthrights); gateway account (Africa's Talking); introductions sought (SFH, NHW); MSD for Mothers and Jhpiego prepared but held behind G2 |
| Tier 2 — prepare, engage at 6 months (60–69) | NPEU, NIHR, mDoc, Tommy's, RCM, UNFPA, PATH, King's, Jacaranda, LSHTM | High credibility, slower institutions; most need the entity, a clinical adviser or IP resolution | Desk research; identify the right programme or call; warm-introduction paths mapped; mDoc/Jacaranda conversations as soon as G2 and G4 pass |
| Tier 3 — track (< 60) | Gates/Grand Challenges, Wellbeing of Women, System C, MSI, FCDO, MTN | Long cycles, high cost, or only relevant after evidence exists | Calendar of calls; no outreach beyond a courtesy contact |

The ranking is sensitive to one variable: if G2 (IP) is resolved by day 30, mDoc, Jhpiego, SFH and MSD for Mothers all move up a tier because time-to-value improves; if it is not resolved by day 90, every HS-pillar partner freezes and the plan collapses to HIN, community co-design and E-Learning partnerships.

## 4. Partnership models

| Model | Structure | Economics (ESTIMATE) | Default contract form | Best partner types | When to use | Principal risks and controls |
| --- | --- | --- | --- | --- | --- | --- |
| Referral | Partner introduces Vytalix to buyers (or vice versa); no delivery obligation | Introduction fee 5–10% of first-year fees, or reciprocal referrals with no fee; HINs and accelerators take no fee | Referral agreement or programme terms; fee disclosed to the customer | HINs, accelerators, consultancies, diaspora associations, convenors | Services growth; NHS introductions | Bribery Act and NHS conflict-of-interest exposure — fees written, disclosed, never to public officials; register entry |
| Co-development | Joint design, content or research with shared outputs | Vytalix pays community partners (£2k–£10k per engagement, ESTIMATE); joint IP terms written before work starts | Collaboration agreement with IP schedule; content licence | Five X More, Birthrights, MNVPs, Tommy's, RCM, mDoc/Jacaranda (complementarity) | MaternaLink content and safety-critical journeys; C8 listening exercises | IP ambiguity — ownership/licence stated per deliverable; consent and safeguarding for lived-experience work; no "endorsement" claims |
| Distribution | Partner carries MaternaLink (in development) or E-Learning to its cohort, members or customers | Revenue share 10–30% to the partner or programme licence to the partner (£8k–£60k/programme/yr, /assets/PARTNERSHIP_DECK.md slide 7); telco white-label £25k–£75k set-up + £2–£8/user/yr (24m+) | Reseller/programme agreement; data-processing agreement; SLA | Implementing NGOs, HMOs, telecoms, private hospital groups, RCM (E-Learning), EPR vendors | African cohorts; E-Learning scale; telco channel (24m+) | Dependency on a single channel; data-controller/processor split; local data residency (Nigeria NDPA, Kenya ODPC) |
| Data | Integration, data exchange or shared datasets | Usually no fee; integration cost borne by Vytalix (v2); no individual-level data to insurers | Data-sharing agreement; DPIA; integration agreement | EPR vendors, Helium Health, state DHIS2 owners, insurers (aggregate only) | v2 integration; state data ownership; adherence dashboards | Regulatory exposure — DPIA before any exchange; state owns programme data; no processing of real patient data in the prototype until audited (FACTS_BASE §2) |
| Research | Co-applicant on evaluation or research; shared authorship; pre-registered protocols | Grant-funded; Vytalix costs recovered at 70–100% of eligible costs (scheme-dependent, TO VALIDATE); no fee to the university | Collaboration agreement; ethics (HRA/REC or NHREC) before data; publication policy | NPEU, King's, LSHTM, NIHR ARCs, PATH | UK service evaluation (2027), feasibility study (2028), v3 research track (data partnership only after v1 evidence) | Timeline (12–36 months); authorship disputes; v3 claims discipline (no predictive claims before validation and MHRA pathway) |
| Funding | Grants, programme funding, corporate/foundation support | £25k–£500k per award (ESTIMATE); success rates single-digit to ~20% (ESTIMATE); match funding 30–50% | Grant agreement; consortium agreement | NIHR, Innovate UK/SBRI, Grand Challenges, UNFPA/UNICEF calls, MSD for Mothers, Wellcome, FCDO via primes | Non-dilutive R&D and evaluation | Eligibility (UK entity; NHS or NGO partner); subsidy control; reporting burden; MSD for Mothers conflict with its existing grantee |
| Variant — Sub-contracting | Vytalix delivers days inside a prime's programme | Day rate £900–£1,200 (associate rates in /docs/01_BUSINESS_MODEL.md §3) | Sub-contract with IP and non-solicit terms | Consultancies, HINs (evaluation), international NGOs | First NHS/donor references | Margin; being typecast; IP leakage of Vytalix methods |
| Variant — Content licensing | Vytalix licenses in signed-off content rather than authoring clinical content | Licence fee or free-with-attribution; clinical sign-off by the licensor | Content licence; attribution; update obligations | RCOG patient information, Tommy's, Best Beginnings, WHO ANC digital adaptation kit (open) | MaternaLink education layer; E-Learning | Version drift; licensor's clinical-governance requirements; no re-writing clinical content without sign-off |

Model selection rule (PROPOSED): for each partner, choose the model with the shortest path to a signed document, then add models over time. A community organisation starts as paid co-development and may become a distribution partner; an NGO starts as a joint-bid research/funding partner and becomes a distribution partner when a cohort exists; a HIN starts as referral and becomes an evaluation (research) partner.

## 5. Twelve-month partnership plan (PROPOSED)

Month 1 = the month of incorporation (planned September–October 2026 per /docs/18_90_DAY_EXECUTION_PLAN.md). Everything below depends on gates G1–G5 in §2.

### 5.1 Quarter plan and targets

| Quarter | Focus | Partner actions | Documents targeted by quarter-end | Founder days (ESTIMATE) |
| --- | --- | --- | --- | --- |
| Q1 (months 1–3) | Access and co-design; gate-clearing | Apply to one regional HIN programme and DigitalHealth.London; paid co-design proposals to Five X More and Birthrights; Africa's Talking developer account and pricing; introduction requests to SFH Nigeria and Nigeria Health Watch via public routes; Ekiti status call; mDoc complementarity email only if G2 passes; advisory-board recruitment via diaspora associations | 1 programme application submitted; 1 paid co-design agreement signed; gateway account live; 2 advisory-board letters (per /docs/18_90_DAY_EXECUTION_PLAN.md 3.11); partnership register created | 12 |
| Q2 (months 4–6) | Evidence and Nigeria route | University conversations (NPEU, King's, LSHTM) about a 2027 service evaluation; NIHR ARC engagement; second co-design agreement; RCM content/CPD conversation; SFH Nigeria or Jhpiego LOI for a cohort scoping; Jacaranda conversation; state scorecard field scan (Oyo, Kano) with in-country partners; Tommy's content conversation | 1 university letter of intent to co-apply; 1 NGO LOI to scope a cohort; 2 paid co-design agreements in total; mDoc and Jacaranda conversations documented | 15 |
| Q3 (months 7–9) | Funding and design partner | First two grant bids (e.g., SBRI Healthcare or Innovate UK; a Grand Challenges or UNFPA call — calendars TO VALIDATE) with a university or NGO lead; NHS design-partner conversation opened through a clinical adviser and the HIN; MSD for Mothers approach with complementarity framing (post-G2, G4); private maternity pilot conversation (HCA UK-type unit) | 2 bids submitted; 1 NHS trust design-partner conversation at "exploring DCB0160 with CSO"; 1 private-provider pilot LOI | 18 |
| Q4 (months 10–12) | Convert and institutionalise | Convert one design-partner conversation to a written evaluation plan; convert NGO LOI to a programme agreement or joint bid; E-Learning distribution conversation with RCM or a university programme; telco/HMO discovery interviews (5); re-score the long-list; partnership board paper | 1 design-partner agreement or evaluation plan; 1 programme agreement or funded bid; 1 E-Learning distribution LOI; long-list re-scored | 15 |

Twelve-month scorecard (PROPOSED): 1 HIN/accelerator programme place · 2 paid community co-design agreements · 1 university co-applicant agreement · 1 Nigerian implementing-partner LOI or agreement · 1 gateway pilot account · 1 NHS design-partner conversation opened (agreement is a stretch) · 2 joint grant bids submitted · 1 E-Learning distribution LOI · 0 unverified "partner" claims in any material (audited monthly).

### 5.2 Outreach sequence (per partner; adapt to model)

| Step | Timing | Action | Rule |
| --- | --- | --- | --- |
| 1 | Day 0 | Qualify: score in §2; check gates; identify the decision-maker title and a public route (programme application, published contact, event, LinkedIn); log in CRM with trigger URL | No invented contact details |
| 2 | Day 0–3 | Earn the right: read the organisation's latest report, strategy or programme page; identify one thing Vytalix can offer that costs them nothing (a data point, a draft, an introduction, a paid brief) | Never open with an ask for endorsement or a logo |
| 3 | Day 3 | First message (≤ 120 words): who Vytalix is (pre-seed, honest stage), why this organisation specifically, the one offer, one question, a 20-minute ask | Use the "what we offer / what we ask" line for the partner type (§5.3); language rules from FACTS_BASE §4 |
| 4 | Day 10 | Follow-up 1: add one piece of value (a relevant excerpt from the sourced report in /docs/14_MARKETING_AND_CONTENT_ENGINE.md, a public call they may not have seen) | One follow-up; no pressure |
| 5 | Day 20 | Follow-up 2 or alternative route: an event, a mutual contact found through public sources, or a programme application instead of a cold message | Three touches maximum, then park for 90 days |
| 6 | Meeting | Discovery, not pitch: 60% listening; confirm what they control, their calendar (calls, cohorts, board dates), their conditions; agree one concrete next step with a date | Bring the artefact relevant to the model (co-design brief, integration note, evaluation outline, bid outline) |
| 7 | +7 days | Written follow-up: one-page note of what was agreed; proposed document type (LOI/MoU/agreement/application); named next action on both sides | Nothing is a partnership until signed; wording of any public reference agreed in writing |
| 8 | Monthly | Register review: status, next action, gate status, any public reference permission | Founder + (later) a partnerships lead |

### 5.3 What we offer / what we ask — by partner type

| Partner type | What we offer | What we ask | What we will not do |
| --- | --- | --- | --- |
| NHS trusts / LMNS | Vendor-neutral readiness and inequalities reviews (C3, C8); a non-diagnostic communication and handover layer beside the EPR with the safety artefacts (DCB0129 hazard log, DPIA, intended-use statement) supplied; a service-evaluation design; no licence fee for the design partner | A digital midwife and a Clinical Safety Officer willing to run DCB0160; one community team; 3–6 months; a service-evaluation write-up | Replace the EPR; make clinical claims; use the trust's name without written permission |
| Health Innovation Networks / accelerators | A maternal-health innovation with an honest evidence plan and a founder who will do the work; participation in their evaluation and reporting; case-study material once evidence exists | A programme place; introductions to two or three maternity digital leads; evaluation methodology support; no fee | Present the programme as an endorsement; ask them to sell for us |
| Universities / NIHR | A real-world deployment to study; co-designed protocols; shared authorship; SME co-applicant status; industry match where schemes require it | Methodological partnership; a named principal investigator; co-application on one call in 2027; ethics route guidance | Train models on patient data without approvals; make predictive claims; treat the v3 research track as a product commitment |
| Charities and community organisations | Payment for co-design, listening exercises and content review; credit in outputs; influence over the woman-facing journeys; joint bids where they lead | Lived-experience input; content review; participation in a C8 listening exercise; candid criticism | Ask for endorsement, logos, free advocacy or unpaid time; speak on their behalf |
| Professional bodies (RCM, RCOG) | CPD-ready E-Learning aligned to their standards (accreditation TO VALIDATE); content licensing revenue where relevant; speaking content on digital maternity | A content-licensing conversation; guidance on CPD routes; conference slots | Claim accreditation or endorsement before it exists |
| Implementing NGOs (Nigeria, Kenya) | Enrolment and follow-up tracking, two-way SMS at scale, CHEW defaulter lists, logframe/DHIS2-compatible exports, data owned by the NGO or state, local-hosting option (TO VALIDATE), a programme licence priced to a grant line (£8k–£60k/yr, ESTIMATE), joint bid capacity from the UK | An existing cohort in 1–2 LGAs; CHEW supervision; a budget line or joint grant; co-authorship of the evaluation; NHREC/state ethics | Arrive with a state-wide proposal; compete on price with an incumbent programme; share individual data with third parties |
| Donors, foundations and multilaterals (MSD for Mothers, Gates/Grand Challenges, UNFPA, UNICEF, FCDO primes) | A complementary, partner-first coordination layer for existing programmes; transparent total programme cost; evaluation-grade data; UK–Nigeria/Kenya corridor delivery with a UK entity | Programme-officer conversation; call eligibility guidance; consideration as a sub-grantee or consortium member; introductions to grantees | Pitch against an existing grantee (mDoc); restate the Ekiti proposal; claim any relationship |
| African governments (via partners) | An LGA-level pilot under £0.5m/yr (ESTIMATE) with a 12-month evaluation and defined exit; data ownership with DHIS2 export; NDPA compliance; a local implementing partner | An LOI, then an MoU, then a pilot agreement — in that order; a named focal person; access to CHEWs and facilities | Approach alone; describe an MoU as a government partnership; make payments to officials or intermediaries |
| Incumbents (mDoc, Jacaranda, Helium Health) | Complementary facility-side coordination, referral tracking and handover; integration-ready posture; shared learning; a joint offer to donors where it helps them | One exploratory conversation; clarity on where they see gaps; an integration or referral conversation if there is fit | Enter their state/county against them on price; imply a partnership after one call |
| Telecoms and gateways | A maternal-health messaging and coordination use case with programme buyers; volume assumptions (~60 SMS/woman/year, ESTIMATE); a white-label option later | Gateway pricing and sender-ID/DND guidance (NCC rules TO VALIDATE); zero-rating or bundled data for enrolled women; a named pilot contact | Pass identifiable health data; commit volumes before a funded pilot |
| Insurers and HMOs | Aggregate adherence dashboards; engagement-fee pricing (24m+); reduced no-shows for covered women (to be evidenced) | Discovery interviews now; a benefits-bundle conversation after evidence | Share individual clinical data; perform underwriting or risk scoring |
| Private hospital groups | A fast, low-IG-barrier pilot with the safety artefacts included (£10k minimum bundle per /docs/13_SALES_ENGINE.md); a C1 discovery sprint; staff E-Learning | A lead obstetrician sponsor; one service line; a paid pilot | Undercut on price; skip DPIA and safety case because the setting is private |
| Consultancies (primes) | Specialist maternity/digital/Africa depth at associate rates; speed; fixed-price sub-scopes | Sub-contract days on NHS or donor programmes; a framework route | Compete for their prime work; use their client names |

### 5.4 Ekiti and mDoc — the specific plan

| Step | Timing | Action | Owner |
| --- | --- | --- | --- |
| 1 | Q1, by day 26 | One call to learn the status of the March 2026 proposal (live, dead, in negotiation — FACTS_BASE §2). No restatement of the proposal. Outcome recorded in FACTS_BASE. | Founder (with David Agunede, subject to the IP conversation) |
| 2 | Q1, only after G2 and G4 | Complementarity email to mDoc (wording rules in §5.5). One exploratory conversation. | Founder |
| 3 | Q1–Q2 | Two-state scorecard field scan (Oyo, Kano) with in-country NGO conversations (/docs/05_MARKET_STRATEGY.md §2.1). | Founder + in-country associate (TO RECRUIT) |
| 4 | Day 60 | Go/no-go: partner / differentiate / move state (/docs/18_90_DAY_EXECUTION_PLAN.md G-D). | Founder + advisory board |
| 5 | Q3 | MSD for Mothers approached only with a complementarity framing agreed (or not objected to) by mDoc, or with a different-state, NGO-led proposal. | Founder |

### 5.5 Wording rules for incumbent and donor outreach (mDoc, Jacaranda, MSD for Mothers)

State the stage honestly: "pre-seed, UK-based, MaternaLink in development, no deployments".

Acknowledge their programme explicitly and by its public name; cite the public source of what we know.

Position on what they do not do (facility-side coordination, referral tracking, handover, CHEW defaulter lists, evaluation-grade exports) — never on price, never on "better".

Ask one question: "Where do you see gaps a complementary coordination layer could fill, and would a 30-minute conversation be useful?"

Never mention the Ekiti proposal, its pricing, or any state contact; never imply a state relationship.

No public reference to the conversation afterwards; the CRM entry is the only record.

If they decline or do not reply, the fallback is "move state" or "different layer", not repetition.

### 5.6 Governance

| Instrument | Content | Owner | Cadence |
| --- | --- | --- | --- |
| Partnership register | Organisation, class, model, gate status, document status (target/conversation/LOI/MoU/agreement), fee terms, public-reference permission, conflicts, next action | Founder | Updated within 24h of contact; reviewed monthly |
| Document ladder | LOI (non-binding, 1 page) → MoU (non-binding, scope and principles) → agreement (binding: collaboration, referral, reseller, data-sharing, sub-contract, grant/consortium) | Founder; solicitor for binding documents | Per partner |
| Conflicts register | Competitors advised, incumbents contacted, referral fees, public officials met | Founder | Monthly |
| Public-reference protocol | No name, logo or "in discussion" without written permission; wording approved by the partner | Founder | Per reference |
| Anti-bribery and gifts policy | Bribery Act 2010; no facilitation payments; hospitality thresholds; agent due diligence in Nigeria/Kenya | Founder | Adopted at incorporation; reviewed annually |
| Partner review | Score re-run, pipeline by tier, documents signed, days spent, lessons | Founder + advisory board | Quarterly |

### 5.7 Budget (ESTIMATE, 12 months)

| Item | Amount | Note |
| --- | --- | --- |
| Paid community co-design (2 agreements) | £6k–£16k | £3k–£8k each; the single most important spend in this plan |
| Programme and application fees | £0–£2k | Most HIN/accelerator routes are free (TO VALIDATE) |
| Messaging gateway pilot credits | £500–£2k | Africa's Talking-type account; pass-through in pilots |
| In-country field scan (two states) | £4k–£10k | Associate days, travel; may be partly covered by a C5-type paid engagement |
| Legal (LOI/MoU templates, collaboration and referral agreements) | £3k–£8k | Templates once; reuse |
| Travel and events (UK conferences, one Nigeria trip, one Kenya desk phase) | £4k–£8k | Nigeria travel only after G2 and an NGO conversation |
| Founder time | ~60 days | ~25% of available days; in tension with ~87 billable days (/docs/01_BUSINESS_MODEL.md §4.2) |
| Total cash | £18k–£46k | Funded from services revenue and, from Q3, grant cost recovery |

## Priorities / Risks / Next actions

Priorities

Clear the gates before the outreach: entity (G1), IP with David Agunede (G2) and the claims re-base (G3) are partnership prerequisites, not parallel tracks. Services and community co-design proceed under G1/G3 only.

Engage Tier 1 in the first 90 days: one HIN programme application, DigitalHealth.London application, two paid co-design proposals (Five X More, Birthrights), a gateway account, and public-route introductions to SFH Nigeria and Nigeria Health Watch.

Treat mDoc and Jacaranda as partner tests: one documented complementarity conversation each before any further product spend in Nigeria or Kenya.

Build the evidence coalition early: a university co-applicant and a HIN evaluation route by month 6, so that 2027 grant bids have partners named.

Keep every partner claim auditable: partnership register, public-reference protocol and a monthly zero-unverified-claims check across website, decks and investor material.

Risks

IP unresolved → every Health Solutions partnership freezes; mitigation: the plan degrades gracefully to HIN, co-design and E-Learning partnerships, and the day-30 and day-90 decision points are explicit.

Incumbent reads outreach as competitive (mDoc, MSD for Mothers) and closes Nigeria doors; mitigation: §5.5 wording rules, no Ekiti restatement, "move state" fallback with Oyo/Kano scored.

Founder capacity: ~60 partnership days compete with ~87 billable days and fundraising; mitigation: Tier 1 only in Q1; an in-country associate and a fractional partnerships lead from Q3 if services revenue allows.

Community organisations approached as free endorsement by a start-up with no track record damages reputation permanently; mitigation: paid co-design only; written credit; no logos.

Grant dependence: two bids at single-digit to ~20% success rates (ESTIMATE) may yield nothing; mitigation: bids are a by-product of partnerships, not the plan's spine; services revenue funds the year.

Regulatory or data exposure through a partner (e.g., a gateway or NGO handling data without a DPA, or the un-audited prototype used in a demo with real data); mitigation: DPIA and data-sharing agreements before any data; prototype audit (/docs/04_MATERNALINK_PRODUCT_STRATEGY.md §25) before any partner demo.

Bribery Act and NHS conflict-of-interest exposure from referral fees or in-country intermediaries; mitigation: §0 rule 5, §5.6 policy, no payments to officials, agent due diligence.

Next actions

Day 1–7: create the partnership register and conflicts register; write the one-page LOI and MoU templates; identify the regional HIN and its current programme calendar; draft the two paid co-design briefs (£3k–£8k each).

Day 7–14: submit or diarise the HIN and DigitalHealth.London applications (once incorporated); open the Africa's Talking-type gateway account; send introduction requests to SFH Nigeria and Nigeria Health Watch via public routes; hold the Ekiti status call (by day 26 at the latest).

Day 14–30: send the co-design proposals to Five X More and Birthrights; map university contacts (NPEU, King's, LSHTM) and NIHR ARC programmes; recruit the first two advisory-board members through diaspora and clinical networks.

Day 30: G2 decision point — if the IP agreement is signed, send the mDoc complementarity email and open Jhpiego/SFH cohort conversations; if not, hold all Health Solutions outreach and record the decision.

Day 60: Ekiti go/no-go with the two-state scorecard; first re-score of the long-list; update /docs/06_CUSTOMER_SEGMENTS.md §3.4 on the design-partner route (NHS trust vs private maternity vs NGO).

Day 90: quarterly partner review; Q2 plan confirmed; partnership section of the investor narrative updated with documents only — never conversations.