# 20 — VYTALIX DECISION FRAMEWORK (BUILD / TEST / DEFER / KILL)

Owner: Founder (CEO), with the Chief of Staff as scorer of record · Status: PROPOSED · Version: 1.0 (8 September 2026) · Governed by: /FACTS_BASE.md (every score is an ASSUMPTION or ESTIMATE unless the evidence column says KNOWN or VERIFIED) · Used by: /docs/18_90_DAY_EXECUTION_PLAN.md gates G-C (Day 3), G-D (Day 60), task 3.16 (grant bid/no-bid, Fri 23 Oct 2026), task 4.7 (MVP build decision, Tue 8 Dec 2026) and task 4.16 (quarterly re-score); /docs/16_ORGANISATION_AND_SOPS.md SOP 03 step 3 and SOP 07; /docs/17_FOUNDER_OPERATING_SYSTEM.md §2.4 (quarterly re-score) · Related: /docs/00_MASTER_AUDIT.md §5–§6, /docs/01_BUSINESS_MODEL.md, /docs/04_MATERNALINK_PRODUCT_STRATEGY.md, /docs/05_MARKET_STRATEGY.md, /assets/PRICING_STRUCTURE.md

## Executive view

One scoring sheet for every idea that competes for the founder's time or the company's cash: ten criteria, each 1–10, unweighted, total out of 100, with three criteria reverse-scored (cost, regulatory risk, execution complexity — a high score means low cost, low risk, low complexity) and four knock-out rules that override the total. Verdicts: BUILD ≥ 70 · TEST 50–69 · DEFER 35–49 · KILL < 35.

Applied to the eight live ideas today: BUILD founder-led advisory (76). TEST the research report as lead magnet (65), MaternaLink v1 care-coordination (59) and UK NHS pilot pursuit as a design-partner evaluation (54). DEFER e-learning launch in year 1 (49) and white-label MaternaLink for NGOs (45). KILL the MaternaLink AI risk score as a product now (33; knock-out on regulatory risk) and the Ekiti proposal at £300 per woman per year as written (33; knock-out on strategic fit and an unvalidated price). Every score is a desk ESTIMATE from the audit, not a forecast.

"KILL" means the idea as stated is not pursued; it does not mean the underlying opportunity is dead. The AI risk score re-enters as a v3 research track with a data partner and an ethics route; the Ekiti conversation re-enters as a partner-aware, re-priced option scored at gate G-D on Day 60 (Thu 12 Nov 2026).

"TEST" is a commitment to a defined experiment with a budget cap, a KPI and a decision date — not a soft yes. The three TEST verdicts already have their experiments in the 90-day plan (report 1 by Week 9–10; PRD sign-off and the MVP build decision on Day 86; 15 UK discovery interviews and five design-partner briefs by Day 90).

Re-score quarterly (first: week of Mon 14 December 2026) and at every gate; any score that moves by three or more points must cite new evidence. A blank template (§6) is provided for future ideas; scoring without evidence labels is not accepted.

## 1. The ten criteria

| # | Criterion | What it measures | Direction | 1 means | 10 means | Evidence that raises confidence |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Strategic fit | Alignment with the group thesis: services fund the company, MaternaLink (in development) is the equity story, UK-first then Nigeria, non-diagnostic v1, truth-first | Normal | Contradicts the thesis or the language rules | Directly advances the thesis and at least two pillars | Business model §1; FACTS_BASE A4–A6 |
| 2 | Revenue potential | Realistic cash in 12–24 months and the size of the stream at maturity, probability-weighted | Normal | No path to cash | Large, recurring, high-margin, evidenced | Signed engagements; validated pricing; comparable programmes |
| 3 | Customer demand | Evidence that a named buyer wants this and can pay | Normal | No buyer conversation; no public evidence | Multiple paying customers or signed LOIs | Discovery calls; LOIs; public procurement signals |
| 4 | Speed to market | Time to first paying customer or first live use | Normal | > 24 months | < 1 month | Dependency chain in the 90-day plan |
| 5 | Cost | Cash required to reach the first result (reverse-scored) | Reverse | > £250k before first result | < £2k | Budget lines in the 90-day plan and financial model |
| 6 | Scalability | Growth without proportional founder time or cost | Normal | Founder-hours only | Software-like margins across markets | Unit economics in the business model |
| 7 | Competitive advantage | Defensible difference versus named alternatives, buildable within 12 months | Normal | Commodity; incumbents stronger on every axis | Unique, protected, evidenced | Competitive intelligence doc |
| 8 | Regulatory risk | Exposure to medical-device, data-protection, clinical-safety, procurement and financial-promotion rules (reverse-scored) | Reverse | Requires a claim or pathway Vytalix cannot lawfully make or fund now | No regulatory exposure beyond ordinary B2B | Legal and regulatory doc §2–§6 |
| 9 | Execution complexity | Number of dependencies, partners, skills and unknowns between now and the first result (reverse-scored) | Reverse | Many external dependencies, several unknowns, no owner | One owner, known steps, no external dependency | Task dependencies in the 90-day plan |
| 10 | Founder leverage | Whether the solo founder can deliver it with current skills, time and network without hiring first | Normal | Requires a team the company does not have | Founder can deliver alone within the time-allocation rule | Founder OS §1; hiring plan triggers |

Reverse-scoring rule. Criteria 5, 8 and 9 are assessed as High / Medium / Low first, then scored so that Low = 8–10, Medium = 4–7, High = 1–3. This keeps every criterion pointing the same way: a higher total is always better, and a reader can compare ideas by a single number.

Evidence labels. Each score carries one of KNOWN / VERIFIED / ASSUMPTION / ESTIMATE / TO VALIDATE. A score of 8 or above on criteria 2, 3 or 7 requires at least one KNOWN or VERIFIED item in the evidence column; without it the score is capped at 7.

## 2. Thresholds and verdicts

| Verdict | Total /100 | Meaning | What happens next | Rationale for the band |
| --- | --- | --- | --- | --- |
| BUILD | ≥ 70 | Commit founder time and budget; put it in the operating plan with owner, dates and KPIs | Enters the 90-day plan as P0/P1 tasks; reported weekly | An average of 7 across all ten criteria means the idea is strong on nearly every dimension and weak on none that matters; with unweighted criteria this is the level at which a pre-seed company can commit scarce time without hedging |
| TEST | 50–69 | Promising but with real unknowns; run a bounded experiment | A written test card: hypothesis, budget cap (£ ESTIMATE), KPI, decision date; re-scored on that date | The mid-band is where most product ideas sit before validation; the right response is to buy evidence cheaply, not to commit or abandon |
| DEFER | 35–49 | Not now; revisit when a named trigger fires | Logged with the trigger (e.g., "after MVP", "after first NHS design partner", "Month 9"); no time spent beyond a waitlist or a note | Below the midpoint the idea fails on several criteria at once; spending time now would starve a BUILD or TEST item |
| KILL | < 35 | Not pursued as stated | Recorded with the reason; the underlying opportunity may re-enter as a differently stated idea | An average under 3.5 means the idea fails on most dimensions; carrying it forward costs credibility with investors and buyers |

Knock-out rules (override the total):

K1 — Strategic fit ≤ 3 → KILL regardless of total. An idea that contradicts the thesis or the language rules is not improved by scoring well elsewhere.

K2 — Regulatory risk ≤ 2 → cannot be BUILD or TEST. Maximum verdict DEFER until a lawful, funded pathway exists; if the idea requires a claim prohibited by /FACTS_BASE.md §4 it is KILL as stated.

K3 — Founder leverage ≤ 2 with no funded team → cap at DEFER. The company has one operator; an idea that needs a team the company cannot pay for waits for the round or the revenue.

K4 — Customer demand ≤ 2 → cannot be BUILD. Nothing is built without at least one buyer conversation that says so.

Tie-breaks and adjustments: if two ideas compete for the same founder hours, the one that creates revenue sooner (criterion 4 × criterion 2) wins; if a score sits on a band boundary, the verdict takes the lower band until evidence moves it.

## 3. The eight live ideas — scoring table

All scores are ESTIMATES made on 8 September 2026 from the audit and the strategy documents. Columns 1–10 follow §1; 5, 8 and 9 are reverse-scored (high = good).

| Idea | 1 Fit | 2 Rev | 3 Demand | 4 Speed | 5 Cost (R) | 6 Scale | 7 Adv | 8 Reg (R) | 9 Complex (R) | 10 Leverage | Total | Knock-out | Verdict |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A. Founder-led advisory | 9 | 7 | 6 | 10 | 10 | 3 | 5 | 9 | 9 | 8 | 76 | — | BUILD |
| B. Vytalix research report as lead magnet | 8 | 3 | 6 | 8 | 8 | 5 | 6 | 8 | 6 | 7 | 65 | — | TEST |
| C. MaternaLink v1 care-coordination (non-diagnostic) | 10 | 7 | 5 | 4 | 4 | 8 | 5 | 7 | 4 | 5 | 59 | — | TEST |
| D. UK NHS pilot pursuit (design-partner evaluation first) | 9 | 5 | 6 | 3 | 6 | 8 | 4 | 5 | 3 | 5 | 54 | — | TEST |
| E. E-learning launch in year 1 | 6 | 4 | 3 | 4 | 6 | 9 | 2 | 7 | 5 | 3 | 49 | — | DEFER |
| F. White-label MaternaLink for NGOs | 6 | 5 | 5 | 2 | 3 | 8 | 4 | 5 | 3 | 4 | 45 | — | DEFER |
| G. MaternaLink AI risk score as a product now | 6 | 3 | 4 | 1 | 2 | 7 | 6 | 1 | 1 | 2 | 33 | K2, K3 | KILL (now) |
| H. Ekiti proposal at £300/woman/year as written | 4 | 5 | 2 | 2 | 5 | 4 | 2 | 4 | 2 | 3 | 33 | K4 (and K1 borderline) | KILL (as written) |

## 4. Scoring rationale by idea

Each row: score · reasoning · evidence label.

### A. Founder-led advisory (Advisory days A1, retainers A2, packages C1–C10 where proof exists) — 76, BUILD

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 9 | The cash story in FACTS_BASE A6; funds the product; builds references and market knowledge | KNOWN (strategy) |
| Revenue potential | 7 | £15k–£30k contracted by Day 90 (ESTIMATE); day rates £1,200–£1,800; capped by founder days | ESTIMATE |
| Customer demand | 6 | S1/S2 segments have short cycles and a clear pain (NHS readiness, investor readiness); zero conversations held yet | ASSUMPTION; TO VALIDATE via 40 touches in Week 1 |
| Speed to market | 10 | Sellable the week the entity, insurance and a contract template exist | KNOWN (dependency chain) |
| Cost (R) | 10 | Near-zero cash: templates, insurance, CRM free tier | KNOWN |
| Scalability | 3 | Founder-hours; associates add margin but not scale | KNOWN (business model) |
| Competitive advantage | 5 | Crowded market; the UK–Nigeria corridor and maternity focus are distinctive but unproven | ASSUMPTION |
| Regulatory risk (R) | 9 | Ordinary B2B consultancy; PI insurance; no clinical claims | KNOWN |
| Execution complexity (R) | 9 | One owner, known steps, SOP 01 written | KNOWN |
| Founder leverage | 8 | Founder can deliver alone; a technical or clinical associate needed only for C3/C5/C6/C8/C9 | ASSUMPTION on founder expertise (TO CONFIRM domain depth) |

Verdict — BUILD. This is the only idea that scores 8 or above on speed, cost, regulatory simplicity, execution and founder leverage at once, and it is the only one that produces cash inside 90 days. Its weakness — scalability at 3 — is accepted because its job is to fund the company and earn references, not to be the exit. The 90-day plan already treats it as P0 (sales quota from Day 8, first SOW Day 30, three by Day 90). Demand is the unvalidated score: if fewer than five discovery calls happen by Day 14 or no proposal converts by Day 45, the re-score reduces criterion 3 and the package mix is revisited, but the verdict holds as long as the day-rate floor of £1,200 is not breached.

### B. Vytalix research report as lead magnet ("The State of Digital Maternal Care Coordination: UK and Nigeria, 2026") — 65, TEST

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 8 | Credibility asset for every pillar; feeds proposals, investor materials and the PRD; master audit opportunity 6 | KNOWN |
| Revenue potential | 3 | Indirect only; 5 inbound conversations targeted; no direct sales | ESTIMATE |
| Customer demand | 6 | Buyers and investors read landscape reports; no evidence yet that this one will be downloaded | ASSUMPTION |
| Speed to market | 8 | Draft by Week 7, publish Week 9–10 | KNOWN (plan) |
| Cost (R) | 8 | £1k–£2k design; founder time for 20 interviews | ESTIMATE |
| Scalability | 5 | One asset, reused many times; not a revenue engine | KNOWN |
| Competitive advantage | 6 | Few small-n mixed UK–Nigeria reports exist on this question; transparent method is the differentiator | ASSUMPTION |
| Regulatory risk (R) | 8 | Professional interviews, no patient data; consent, ICO registration and privacy notice needed | KNOWN |
| Execution complexity (R) | 6 | 20 interviews, a survey, a landscape scan, design and PR — all founder-run | KNOWN |
| Founder leverage | 7 | Founder can deliver; a designer for £1k–£2k | ESTIMATE |

Verdict — TEST. The report is the cheapest credibility asset available and it doubles as the market-validation work the company must do anyway (the 15 UK interviews are shared with task 3.7). It stays a TEST rather than a BUILD because its value is indirect and unproven: the test card is "150 downloads in 14 days, 400 in 90 days, 5 inbound conversations, 3 citations" with a decision on report 2 taken at the quarterly re-score in December. If downloads fall below 50 in 14 days, the second report is not commissioned and the interview material is reused as articles instead.

### C. MaternaLink v1 care-coordination platform (non-diagnostic; care-coordination, communication, education, monitoring-support) — 59, TEST

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 10 | The equity story, re-based to the intended-use statement adopted at gate G-C | KNOWN |
| Revenue potential | 7 | Site licences £40k–£120k/yr (ESTIMATE) in the UK; programme licences £8k–£60k in Africa; pilots small; 12–24 months away | ESTIMATE |
| Customer demand | 5 | National reviews (Ockenden, Kirkup) evidence the communication problem; no buyer has yet said it would pay; Ekiti outcome unknown | VERIFIED (problem) / TO VALIDATE (willingness to pay) |
| Speed to market | 4 | MVP 12–16 weeks after a funded build decision (Day 86 at the earliest); first live use 2027 | KNOWN (plan) |
| Cost (R) | 4 | MVP build, CSO, DPIA, security baseline, hosting — a six-figure envelope over 12 months (ESTIMATE; see MVP spec) | ESTIMATE |
| Scalability | 8 | Software; multi-market; SMS channel for Nigeria | ASSUMPTION |
| Competitive advantage | 5 | Care-coordination and handover focus with interoperability is a defensible position, but incumbents exist in both markets (competitive intelligence doc) | ASSUMPTION |
| Regulatory risk (R) | 7 | Designed to sit outside device classification (TO VALIDATE with counsel); still needs DTAC, DCB0129, DSPT, DPIA, NDPA in Nigeria | KNOWN (pathway) / TO VALIDATE (qualification) |
| Execution complexity (R) | 4 | IP resolution, prototype audit, CSO, clinical advisers, design partners, engineering — many dependencies | KNOWN |
| Founder leverage | 5 | Needs a fractional CTO, a CSO and clinical advisers before build; founder can run discovery and PRD | KNOWN |

Verdict — TEST. MaternaLink v1 is the reason the company exists and it scores 10 on fit, but it cannot be a BUILD today: IP is undocumented (gate G-B), the prototype is unaudited, no buyer has confirmed willingness to pay and no clinician has reviewed the PRD. The test is already written into the plan — PRD v0.2 signed off with a CSO and a clinical adviser (Day 60), 15 UK discovery interviews and five design-partner briefs (Day 90), the prototype audit (Day 30) and the MVP build decision on Tue 8 Dec 2026 (build / build-lite / wait). Criterion 3 rises to 7 or more only with a signed design-partner LOI; criterion 9 rises once the IP deed is executed and the audit reports "pass" or "conditions". A total of 70 or more at the December re-score is the condition for a funded BUILD.

### D. UK NHS pilot pursuit (design-partner evaluation with one trust or private maternity provider, then a paid pilot) — 54, TEST

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 9 | UK-first thesis; a trust evaluation is the credibility milestone investors ask for | KNOWN |
| Revenue potential | 5 | Design partnership £0–£5k; paid pilot £20k–£60k after evaluation; site licence later (all ESTIMATE) | ESTIMATE |
| Customer demand | 6 | Problem evidenced by national reviews; trusts have been burnt by unvalidated maternity apps; no UK conversation held yet | VERIFIED (problem) / TO VALIDATE |
| Speed to market | 3 | Procurement and governance 8–16 weeks after artefacts exist; artefacts (DTAC pack, hazard log, DPIA, Cyber Essentials) are Phase 3–4 work | KNOWN |
| Cost (R) | 6 | Mostly founder time; CSO days; Cyber Essentials fee | ESTIMATE |
| Scalability | 8 | One successful evaluation is repeatable across trusts with the same artefacts | ASSUMPTION |
| Competitive advantage | 4 | Incumbent maternity digital tools exist; Vytalix's advantage is artefacts-first and coordination focus, unproven | ASSUMPTION |
| Regulatory risk (R) | 5 | DCB0160 on the trust side, DTAC, DSPT, information-governance sign-off; manageable but non-trivial | KNOWN |
| Execution complexity (R) | 3 | Depends on IP, MVP or a demonstrable prototype, CSO, a clinical champion and a trust innovation lead | KNOWN |
| Founder leverage | 5 | Founder can run discovery and relationship building; delivery needs CSO and engineering | KNOWN |

Verdict — TEST. The right idea at the wrong altitude: a "pilot pursuit" today would be a promise without a product. Scored as what the plan actually does — discovery interviews, a synthesis note, five design-partner briefs and one LOI in drafting by Day 90 — it is a bounded test with near-zero cash cost. It stays below BUILD because speed (3) and complexity (3) are structural until the MVP decision and the assurance artefacts exist. Trigger to re-score upward: a written expression of interest from a maternity digital lead or a trust innovation team plus a CSO engaged. The rule from the outreach engine applies throughout: never describe any NHS conversation as a partnership or an approval.

### E. E-learning launch in year 1 (courses on sale before Month 9) — 49, DEFER

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 6 | A named pillar, but the business model places first revenue at Month 9 and treats it as year-2 income | KNOWN |
| Revenue potential | 4 | £49–£299 per course (ESTIMATE); volume requires an audience that does not exist yet | ESTIMATE |
| Customer demand | 3 | No waitlist, no learner conversation, no employer or NGO buyer identified | KNOWN (absence) |
| Speed to market | 4 | Two courses could be authored in a quarter, but the audience takes longer than the content | ESTIMATE |
| Cost (R) | 6 | LMS £25–£250/month, production time; modest cash, significant founder hours | ESTIMATE |
| Scalability | 9 | Self-serve, high gross margin once built | KNOWN (model) |
| Competitive advantage | 2 | Crowded market of platforms and professional bodies; no accreditation may be claimed | KNOWN |
| Regulatory risk (R) | 7 | Low if no CPD or accreditation claims are made and clinical content is reviewed | KNOWN |
| Execution complexity (R) | 5 | Content authoring, clinical review, platform, payments, marketing funnel | KNOWN |
| Founder leverage | 3 | Every hour spent here is taken from the revenue block; founder cannot author, review and market alone in year 1 | KNOWN |

Verdict — DEFER. Scalability is the best in the set and the regulatory burden is light, but demand is unevidenced, the competitive position is weak and the founder's hours are the binding constraint. The plan's treatment stands: a waitlist page and two course outlines by Day 90 (task 4.14), free primers from Month 6 to build the funnel, first courses at Month 9 (ESTIMATE), corporate and NGO licences later. Trigger to re-score: 500 waitlist sign-ups or one corporate or NGO training conversation with a budget — either would move criteria 3 and 2 enough for TEST.

### F. White-label MaternaLink for NGOs (branded patient-facing layer licensed to NGO programmes) — 45, DEFER

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 6 | Consistent with the NGO route to a Nigeria cohort, but white-labelling a product that does not exist yet is a year-2 stream in the business model | KNOWN |
| Revenue potential | 5 | Set-up £25k–£75k plus £2–£8 per user per year (ESTIMATE); real but distant | ESTIMATE |
| Customer demand | 5 | NGOs have enrolled women, CHEWs and donor reporting needs; none has been asked whether they want a white-label rather than a programme licence | ASSUMPTION |
| Speed to market | 2 | Requires v1 to exist, plus multi-tenant branding and data-residency configuration | KNOWN |
| Cost (R) | 3 | Adds engineering on top of the MVP envelope | ESTIMATE |
| Scalability | 8 | Software licence; repeatable across programmes and telecoms later | ASSUMPTION |
| Competitive advantage | 4 | Incumbent programmes (mDoc, MomConnect-style services) already serve NGO and state cohorts | VERIFIED (incumbents exist) |
| Regulatory risk (R) | 5 | Cross-border data flows, NDPA registration, safeguarding on shared phones; manageable with design | KNOWN |
| Execution complexity (R) | 3 | Depends on v1, an NGO partner, in-country associate, data-residency architecture | KNOWN |
| Founder leverage | 4 | Founder can hold NGO conversations; delivery needs the product team | KNOWN |

Verdict — DEFER. The idea is a delivery model for a product that is itself still a TEST, so it cannot score higher than the product it depends on. The nearer path to an NGO cohort is the programme licence in the product strategy §13 (enrolment, SMS workflows, defaulter tracing, logframe exports) priced to a grant budget line, which needs no white-label engineering. Trigger to re-score: an NGO or telecom partner asking for a branded instance in writing after v1 is live. Until then the white-label option is a line in the partnership deck, not a workstream.

### G. MaternaLink AI risk score ("Maternal Instability Score") as a product now — 33, KILL (now); re-enters as the v3 research track

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 6 | Long-term vision yes; as a product now it contradicts FACTS_BASE A4 and the language rules | KNOWN |
| Revenue potential | 3 | No lawful sale before validation and a device pathway; years away | KNOWN |
| Customer demand | 4 | Clinicians want earlier warning; buyers will not procure an unvalidated predictive tool | ASSUMPTION |
| Speed to market | 1 | Data partnership, ethics approval, validation study, SaMD conformity assessment: > 24 months | KNOWN |
| Cost (R) | 2 | Research, data governance, clinical evaluation, Approved Body costs: well above £250k (ESTIMATE) | ESTIMATE |
| Scalability | 7 | If ever validated, high | ASSUMPTION |
| Competitive advantage | 6 | Multimodal (clinical + voice + social) concept is distinctive on paper; no data, model or validation exists | VERIFIED (concept only) |
| Regulatory risk (R) | 1 | Almost certainly a medical device (prediction/prognosis intended purpose); no MHRA pathway, ethics approval or data access exists | KNOWN |
| Execution complexity (R) | 1 | Requires a university or NHS research partner, data-sharing agreements, ethics, a clinical lead, ML engineering and QMS | KNOWN |
| Founder leverage | 2 | Cannot be delivered by the current team | KNOWN |

Verdict — KILL as a product now (knock-outs K2 and K3). Shipping or even pitching a predictive score today would expose Vytalix to medical-device regulation it cannot meet, to investor diligence it would fail, and to reputational harm in a field where over-claiming is unforgivable. This is the "KILL-now" referenced at gate G-C. The opportunity is preserved, not discarded: the concept moves to the v3 research track in the product strategy §8, advancing only through a university or NHS research partnership with data access, ethics approval and a clinical lead, funded by research grants (NIHR i4i, Grand Challenges — eligibility TO VALIDATE). It is re-scored as a research proposal, not a product, when such a partner exists.

### H. The Ekiti State proposal at £300 per woman per year as written (15,000 women, £4.5m Phase 1) — 33, KILL (as written); a re-scoped option is scored at gate G-D

| Criterion | Score | Reasoning | Evidence |
| --- | --- | --- | --- |
| Strategic fit | 4 | Nigeria is the second market, but a £36m headline government sale led by an unresolved collaborator contradicts UK-first, truth-first and the IP position | KNOWN |
| Revenue potential | 5 | Large headline; probability-weighted value is low — no response, no budget line, unvalidated price | VERIFIED (proposal only) |
| Customer demand | 2 | No evidence of acceptance, contract or payment since 18 March 2026; the state already runs a funded programme | VERIFIED |
| Speed to market | 2 | Government cycles 3–9 months at best; this one has been silent for six months | KNOWN |
| Cost (R) | 5 | Pursuing it costs founder time and relationship capital more than cash; delivering it would cost far more than the company has | ESTIMATE |
| Scalability | 4 | Government programmes scale politically, not commercially; donor logic dominates | ASSUMPTION |
| Competitive advantage | 2 | mDoc's Digital Mom Project is incumbent, donor-funded, with ~24,000 women onboarded (public reporting) | VERIFIED |
| Regulatory risk (R) | 4 | NDPA, procurement and anti-bribery exposure; IP not owned; board approval required for any government proposal | KNOWN |
| Execution complexity (R) | 2 | Depends on IP resolution, in-country delivery capacity, a product that does not exist, and a ministry that has not replied | KNOWN |
| Founder leverage | 3 | The relationship, if real, sits with David Agunede; the founder cannot deliver a state programme alone | KNOWN |

Verdict — KILL as written (knock-out K4; K1 borderline). The proposal as sent — £300 per woman per year, £4.5m for Phase 1, £36m for the state — is not restated under any option because the price is an unvalidated proposal figure, the state has an incumbent, and Vytalix does not yet own what was proposed. That is a decision about a document, not about Nigeria. The plan keeps the conversation alive on facts: an Ekiti status call by Day 26, an mDoc complementarity conversation by Day 54, a two-state scorecard (Oyo and Kano lead on the desk estimate in the market strategy §2.1) by Day 55, and gate G-D on Thu 12 Nov 2026. If the ministry identifies a gap and mDoc is open to complementarity, a partner-aware LGA pilot at a £6–£40 per woman per year platform layer (ESTIMATE) and an envelope under £0.5m per year is drafted for board approval and scored on this sheet as a new idea; the default if that fails is to move state with an NGO or donor cohort.

## 5. Portfolio view and what the scores say about the next 90 days

| Rank | Idea | Total | Verdict | Owner of the next step | Decision date |
| --- | --- | --- | --- | --- | --- |
| 1 | Founder-led advisory | 76 | BUILD | Founder | Continuous; first SOW Tue 13 Oct 2026 |
| 2 | Research report as lead magnet | 65 | TEST | Founder (+ designer) | Report 2 go/no-go at the December re-score |
| 3 | MaternaLink v1 care-coordination | 59 | TEST | Founder + CSO + fractional CTO | MVP build decision Tue 8 Dec 2026 |
| 4 | UK NHS pilot pursuit (design-partner first) | 54 | TEST | Founder | Design-partner pipeline review Fri 11 Dec 2026 |
| 5 | E-learning launch in year 1 | 49 | DEFER | Founder | Trigger: 500 waitlist sign-ups or one B2B training conversation with budget |
| 6 | White-label MaternaLink for NGOs | 45 | DEFER | Founder | Trigger: written request after v1 is live |
| 7 | AI risk score as a product now | 33 | KILL (now) | — | Re-enters only as a research proposal with a data partner |
| 8 | Ekiti proposal at £300/woman/year | 33 | KILL (as written) | Founder; board | Re-scoped option scored at G-D, Thu 12 Nov 2026 |

Reading: the portfolio is one cash engine (A), three bounded experiments that share most of their inputs (B, C, D all draw on the same 15–20 interviews, the same CSO and the same intended-use statement), two parked options with named triggers, and two ideas retired as stated so that the company never has to defend them in diligence. Founder time in the 90 days follows this ranking: revenue first (40%), then the shared validation work behind B–D.

Grant bid/no-bid (task 3.16, Fri 23 Oct 2026) uses the same sheet on each candidate call: a bid scores BUILD only if eligibility is KNOWN, a required clinical partner is at "agreed in principle" and the founder-day cost (10–15 days per bid, ESTIMATE) does not breach the sales quota for more than one week.

## 6. Blank template for future ideas

Copy this block into the decision log or into this file under a new heading. Every score needs a one-line reason and an evidence label; totals without reasons are not accepted at the Friday review.

IDEA: [name, stated precisely — "X for Y priced at Z by [date]"]
Proposed by: [name]      Date scored: [dd Mon yyyy]      Scorer: [name]
Trigger for scoring: [gate / inbound approach / quarterly re-score / other]
Depends on: [ideas or gates this cannot precede, e.g. G-B IP resolution, MVP build]

| # | Criterion                     | Raw view (H/M/L for 5, 8, 9) | Score 1–10 | One-line reason | Evidence label |
|---|-------------------------------|------------------------------|-----------|-----------------|----------------|
| 1 | Strategic fit                 |                              |           |                 |                |
| 2 | Revenue potential             |                              |           |                 |                |
| 3 | Customer demand               |                              |           |                 |                |
| 4 | Speed to market               |                              |           |                 |                |
| 5 | Cost (reverse: low = high)    |                              |           |                 |                |
| 6 | Scalability                   |                              |           |                 |                |
| 7 | Competitive advantage         |                              |           |                 |                |
| 8 | Regulatory risk (reverse)     |                              |           |                 |                |
| 9 | Execution complexity (reverse)|                              |           |                 |                |
| 10| Founder leverage              |                              |           |                 |                |
|   | TOTAL /100                    |                              |           |                 |                |

Knock-outs checked: K1 fit ≤ 3 [ ]  K2 reg ≤ 2 [ ]  K3 leverage ≤ 2 without funded team [ ]  K4 demand ≤ 2 [ ]
Caps applied: 8+ on criteria 2/3/7 without KNOWN/VERIFIED evidence → capped at 7 [ ]

VERDICT: BUILD (≥70) / TEST (50–69) / DEFER (35–49) / KILL (<35)  → [verdict]
If TEST — test card: hypothesis: [ ]  budget cap (ESTIMATE): £[ ]  KPI: [ ]  decision date: [ ]
If DEFER — trigger to re-score: [ ]
If KILL — reason in one sentence and what (if anything) re-enters differently stated: [ ]
Language check: does pursuing this require any statement prohibited by /FACTS_BASE.md §4?  [yes → KILL as stated / no]
Logged in decision log as: D-[nnn]      Next re-score: [date]

## Priorities / Risks / Next actions

Priorities

Act on the verdicts as they stand: advisory at full quota; the three TEST ideas run as the bounded experiments already dated in the 90-day plan; nothing spent on DEFER items beyond a waitlist and a note; KILL items retired from every external document.

Score the re-scoped Ekiti option and the grant bid/no-bid on this sheet before either goes to the board — no government proposal and no bid without a logged score.

Re-score all eight ideas in the week of Mon 14 December 2026 with the evidence gathered by Day 90 (interviews, audit, IP outcome, first engagements, report downloads).

Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Scores treated as facts (they are desk ESTIMATES by one scorer) | Medium | Medium | Evidence labels mandatory; a second scorer (adviser or NED) from the first advisory-board meeting; changes ≥ 3 points must cite new evidence |
| Sunk-cost pressure to keep the Ekiti proposal or the AI score alive as stated | Medium | High | Knock-out rules are written and board-visible; the re-entry routes (G-D option; v3 research track) give the ideas a legitimate home |
| TEST verdicts drifting into open-ended work without decision dates | High | Medium | Every TEST has a test card with a date; the Friday review lists them; the quarterly re-score closes them |
| Founder leverage scored optimistically because the founder is the scorer | Medium | Medium | Time audit data from the founder OS replaces the assumption after four weeks |
| Unweighted criteria hide that strategic fit and regulatory risk matter more at this stage | Low | Medium | Knock-outs K1 and K2 carry that weight explicitly; weights are revisited at the first quarterly re-score if the portfolio changes |

Next actions

| Action | Owner | Deadline |
| --- | --- | --- |
| Ratify the eight verdicts and the framework at the first board meeting; log as D-007 | Founder; board | Tue 13 Oct 2026 |
| Score the grant bid/no-bid candidates from the grant calendar | Founder | Fri 23 Oct 2026 |
| Score the re-scoped, partner-aware Ekiti option (if the ministry identifies a gap) ahead of gate G-D | Founder; advisory board profile 4 if appointed | Thu 12 Nov 2026 |
| Score the MVP build / build-lite / wait options with the audit, IP and design-partner evidence | Founder; board | Tue 8 Dec 2026 |
| Quarterly re-score of all live ideas; publish the scoring template as the Week 12 practical post | Founder | Week of Mon 14 Dec 2026 |