## Cover
Content Calendar
Twelve weeks from Monday 14 September 2026 across LinkedIn, website, email, video and events; consistent with the marketing engine.
Prepared for | The Founder, Vytalix
Date | 8 September 2026
Version | 1.0 · Confidential draft
Contents
Calendar | Dated items with pillar, format, CTA, owner and status
Colour code: yellow cells are inputs you can change; blue headers are fixed; every figure is an ESTIMATE unless labelled VERIFIED (see FACTS_BASE).

## Calendar
week | date | channel | title | pillar | format | CTA | owner | status
1 | 2026-09-14 | website/insights | Foundations: analytics tracking sheet opened; domain and social handles reserved within 24 h of the name decision (Fri 18 Sept); no paid brand assets before clearance | n/a (infrastructure) | Setup task | None | Founder | Gated: name decision Fri 18 Sept (doc 18 task 1.2/1.11)
1 | 2026-09-15 | LinkedIn | Founder profile rewrite: headline 'Founder, Vytalix — health-technology advisory, consulting and MaternaLink (in development)'; About carries the stage disclosure 'Pre-seed, founder-led' | P4 Building Vytalix in public | Profile update | Follow the 90-day build | Founder | Planned (doc 14 §3.1)
1 | 2026-09-15 | LinkedIn | Why I'm starting a health-tech group with a consultancy, not an app | P4 Building Vytalix in public | Text post (insight) | Reply or DM if you run a health-tech company trying to reach the NHS, or a maternity service trying to make digital tools useful | Founder | Drafted (doc 14 §7 Post 1)
1 | 2026-09-16 | LinkedIn | Day 1: what Vytalix is, what it isn't, and what I don't know yet | P4 Building Vytalix in public | Text post (build-in-public) | Follow the 90-day plan; tell me what I've missed | Founder | Drafted (doc 14 §7 Post 2)
1 | 2026-09-17 | LinkedIn | The three questions I ask before any digital maternity idea | P1 Digital maternity and inequality | Text post (practical) | Comment with the question you would add | Founder | Planned
1 | 2026-09-18 | LinkedIn | 20 substantive comments this week on posts by midwives, maternity digital leads, health-tech founders and investors (no 'great post') | P1 Digital maternity and inequality | Engagement | None | Founder | Planned (weekly rule, doc 14 §3.1)
2 | 2026-09-22 | LinkedIn | Ockenden and Kirkup keep finding the same failure: communication (both reports cited) | P1 Digital maternity and inequality | Text post (insight) | Read both reports in full; tell me what you take from them | Founder | Drafted (doc 14 §7 Post 3)
2 | 2026-09-23 | LinkedIn | We are calling the AI risk score a research track. Here's why. | P4 Building Vytalix in public | Text post (build-in-public) | Ask me anything about the intended-use decision | Founder | Drafted (doc 14 §7 Post 4)
2 | 2026-09-24 | LinkedIn | A one-page intended-use statement — the most valuable document a health-tech founder can write | P2 Health-tech go-to-market and regulation (UK) | Text post + template (practical) | DM for the one-page template | Founder | Planned
2 | 2026-09-24 | LinkedIn | Vytalix company page live: what we are, what we are not, and the stage disclosure (founder reposts) | P4 Building Vytalix in public | Company page post | Follow the page | Founder | Gated: name decision; page live by Fri 25 Sept (doc 18 task 2.13)
2 | 2026-09-25 | website/insights | Article A1 draft: 'DTAC without the panic — a founder's map of NHS digital assurance' (outline per doc 14 §8; 1,800 words) | P2 Health-tech go-to-market and regulation (UK) | Long-form article (draft) | None (internal) | Founder | Drafting
2 | 2026-09-25 | LinkedIn | 20 substantive comments this week (target-audience posts) | P2 Health-tech go-to-market and regulation (UK) | Engagement | None | Founder | Planned
3 | 2026-09-28 | website/insights | Website staging: entity details in footer and legal pages (privacy, cookies, terms), contact-form data statement, Search Console verification, schema.org Organization | n/a (infrastructure) | Setup task | None | Founder | Gated: incorporation (Day 10–12); publish as soon as ready, no later than Fri 9 Oct (doc 18 task 2.12; doc 14 week 3 target)
3 | 2026-09-29 | LinkedIn | What DTAC actually asks for (and what it doesn't) | P2 Health-tech go-to-market and regulation (UK) | Text post (insight) | Save this; ask me about the readiness sequence | Founder | Drafted (doc 14 §7 Post 5)
3 | 2026-09-30 | LinkedIn | Naming a company when four similar names already exist (the real Week 1 story, whatever the outcome) | P4 Building Vytalix in public | Text post (build-in-public) | Share your own naming lesson | Founder | Planned
3 | 2026-10-01 | LinkedIn | Discovery interview guide: 12 questions for maternity teams (template) | P5 Learning and method | Carousel / template (practical) | Download the guide; volunteer for a 30-minute interview for Report 1 | Founder | Planned
3 | 2026-10-01 | LinkedIn | Company page: what Vytalix Advisory and Consulting do, packages with 'from' prices (ESTIMATE labels kept) | P2 Health-tech go-to-market and regulation (UK) | Company page post | Book a free 30-minute session (one per prospect) | Founder | Planned
3 | 2026-10-02 | email | Newsletter tool live with double opt-in; sign-up form linked from LinkedIn and the site; privacy notice and ICO reference in the footer | n/a (infrastructure) | Setup task | Subscribe (double opt-in) | Founder | Gated: ICO registration (doc 18 task 2.3); tool live Fri 2 Oct (task 2.12)
3 | 2026-10-02 | LinkedIn | 20 substantive comments this week (target-audience posts) | P1 Digital maternity and inequality | Engagement | None | Founder | Planned
4 | 2026-10-06 | LinkedIn | The £300-per-woman question: how to price a maternal health programme honestly (figure described as 'proposed' and being re-based) | P3 UK–Africa corridor | Text post (insight) | If you've priced a programme like this, compare notes with me | Founder | Drafted (doc 14 §7 Post 6); publish only after the pricing memo is adopted Mon 5 Oct (doc 18 task 2.9)
4 | 2026-10-06 | website/insights | Article A1 published: 'DTAC without the panic — a founder's map of NHS digital assurance' (LinkedIn article Tue 6 Oct; mirrored on the website Insights page at launch) | P2 Health-tech go-to-market and regulation (UK) | Long-form article | Subscribe to the newsletter; ask about the C6 DTAC & Evidence Readiness Sprint | Founder | Planned
4 | 2026-10-07 | LinkedIn | Week 4: first proposals out. What buyers pushed back on. (real objections only; if none yet, say so) | P4 Building Vytalix in public | Text post (build-in-public) | Tell me what you would have pushed back on | Founder | Planned
4 | 2026-10-08 | LinkedIn | DTAC readiness self-check: 20 items | P2 Health-tech go-to-market and regulation (UK) | Carousel (practical) | Save and share; DM for the checklist file | Founder | Planned
4 | 2026-10-08 | email | Signal issue 1 (working title, TO VALIDATE): one thing / what we're building / three links / a template / one ask | P4 Building Vytalix in public | Newsletter (fortnightly, Thu 08:00 UK) | Reply with one introduction or one critique | Founder | Planned; if the list is too small, hold to Fri 23 Oct (doc 18 task 3.17)
4 | 2026-10-08 | webinar/event | Event 1: attend one London NHS-digital or health-tech founder event (organiser dates and cost TO VALIDATE before booking) | P2 Health-tech go-to-market and regulation (UK) | Event attendance | 10 conversations; same-day CRM update; follow-up within 48 h | Founder | Planned (date TO VALIDATE)
4 | 2026-10-09 | website/insights | Website v1 live: Home, Advisory, Consulting, Health Solutions (MaternaLink in development, intended-use statement visible), E-Learning waitlist, Insights, About, Contact; sitemap submitted | n/a (infrastructure) | Site launch | Contact form; newsletter sign-up | Founder | Gated: incorporation, ICO, legal pages (doc 18 task 2.12)
4 | 2026-10-09 | LinkedIn | 20 substantive comments this week (target-audience posts) | P2 Health-tech go-to-market and regulation (UK) | Engagement | None | Founder | Planned
5 | 2026-10-13 | LinkedIn | Ekiti already has a digital maternal programme. That's good news, if you design for it. (Nigeria Health Watch cited) | P3 UK–Africa corridor | Text post (insight) | If you work in this space in Nigeria, tell me what I'm missing | Founder | Drafted (doc 14 §7 Post 7)
5 | 2026-10-14 | LinkedIn | Interviewing 20 people for our first report: what surprised me in the first 10 (publish only when 10 interviews are done; otherwise report the real count) | P4 Building Vytalix in public | Text post (build-in-public) | Volunteer for an interview | Founder | Planned
5 | 2026-10-14 | website/insights | Report 1 interview recruitment page: participant information sheet, consent form, 'no patient data' statement, privacy link | P1 Digital maternity and inequality | Landing page | Volunteer for a 30-minute interview | Founder | Planned (doc 14 §9 Report 1 ethics)
5 | 2026-10-15 | LinkedIn | Hazard log starter: 9 hazards every maternity communication tool must consider | P2 Health-tech go-to-market and regulation (UK) | Carousel / template (practical) | DM for the starter hazard log | Founder | Planned
5 | 2026-10-15 | webinar/event | Webinar 1 announced: 'Designing maternity communication tools that don't become medical devices by accident' — Tue 17 Nov, 12:30–13:15 UK (TO VALIDATE diary); registration page live | P2 Health-tech go-to-market and regulation (UK) | Event announcement (registration page + company page event) | Register (double opt-in) | Founder | Planned (doc 14 §10)
5 | 2026-10-16 | LinkedIn | 20 substantive comments this week (target-audience posts) | P1 Digital maternity and inequality | Engagement | None | Founder | Planned
6 | 2026-10-20 | LinkedIn | Is your app a medical device? The one question that decides it (UK) | P2 Health-tech go-to-market and regulation (UK) | Text post (insight) | Write down your qualification decision; ask me how | Founder | Drafted (doc 14 §7 Post 8)
6 | 2026-10-21 | LinkedIn | Why our v1 will display data and not interpret it | P4 Building Vytalix in public | Text post (build-in-public) | Clinicians: tell me where this breaks | Founder | Planned
6 | 2026-10-22 | LinkedIn | Grant calendar for maternal health-tech, Q1 2027 (all dates TO VALIDATE on funder sites) | P5 Learning and method | Table / carousel (practical) | DM for the calendar; ask about the C7 Grant & Investor Readiness Sprint | Founder | Planned
6 | 2026-10-22 | website/insights | Article A2 published: 'Intended use is a product decision, not a legal afterthought' (1,500 words; MaternaLink v1 statement as the worked example) | P2 Health-tech go-to-market and regulation (UK) | Long-form article | Subscribe; register for Webinar 1 | Founder | Planned (doc 14 §8 A2)
6 | 2026-10-22 | email | Signal issue 2: intended use; report interviews progress; Webinar 1 registration; template of the fortnight | P2 Health-tech go-to-market and regulation (UK) | Newsletter | Register for Webinar 1 | Founder | Planned
6 | 2026-10-23 | LinkedIn | Company page: Webinar 1 promotion (1 of 6 promotional touches) and Article A2 repost | P2 Health-tech go-to-market and regulation (UK) | Company page post | Register for Webinar 1 | Founder | Planned
6 | 2026-10-23 | LinkedIn | 20 substantive comments this week (target-audience posts) | P2 Health-tech go-to-market and regulation (UK) | Engagement | None | Founder | Planned
7 | 2026-10-27 | LinkedIn | Black maternal health in the UK: the numbers, the sources, the caveats (current MBRRACE-UK report cited) | P1 Digital maternity and inequality | Text post (insight) | Read the MBRRACE-UK report; correct me if a figure is out of date | Founder | Planned
7 | 2026-10-28 | LinkedIn | The IP conversation every founder with a collaborator must have early | P4 Building Vytalix in public | Text post (build-in-public) | If you're in this situation, do it this week | Founder | Drafted (doc 14 §7 Post 9)
7 | 2026-10-29 | LinkedIn | How to run a 30-minute discovery call that respects a midwife's time | P5 Learning and method | Text post + checklist (practical) | DM for the call structure | Founder | Planned
7 | 2026-10-30 | website/insights | Report 1 draft v1 (internal): 8–10 findings, must/must-not design list, buyer's checklist, limitations section | P1 Digital maternity and inequality | Report draft (internal) | None (internal) | Founder | Drafting (doc 18 task 3.15: draft by Fri 13 Nov)
7 | 2026-10-30 | email | PR pre-brief drafted: 120-word pitch for 3 outlets (Digital Health, HTN, Nigeria Health Watch — editorial contacts TO VALIDATE; public editorial addresses only) | P1 Digital maternity and inequality | PR pitch (draft) | None (internal) | Founder | Drafting (doc 14 §3.5)
7 | 2026-10-30 | LinkedIn | 20 substantive comments this week (target-audience posts) | P1 Digital maternity and inequality | Engagement | None | Founder | Planned
8 | 2026-11-03 | LinkedIn | Care coordination is not care. Why the distinction matters for safety. | P1 Digital maternity and inequality | Text post (insight) | Clinicians: where does coordination end and care begin for you? | Founder | Planned
8 | 2026-11-04 | LinkedIn | Report 1 is in design. Three findings I'm nervous to publish. | P4 Building Vytalix in public | Text post (build-in-public) | Pre-register for the report download | Founder | Planned
8 | 2026-11-05 | LinkedIn | Handover summary template (antenatal → intrapartum) | P5 Learning and method | Template (practical) | DM for the template; volunteer to critique it | Founder | Planned
8 | 2026-11-05 | email | Signal issue 3: report preview; Webinar 1 reminder; handover template | P1 Digital maternity and inequality | Newsletter | Register for Webinar 1; pre-register for the report | Founder | Planned
8 | 2026-11-06 | website/insights | Report 1 design (freelance designer, £1k–£2k ESTIMATE) and gated download page with UK GDPR/PECR consent wording | P1 Digital maternity and inequality | Report design + landing page | None (internal until launch) | Founder + designer | Planned (doc 18 task 4.3)
8 | 2026-11-06 | webinar/event | Webinar 1 rehearsal: slides v1; guest speaker only if confirmed in writing, otherwise founder-only; tooling TO VALIDATE (LinkedIn Live or Zoom) | P2 Health-tech go-to-market and regulation (UK) | Rehearsal | None (internal) | Founder (+ guest if confirmed in writing) | Planned
8 | 2026-11-06 | LinkedIn | 20 substantive comments this week (target-audience posts) | P2 Health-tech go-to-market and regulation (UK) | Engagement | None | Founder | Planned
9 | 2026-11-10 | LinkedIn | Report launch: The State of Digital Maternal Care Coordination — UK and Nigeria, 2026 | P1 Digital maternity and inequality | Launch post + carousel (insight) | Download the report (email with explicit consent) | Founder | Planned; launch Thu 12 Nov target (doc 14 week 9), hard deadline Fri 20 Nov (doc 18 task 4.3)
9 | 2026-11-11 | LinkedIn | What 20 interviews told us about who actually owns the communication problem | P4 Building Vytalix in public | Text post (build-in-public) | Download the report; tell me if your experience differs | Founder | Planned
9 | 2026-11-12 | LinkedIn | Ten things buyers of maternity digital tools should ask vendors | P2 Health-tech go-to-market and regulation (UK) | Carousel (practical) | Save and share; download the buyer's checklist in the report | Founder | Planned
9 | 2026-11-12 | website/insights | Report 1 published on the Insights page: gated download; copy sent to every interviewee; aggregated survey results published | P1 Digital maternity and inequality | Research report (20–28 pages) | Download the report | Founder | Planned (target 150 downloads in 14 days)
9 | 2026-11-12 | email | PR pitch sent to 3 outlets with the report's headline finding as the hook; founder available for comment on maternity-digital topics | P1 Digital maternity and inequality | PR pitch | Request an interview or the full report | Founder | Planned (1 earned mention target)
9 | 2026-11-13 | LinkedIn | Company page: report launch; direct invites to 100 CRM contacts for Webinar 1 (promotional touches 3–4 of 6) | P1 Digital maternity and inequality | Company page post + direct invites | Download the report; register for Webinar 1 | Founder | Planned
9 | 2026-11-13 | LinkedIn | 20 substantive comments this week (target-audience posts) | P1 Digital maternity and inequality | Engagement | None | Founder | Planned
10 | 2026-11-17 | LinkedIn | Webinar today: designing maternity communication tools that don't become medical devices by accident | P2 Health-tech go-to-market and regulation (UK) | Text post (insight) | Join at 12:30 UK; registration link | Founder | Planned
10 | 2026-11-17 | webinar/event | Webinar 1 delivered: 25-min talk + 15-min Q&A + 5-min close; recorded; offer of one free 30-minute session per prospect | P2 Health-tech go-to-market and regulation (UK) | Live webinar (45 min) | Book a free 30-minute session (one per prospect) | Founder (+ guest if confirmed in writing) | Planned (targets: 60 registrations, 40% attendance, 5 discovery calls)
10 | 2026-11-18 | LinkedIn | What I got wrong in the first 60 days | P4 Building Vytalix in public | Text post (build-in-public) | Tell me what you would have done differently | Founder | Planned
10 | 2026-11-19 | LinkedIn | Webinar recording + slide pack | P2 Health-tech go-to-market and regulation (UK) | Text post with link (practical) | Watch the recording; book a session | Founder | Planned
10 | 2026-11-19 | email | Signal issue 4: webinar recording; report findings; follow-up sequence to registrants (attended / did not attend variants) | P2 Health-tech go-to-market and regulation (UK) | Newsletter + follow-up sequence | Book a free 30-minute session | Founder | Planned
10 | 2026-11-20 | video | Webinar 1 recording cut into 5 short clips (60–90 s, captions burned in, no music) — queued for native LinkedIn video | P2 Health-tech go-to-market and regulation (UK) | Short-form video (5 clips) | Watch the full recording | Founder | Queued; native video publishing begins Month 4 per doc 14 §3.7
10 | 2026-11-20 | LinkedIn | 20 substantive comments this week (target-audience posts) | P2 Health-tech go-to-market and regulation (UK) | Engagement | None | Founder | Planned
11 | 2026-11-24 | LinkedIn | Interoperability with what's already there: designing for DHIS2 and incumbent platforms in Nigeria | P3 UK–Africa corridor | Text post (insight) | Nigeria digital-health colleagues: what should a new entrant connect to first? | Founder | Planned
11 | 2026-11-25 | LinkedIn | We're looking for midwives and obstetricians to co-design MaternaLink (in development) — here's what it involves and what it doesn't | P4 Building Vytalix in public | Text post (build-in-public) | Express interest via the co-design form | Founder | Planned
11 | 2026-11-26 | LinkedIn | Clinical advisory group terms of reference (template) | P5 Learning and method | Template (practical) | DM for the template | Founder | Planned
11 | 2026-11-26 | website/insights | Article A3 published: 'Designing for what already exists: digital maternal health in Nigeria in 2026' (2,000 words; mDoc/MSD for Mothers cited from public reporting; NDPA points TO VALIDATE) | P3 UK–Africa corridor | Long-form article | Subscribe; ask about the C5 Africa Market-Entry & Partner Scan | Founder | Planned (doc 14 §8 A3)
11 | 2026-11-26 | webinar/event | Clinician co-design call (45 min, online) for those who expressed interest; what co-design involves, what it does not (no diagnosis, no extra clicks) | P1 Digital maternity and inequality | Online call | Join the co-design group (written consent before any name is used) | Founder | Planned (target 3 clinician conversations)
11 | 2026-11-27 | video | Webinar clip 1 of 5 (queued) | P2 Health-tech go-to-market and regulation (UK) | Short-form video | Watch the full recording | Founder | Queued (publish from Month 4)
11 | 2026-11-27 | LinkedIn | 20 substantive comments this week (target-audience posts) | P3 UK–Africa corridor | Engagement | None | Founder | Planned
12 | 2026-12-01 | LinkedIn | Selling to the NHS in 2027: the routes that actually work for a small vendor | P2 Health-tech go-to-market and regulation (UK) | Text post (insight) | Ask about the C4 UK Market-Entry Playbook | Founder | Planned
12 | 2026-12-02 | LinkedIn | 90 days in: the scorecard, honestly (actuals only — targets are never published as results) | P4 Building Vytalix in public | Text post (build-in-public) | Keep replying, arguing, introducing and correcting me | Founder | Drafted as a template (doc 14 §7 Post 10); fill with Day 90 actuals
12 | 2026-12-03 | LinkedIn | Our decision-scoring framework (10 criteria) — free template | P5 Learning and method | Template (practical) | Download the template (docs/20_DECISION_FRAMEWORK.md §6) | Founder | Planned
12 | 2026-12-03 | email | Signal issue 5: 90-day scorecard; Q1 2027 plan; one ask | P4 Building Vytalix in public | Newsletter | Reply with one introduction | Founder | Planned
12 | 2026-12-04 | website/insights | Analytics review: Search Console, site sessions, report downloads, subscribers, inbound conversations; Q1 2027 content calendar drafted | n/a (infrastructure) | Review memo (internal) | None (internal) | Founder | Planned (doc 14 §5 week 12)
12 | 2026-12-04 | website/insights | E-Learning waitlist page live; two course outlines drafted (no build; year-2 revenue per decision framework) | P5 Learning and method | Landing page | Join the waitlist | Founder | Planned (doc 18 task 4.14; target 50 sign-ups)
12 | 2026-12-04 | LinkedIn | 20 substantive comments this week (target-audience posts) | P4 Building Vytalix in public | Engagement | None | Founder | Planned