# 07 — Getting customers

How you find people who will pay you, what you say to them, and what you publish while you do it.

## In one minute

Your first money comes from advisory work you deliver yourself, not from the app.

Sell to UK health-tech founders and investors first. They decide in weeks, not months.

Every week: 40 new contacts, 20 conversations, 5 calls, 2 proposals.

Never claim a client, an approval or a pilot you do not have.

Publish three posts a week, one report and one webinar in 90 days.

## What to do

| Action | Who | By when |
| --- | --- | --- |
| Build the 150-name contact list and set up the CRM | You | Fri 18 Sept 2026 |
| Send the first 40 messages, using the templates below | You | Fri 18 Sept 2026 |
| Hold the first 5 discovery calls and send 2 proposals | You | Sun 27 Sept 2026 |
| Full weekly rate every week from here on | You | From Mon 28 Sept 2026 |
| Sign the first client; sign the third | You | Tue 13 Oct and Fri 11 Dec 2026 |

## Where the first clients come from

Spend at least 60% of your selling time on the first two groups. They pay fastest.

| Who | What they buy | Typical deal (ESTIMATE, our best guess) | How long they take |
| --- | --- | --- | --- |
| UK digital-health start-ups | Help getting NHS-ready, investor-ready, and to market | £2.5k to £5k a month, or £7.5k to £15k for a sprint | 2 to 6 weeks |
| UK health-tech investors and accelerators | Workshops for their companies, help checking a deal | £5k to £20k per programme | 4 to 8 weeks |
| NHS-adjacent bodies and charities | Research, procurement readiness, training | £5k to £25k a project | 8 to 16 weeks |
| African health ministries, NGOs and donors | Strategy, programme design, pilot scoping | £10k to £50k a study | 3 to 9 months |

Weekly targets by channel:

| Channel | What you do each week | What good looks like |
| --- | --- | --- |
| LinkedIn messages | 40 connection requests, 20 messages | 30% accept, 15% reply |
| LinkedIn posts | 3 posts, 20 real comments on other people's posts | 5 inbound conversations a month |
| Warm introductions | 5 asks | 2 introductions |
| Cold email | 25 new contacts, to public business addresses only | 8% reply |
| Events | 1 UK health-tech event a fortnight | 10 conversations, 3 follow-up meetings |
| Referrals | Ask "who else should I speak to?" on every call | 2 customer referrals a month |
| Partners | 2 new conversations with accelerators or networks | 1 referral agreement a quarter |

The floor, every week from week three: 40 new contacts, 20 conversations, 5 discovery calls, 2 proposals.

## The conversation

A discovery call is a first 30-minute call to find out what someone needs. Keep to this shape.

| Minutes | What you do |
| --- | --- |
| 0 to 3 | Thank them, agree the agenda, ask permission to ask questions |
| 3 to 8 | Their role, their organisation, what made them take the call |
| 8 to 18 | The problem: what happens today, what they have tried, what it costs them |
| 18 to 23 | The decision: budget, who signs, timing, what success looks like |
| 23 to 27 | Say back what you heard; describe one or two ways you could help. No hard sell |
| 27 to 30 | Agree one specific next step and a date |

The eight questions worth asking:

What made you take this call now?

How is this handled today, and what have you already tried?

What does success look like for you in six months?

What is this costing you now, in time, money or risk?

Who signs off on money like this, and is there a budget already?

What is setting the timing: a board meeting, a funding round, a deadline?

What would make this a no?

If we started on a set date, what would the first two weeks need to deliver?

Write the answers into the CRM the same day, under: problem, cost, who decides, budget, timing, what success means, next step.

## Two emails and one message

Email 1 — first contact with a founder

Subject: [Company]'s NHS route — one question

Hi [First name], I read your [post about X]. One question: have you mapped the DTAC and clinical-safety evidence you will need before an NHS pilot conversation, or is that still ahead of you?

I am Kelvin, founder of Vytalix, a UK health-technology advisory group. We are early ourselves. We are building MaternaLink, a maternal care-coordination platform, in development, so I have been living these questions first-hand.

If it helps, I can share the one-page checklist I use. Worth 20 minutes next week?

Kelvin Williams, Vytalix

Email 2 — the same day as a call

Subject: Notes and next steps from today

[First name], thank you for your time today. What I heard: (1) [the problem], (2) [what it costs you], (3) [your deadline]. You would call it a success if [their words].

Next step: I will send a short proposal with two options by [date], and we decide by [date]. If I have misread anything, tell me now and I will correct it.

LinkedIn message, after they accept your request

Thanks for connecting, [Name]. One question: what is the hardest part of [their challenge] at [Organisation] right now? I am asking founders and leaders this as I shape Vytalix's advisory work, and I am glad to share back what I am hearing.

## The ten objections and what to say

| They say | You say |
| --- | --- |
| "You are too new, you have no track record." | "True, and I will not pretend otherwise. What I bring is [your real experience]. The work is fixed-scope and paid on delivery, and the first piece is small. If it does not land, you stop." |
| "Too expensive." | "Compared with what? If it is in-house time, let us cost that. If it is budget, Option A is scoped to [price] and the rest can wait." |
| "No budget this quarter." | "Understood. Would a smaller piece at [price] that builds your business case for next quarter help? Otherwise let us put a date in for [month]." |
| "We can do this ourselves." | "You can. The question is speed. We would compress weeks of learning. If you would rather build the skill in-house, the workshop version hands the method to your team." |
| "Send me some information." | "Happy to. So I send the right thing: is the priority [A] or [B]? I will send a one-pager and suggest 15 minutes to talk it through." |
| "We are talking to a bigger firm." | "Good, and compare us on who actually does the work, on speed and on price. I deliver it myself, and I will put that in writing." |
| "Is MaternaLink live? Can we see it?" | "MaternaLink is in development. There is an early prototype and I will show it as a concept, not a product. Today is about the advisory work, which does not depend on it." |
| "Are you NHS-approved or CE-marked?" | "No, and we do not claim to be. Advisory work does not need it. Any software going into the NHS would go through DTAC and clinical safety first, which is the path we help clients plan." |
| "It is not the right time." | "When would be? What changes by then? If [trigger] happens sooner, would you want to move faster?" |
| "Can you do it for free, or for equity?" | "I will give you a free 30 minutes. Paid work stays paid, because that is how I stay independent. Equity only alongside cash, and only where it fits." |

## What you put out publicly

Every dated item is a row in /assets/CONTENT_CALENDAR.csv. That file is the schedule; this table is the shape.

| Month | What you publish | What you are aiming for |
| --- | --- | --- |
| Month 1, 14 Sept to 13 Oct | Rewritten LinkedIn profile with "pre-seed" said out loud. 12 posts. Company page once the name is cleared. Website live with the legal pages and honest prices marked "from". First article. Newsletter issue 1. | 500 relevant followers, 300 website visits, 50 subscribers |
| Month 2, 14 Oct to 12 Nov | 12 posts. Second article. Newsletter issues 2 and 3. Twenty interviews for the research report. Webinar announced. Report drafted and designed. | 900 followers, 200 subscribers, 60 webinar registrations, 3 inbound conversations |
| Month 3, 13 Nov to 12 Dec | Webinar on Tue 17 Nov, 12:30 to 13:15. Research report "The State of Digital Maternal Care Coordination: UK and Nigeria, 2026" published Fri 20 Nov, with a download form. Press pitch to three outlets. Third article. 12 posts. Newsletter issues 4 and 5. | 1,500 followers, 300 subscribers, 150 downloads in 14 days, 40 webinar attendees, 1 press mention |

The report is 20 to 28 pages, built on 20 interviews and a survey, with the limits of the method stated in it. No patient data is used.

## How to price a proposal, and when to walk away

Keep the proposal to about four pages: what you understood, what success means, what you will do, when, the price, what you assume, and a signature line. Offer two or three options and put a date on which the price expires.

| Rule | The number |
| --- | --- |
| Day rate | £900, range £800 to £1,200 (ESTIMATE) |
| Monthly retainer | £2,500 to £5,000 |
| Fixed sprint | £7,500 to £25,000 |
| Never go below | £650 a day equivalent |
| Discount | 15% at most, and only for prepayment or volume. Never cut price without cutting scope or getting something back, such as a reference |
| Payment | Projects 50% up front. Retainers monthly in advance |
| Free work | One free 30-minute session per prospect. No free workshops |
| MaternaLink pilots | Never free. Minimum £10,000 (ESTIMATE), and only with data-protection and safety conditions agreed first |
| Nigerian government work | Quote in pounds or dollars. At least 30% paid before you start. No work before that payment arrives |

Walk away when any of these is true: they ask you to go below the floor; they want free work or equity with no cash; after two calls nobody will name who signs; they want you to say something untrue, such as NHS-approved or clinically proven; the scope keeps growing while the price stays still.

## What to measure each week

Six numbers, in the Friday review. Nothing else.

| Number | Target |
| --- | --- |
| New contacts added | 40 |
| Real conversations held | 20 |
| Discovery calls held | 5 |
| Proposals sent | 2 |
| Posts published | 3 |
| Inbound enquiries (they came to you) | 3 by week 4, 15 by week 13 |

## Words explained

| Word | What it means |
| --- | --- |
| CRM | The software that holds your contacts, your deals and what stage each one is at |
| Discovery call | A first 30-minute call to find out what someone needs, before any pitch |
| Retainer | A fixed monthly fee for an agreed amount of your time |
| Sprint | A fixed piece of work with a fixed price and an end date |
| DTAC | The NHS checklist a digital product must pass before a hospital can buy it |
| Inbound | Someone who contacts you first, rather than you contacting them |
| Mobilisation payment | Money paid up front so you can start work, common in government contracts |