# 08 — Running the company

How you run the company day to day: the shape of your week, the numbers you check, and the six routines to write down.

## In one minute

You are one person, so the day has a fixed shape and money work always comes first.

Every Friday you spend 45 minutes answering five questions and setting three commitments.

You track about 15 numbers. They live in /operations/KPI_DASHBOARD.csv.

You buy expertise by the day. You do not hire anyone until money already in the bank pays for them.

Vytalix gets at least 70% of your working time. Kemek Enterprise Ltd gets 30% at most.

## What to do

| Action | Who | By when |
| --- | --- | --- |
| Block the daily and weekly shape in your calendar; start a daily log | You | Mon 14 Sept 2026 |
| Put Month 1 targets and first real numbers into /operations/KPI_DASHBOARD.csv | You | Fri 18 Sept 2026 |
| Run the first Friday review using the five questions below | You | Fri 18 Sept 2026, 15:30 |
| Hold the first monthly close with your accountant | You + accountant | Wed 14 Oct 2026 |
| Hold the first quarterly reset and decide what to stop | You | Week of Mon 14 Dec 2026 |

## Your week

Fifty working hours. Same shape every day, so you never have to decide what to do first.

| When | What you do | What you end up with |
| --- | --- | --- |
| Every day 08:00–08:30 | Read yesterday's numbers. Write the day's three priorities. One must be money. | Three priorities in the daily log |
| Every day 08:30–11:00 | Money block: 8 new contacts, 5 follow-ups, one call attempt, work you are paid for | CRM updated the same day |
| Every day 11:15–12:45 | The week's priority: investor preparation, product, partners or admin | One task finished |
| Every day 13:30–15:30 | Meetings. All external calls sit here. | Notes written within 30 minutes |
| Every day 15:30–17:00 | Second quiet block: writing, delivery, product and safety papers | Progress on the thing due |
| Every day 17:00–17:30 | Shut down: log the day, set tomorrow's three. Kemek work only after this. | Day closed |
| Monday 08:00 (45 min) | Plan the week. Set targets. Block the calendar. | Weekly plan |
| Wednesday 12:00 (15 min) | Are you on quota? If not, move Thursday and Friday. | Adjusted plan |
| Friday 14:00 (2 hrs) | Write next week's three posts. Check every claim. | Content scheduled |
| Friday 15:00 (30 min) | Clean the pipeline. Every open deal gets a dated next action. | Both CSV files current |
| Friday 15:30 (45 min) | The five questions below. Set three commitments. | Review filed in /operations/reports/ |
| Friday 16:15 (15 min) | Reconcile the bank. Update the 13-week cash sheet. | Cash and runway known |
| Monthly, 5th working day | Close the books with the accountant. Write a one-page report. Re-score the audit. Send the investor update. Check hiring triggers. | Report and score trend |
| Quarterly, first in Dec 2026 | Half a day: what worked, what to stop, next quarter's plan. Refresh the risk list. | Next quarter planned |

Two rules protect the shape. Keep two 90-minute blocks a day with no meetings. Take no more than 12 external meetings a week.

## The five questions to answer every Friday

Answer them in this order. Write one line for each. Then write three commitments for next week.

| # | Question | What you write down |
| --- | --- | --- |
| 1 | What made money this week? | Contacts, calls, proposals, signed work, cash received. The best conversation. The stuck deal and how you unstick it. |
| 2 | What moved an investor? | Touches, replies, meetings. The one new proof point you added: an adviser, a client, a published piece. |
| 3 | What moved the product? | Which gate moved. Interviews held. Any feature that crosses the medical-device line. |
| 4 | What moved a partner? | Conversations in the UK and Nigeria. Briefs sent. Where Ekiti stands. Advisory board progress. |
| 5 | What needs a decision? | Deadlines in the next 14 days. Cash and runway. Admin hours. One thing to stop doing. |

If the answer to question 1 is thin two weeks running, cancel everything optional next week and sell.

## What to measure

Sixteen numbers. Full definitions, sources and owners live in /operations/KPI_DASHBOARD.csv. Every target below is PROPOSED (a plan, not a promise). Every actual today is zero (VERIFIED).

| Group | Number | How you work it out | Month 1 | Month 2 | Month 3 |
| --- | --- | --- | --- | --- | --- |
| Money | Cash in bank (£) | Company bank balance at month end | £12k–£16k | £13k–£19k | £15k–£25k |
| Money | Runway (months) | Cash divided by average monthly burn over three months | 2–4 | 4–8 | 6 or more |
| Money | Revenue invoiced (£) | Invoices raised in the month | £0–£3k | £4k–£8k | £7k–£12k |
| Money | Costs (£) | Everything you spent running the company | £4k–£8k | £2.5k–£5k | £3k–£6k |
| Money | Days to get paid | Money owed to you, divided by revenue, times days | 30 or fewer | 30 or fewer | 30 or fewer |
| Customers | New contacts | New people in the CRM who fit the target list, each with a source link | 60 | 50 | 40 |
| Customers | Discovery calls held | Count of first calls completed | 10 | 15 | 15 |
| Customers | Proposals sent | Written proposals with a price and a start date | 3 | 4 | 5 |
| Customers | Signed clients | Signed statements of work | 1 | 1 | 1 |
| Customers | Contracted revenue (£) | Value of work signed in the month | £3k–£6k | £6k–£10k | £8k–£14k |
| Investors | Investors contacted | Records with at least one logged approach | 0 | 50 | 75 |
| Investors | Investor meetings held | Meetings completed | 0 | 4 | 6 |
| Product | Milestones closed | Gates and checks closed that month | 3 | 3 | 3 |
| Product | Discovery interviews | Women and health professionals interviewed, running total | 4 | 10 | 16 |
| Marketing | Website visits | Sessions in the month | 300 | 800 | 1,500 |
| Marketing | Inbound enquiries | Messages from people you did not approach first | 3 | 6 | 15 |

Investor numbers stay at zero until four things are true and written down: the company exists, the MaternaLink ownership agreement is signed, the 2025 prediction claims are withdrawn everywhere, and the one-pager and data room are ready.

## Who does what now, and who you hire when

You are the accountable owner of every function today. The table says what you do yourself, what you buy by the day, and what waits.

| Job | Now | Roughly what it costs (ESTIMATE — our best guess, not a fact) | What triggers the change |
| --- | --- | --- | --- |
| Selling and delivering the work | You | Your time | Nothing. This is your first job every day. |
| Legal and trademark | Pay a solicitor and a trademark attorney | £4k–£9k for 90 days; £800–£2,000 for the mark | Start now, before anything is signed |
| Accounts and tax | Pay an accountant | £80–£200 a month | At the moment the company is registered |
| Clinical safety | Pay a Clinical Safety Officer by the day | £500–£900 a day, 1–2 days a month | Before any build work starts |
| Technical check of the prototype | Pay a fractional CTO | £1k–£2.5k for the audit | Once you have access to the code |
| Advisers (4 people) | You recruit them | Small share options, or £500–£1,000 a meeting | Once the company exists |
| Admin help (virtual assistant) | You, for now | £650–£1,100 a month | When your admin passes 8 hours a week, two weeks running |
| Product lead, one day a week | You, for now | £2k–£3.5k a month | When a design partner signs a letter of intent |
| Engineers | Nobody | £140k–£320k over 16 weeks | Only when a grant or round pays for it and the ownership deed is signed |
| Salesperson | You | £55k–£70k plus commission | Services revenue at £15k a month for three months |
| Marketing, half time | You | £18k–£25k a year | Inbound at 15 a month for two months and revenue at £10k a month |
| Nigeria country lead | You | £1.5k–£3k a month | Only when a Nigeria pilot has a budget behind it |

The rule underneath the whole table: no salaried person is hired until either signed work pays for them or a closed round names the role. If neither the round nor a funded pilot lands, Vytalix stays a two-person services firm.

## The six routines worth writing down

### 1. Winning work

Trigger: Monday planning, or any enquiry (answer inside 24 hours).

Who: You. An assistant can research names and log the CRM. Never someone else selling.

Steps: Pull the target list and set the week's quota: 40 new contacts, 20 conversations, 5 calls, 2 proposals. Research each person and save the source link. Send one message with one personal reason. Follow up at 4, 10 and 21 days. Run the 30-minute call and write notes within half an hour. Decide inside 48 hours: proposal, second call, refer out, or close. Price from the standard menu, never below the £1,200 day floor. Check every claim before it goes out. Chase at +3 days by phone and +7 days by email, each time with one new proof point.

What you end up with: Proposals out, a clean pipeline, signed statements of work.

How you know it worked: Five calls a week. Three clients signed by 12 December 2026.

### 2. Taking on a client

Trigger: A signed statement of work arrives.

Who: You deliver. An assistant handles logistics.

Steps: Open the private client folder within 24 hours. Hold a 45-minute kick-off within three working days and agree what "done" means in their words. Send the kick-off note within 24 hours; that note is your baseline for any scope change. Confirm in writing that no patient data will be shared. Deliver something real within ten working days. Check in weekly. Anything over 10% more work gets re-quoted. Finish with a sign-off note, the final invoice and a ten-minute feedback call.

What you end up with: A finished piece of work, an invoice paid, a reusable template, a referral.

How you know it worked: Kick-off inside three days every time. Score of 8 out of 10 or better.

### 3. Approaching investors

Trigger: All four pre-conditions logged as met. Earliest date Wed 14 Oct 2026. Until then you only prepare.

Who: You. Your solicitor checks the wording before the first message goes out.

Steps: Write the pre-condition check into the decision log; if one is open, stop. Re-check each investor record before contact and note the date. Write one personal reason per investor. Phone first where a public number exists, otherwise email under 150 words. Log every touch the same day. No second follow-up without a new proof point. On a reply, offer three slots inside seven days and send the one-pager 24 hours ahead. Ask "what would stop you?" and answer in writing within 48 hours. Ask for one referral in every meeting. When someone asks for the data room, send it, then answer every question inside 48 hours.

What you end up with: A working investor list, meetings booked, a data room that stands up.

How you know it worked: 125 investors contacted and 10 meetings held by day 90.

### 4. Approaching partners

Trigger: Quarterly partner planning, or any approach from a health organisation.

Who: You, with your NHS adviser and your Nigeria adviser.

Steps: Keep the long list current: who they are, what they have, what you offer, what must happen first. Approach with a one-page brief. Never state or imply a relationship you do not have. Climb the ladder in order: conversation, written brief, letter of intent, pilot, contract. Your solicitor reads every signed document. Every government-facing paper carries an anti-bribery clause; no facilitation payments, ever. If patient data is involved, stop and run routine 5 first. On Ekiti: a facts-only status call, no new offer, and the old £4.5m proposal is never restated.

What you end up with: An honest partner list, briefs sent, one letter of intent in drafting.

How you know it worked: Five design-partner conversations by month three. One letter of intent being drafted by day 90.

### 5. Building the product safely

Trigger: The ownership gate has passed and a build decision is minuted.

Who: You as acting product owner, a fractional CTO for technical calls, a Clinical Safety Officer for safety.

Steps: Check the gates before any work: ownership deed signed, prototype audited, safety officer engaged with a hazard log open, data protection assessment started, intended-use statement adopted, every contributor's IP paperwork signed. Work only from the written requirements. Run two-week sprints. Apply the line-crossing check to every single feature: if it interprets, scores, alerts on, triages or predicts from clinical information, it is out of version 1. Interview at least 20 women and 10 professionals per market before you freeze the build. Release only through staging, a penetration test and a safety sign-off.

What you end up with: Gate evidence, a hazard log, a safety case, software you can defend.

How you know it worked: Three milestones closed each month. Zero open critical hazards at release.

### 6. Money and reporting

Trigger: Any signature (invoice), Friday 16:15 (cash), the 5th working day (close).

Who: You. Your accountant closes the month and files.

Steps: Invoice on signature and on each milestone, same day, 14-day terms. Chase at day 7, day 15 and day 30. Do no new work for an account more than 30 days overdue. Reconcile the bank every Friday and recompute runway. Any spend over £250 needs one line of justification; over £2,500 needs two quotes. Draw nothing until a month's revenue passes £7,500, then £3,000 a month. Keep Kemek money completely out of Vytalix accounts. Close the month by working day five. Label every number ACTUAL, TARGET or ESTIMATE, and never claim a number before it happens.

What you end up with: Invoices, a weekly cash position, monthly accounts, a monthly one-page report.

How you know it worked: Paid within 30 days. Books closed by working day five. No missed filings.

## Working on two businesses at once

Kemek Enterprise Ltd is a real conflict, so you handle it in the open rather than pretending it is not there.

| Rule | The number |
| --- | --- |
| Vytalix share of your working time | 70% or more (about 35 hours) |
| Kemek share | 30% or less, and only after 17:30 |
| Within Vytalix: money work | 40% (about 14 hours) |
| Within Vytalix: investors | 20% (about 7 hours), from day 31 only |
| Within Vytalix: product and safety | 20% (about 7 hours) |
| Within Vytalix: partners, credibility, admin | 20% (about 7 hours) |

Log your hours daily and report the split in every Friday review. Keep the two sets of accounts fully separate. Declare the conflict in writing to the board and to any investor.

## The stop-doing list

Stop quoting the £300 per woman per year figure. It is withdrawn.

Stop using the 2025 AI prediction deck outside the company. It is withdrawn.

Stop describing MaternaLink as anything other than "in development".

Stop approaching investors until all four pre-conditions are logged as met.

Stop calling anyone a partner before something is signed. A conversation is not a partnership.

Stop counting followers and impressions as progress. Count calls, proposals and cash.

Stop building features that interpret clinical information. They belong to a much longer road.

Stop hiring in anticipation. Signed work pays for people, not hope.

Stop letting admin grow past 8 hours a week. That is the signal to buy help.

Stop doing Kemek work before 17:30.

## Words explained

| Word | What it means |
| --- | --- |
| Runway | How many months your cash lasts at the rate you are spending |
| Burn | Money going out minus money coming in each month |
| Pipeline | Every live deal, investor or partner, with a dated next step |
| Statement of work (SOW) | The signed paper saying exactly what you will do, for how much, by when |
| Letter of intent (LOI) | A written "we intend to work together". It is not a contract and not a sale. |
| Gate | A check you must pass before the next stage of work is allowed to start |
| Fractional | Someone senior you buy by the day instead of employing |
| PROPOSED | A plan we have written down but not yet tested |
| ESTIMATE | Our best guess, not a fact |
| VERIFIED | Checked against a source and true today |