## Cover
Investor Readiness Scorecard
Fifteen readiness items with owners and due dates. Update the Today column (0 or 1) weekly; the score recalculates. Rule: no first investor meeting until items 1–4 are done and two of 5–7 are done.
Prepared for | The Founder, Vytalix
Date | 8 September 2026
Version | 1.0 · Confidential draft
Contents
Scorecard | Items, targets, owners, due dates, live score
Colour code: yellow cells are inputs you can change; blue headers are fixed; every figure is an ESTIMATE unless labelled VERIFIED (see FACTS_BASE).

## Scorecard
# | Readiness item | Today (0/1) | Target | How to close | Owner | Due | Status | Notes
1 | Legal entity, bank, accountant | 0 | 1 | Name clearance, incorporate, bank, accountant, SEIS/EIS advance assurance | Founder | Day 10 | Not started
2 | MaternaLink IP owned or licensed in writing | 0 | 1 | Heads of terms then IP deed with collaborator; contributor assignments | Founder + solicitor | Day 30 | Not started
3 | No unvalidated clinical claims public | 0 | 1 | Retire 2025 deck; relabel prototype rules; auth; remove photos | Founder | Day 14 | Not started
4 | Name and trademark clearance | 0 | 1 | Knock-out searches; file UK TM classes 9, 41, 42, 44 | Founder + attorney | Day 20 | Not started
5 | First revenue | 0 | 1 | Advisory packages; 40 conversations; first SOW | Founder | Day 45 | Not started
6 | Pilot partner LOI | 0 | 1 | 15 discovery interviews; pilot proposal | Founder | Day 60 | Not started
7 | Advisory board (2 confirmed) | 0 | 1 | Named asks; advisory agreements | Founder | Day 60 | Not started
8 | Product evidence (audit, PRD, intended use, hazard log) | 0 | 1 | Code audit; clinician sign-off | CTO/CPO | Day 30 | Not started
9 | Financial model with actuals | 1 | 1 | Update with months 1–3 actuals | CFO role | Day 60 | Not started
10 | Data room | 0 | 1 | Index in doc 23 §2 | Founder | Day 45 | Not started
11 | Investor list and outreach system | 1 | 1 | Verify Call List 1 phones | Founder | Day 55 | Not started
12 | Compliance basics (ICO, Cyber Essentials, insurance) | 0 | 1 | See doc 15 | Founder | Day 30 | Not started
13 | Founder commitment statement and time split | 0 | 1 | Written statement | Founder | Day 7 | Not started
14 | Proof of demand (15 interviews) | 0 | 1 | Discovery interviews | Founder | Day 60 | Not started
15 | Non-dilutive application submitted | 0 | 1 | Innovate UK Smart / SBRI Healthcare | Founder | Day 75 | Not started
| READINESS SCORE /10 |  |  | Rule: no first investor meeting until items 1–4 are done and two of 5–7 are done