# 01 — Where you stand

An honest look at what exists today, what is missing, and what to fix first.

## In one minute

Everything that exists today is an idea, a name, a logo, one prototype and one conversation that went nowhere. That is the true starting point.

The business scores 11 out of 100. Under 20 means a company that has not started trading.

Ten problems are listed below. The first four block everything else and take about four weeks to clear.

Ten opportunities are listed too. The best one is not the product. It is selling your own advice while the product is built.

Nothing here is a criticism of the idea. The idea is sound. The company around it does not exist yet.

## What to do

| Action | Who | By when |
| --- | --- | --- |
| Agree in writing who owns MaternaLink | You and David Agunede | Day 3 |
| Register the company after checking the name | You | Day 10 |
| Withdraw the 2025 AI deck and lock the prototype | You | Day 3 |
| Book a code and security check of the prototype | A developer you pay | Day 14 |
| Re-score this document | You | 14 October |

## What was actually reviewed

| What | Where it was | What it is | Verdict |
| --- | --- | --- | --- |
| The code repository | GitHub | One file with one line of text | Empty |
| Your written brief | This project | A clear, complete description of the company you want to build | The strongest thing you had |
| "Black Maternal health" deck, October 2025 | Google Drive | 13 slides proposing AI that predicts pre-eclampsia, sepsis, bleeding and blood clots | An idea only. No data, no model, no clinician, no permission to use patient data |
| Ekiti State proposal, March 2026 | Email | Sent by David Agunede as "Founder and CEO, Maternal Link". £4.5m for 15,000 women, rising to £36m | A proposal with no reply. The price is far above anything comparable |
| The prototype dashboard | maternal-health-psi.vercel.app | A working website with patients, alerts and a risk engine that suggests clinical actions | Real, but nobody has checked who owns the code or whether it is secure |
| Kemek Enterprise investor files | Google Drive | Your separate property business, with its own 128-name investor list | Not Vytalix. It shows you can run a disciplined process. It also splits your time |
| Public record for "Vytalix" | Web search | No company found. Similar names exist in the UK and the US | The name is at risk until checked properly |

Nothing else was found. No business plan, no financial model, no website, no brand, no contracts, no customers, no revenue, no grants, no partners, no clinicians, no policies, no insurance.

## The score, area by area

Scoring: 0 means nothing exists. 3 means an idea or a draft. 5 means a usable draft that nobody has tested. 7 means it works and there is proof. 10 means best in class.

| Area | Score | Why |
| --- | --- | --- |
| Company and governance | 0 | No registered company, no board, no shareholder agreement |
| Name and brand | 1 | A logo exists. The name has not been checked and clashes with others |
| Business model and prices | 1 | One price existed and it was wrong |
| Advisory and consulting | 1 | An idea. No offers, no collateral, no clients. The fastest money in the company |
| MaternaLink | 2 | A prototype and a concept. No clinician, no evidence, no plan for regulation |
| Clinical safety | 0 | No safety officer, no hazard log, no statement of what the product is for |
| Data protection and regulation | 0 | Not registered with the ICO. No data protection assessment. No thinking about medical device rules |
| Who owns the intellectual property | 0 | Nothing written down with David Agunede or with whoever wrote the code |
| Technology | 1 | One prototype of unknown quality. No domain, no email, no cloud account |
| E-learning | 0 | Nothing exists |
| Proof that customers want it | 1 | One meeting in Nigeria. No UK conversations at all |
| Knowing the competition | 1 | The Ekiti proposal did not mention that the state already has a funded programme |
| Partners | 1 | One ministry meeting. No agreements |
| Sales system | 0 | No contact list, no scripts, no proposals |
| Marketing | 0 | No website, no company page, nothing published |
| Money and accounts | 0 | No model, no budget, no bank account, no accountant |
| Ready for investors | 1 | You have shown you can run a list. Vytalix has no deck, no data room, no tax clearance |
| Team | 1 | One founder and one informal collaborator with unclear roles |
| Routines and reporting | 0 | None |
| Credibility: advisers, evidence, press | 0 | None |
| Total | 11 / 100 | Pre-formation |

!Three columns: what you have, what you are building, what comes next (../diagrams/traction.svg)

Say it in this order to anyone who asks. Never inflate the first column.

## What is strong and what is weak

Strong. A precise founder brief. A genuinely important problem with real political attention behind it in the UK. A live conversation in Nigeria and a working prototype, which most founders at this stage do not have. Proof that you can run an investor list properly.

Weak. No company, no ownership, no brand protection. Medical claims with nothing behind them. A price built on nothing. One founder doing everything, across two businesses. No web presence at all.

The chances. Selling your own advice pays within weeks. A re-scoped MaternaLink can be trialled without becoming a medical device. Grants suit this story. Women's health and impact investors are actively looking for something like it. Partnering with the Nigerian incumbent turns a threat into a route in.

The threats. A name clash with two US health-tech companies. Regulatory trouble if any prediction feature ships. A falling-out over who owns MaternaLink. Slow, political government sales in Nigeria. An investor finding all of this in ten minutes.

## The ten problems, worst first

| # | Problem | Why it matters | What fixes it | By |
| --- | --- | --- | --- | --- |
| 1 | Nobody owns MaternaLink on paper | Blocks funding, contracts and trials. Risks a dispute | Meet this week, agree heads of terms, then a solicitor drafts a deed | Day 7 |
| 2 | No company | Cannot contract, bank, apply for grants or take investment | Check the name, then register | Day 10 |
| 3 | Medical claims with no evidence | Regulatory and reputational risk. Fails any investor check | Withdraw the deck. Re-scope the product. Rewrite what it does | Day 3 |
| 4 | The name may not be yours | Two US health-tech companies use near-identical names | Trademark searches, then file | Day 20 |
| 5 | No money coming in | Your time is the only funding | Launch three advisory offers, hold 40 conversations | Day 45 |
| 6 | The £300 per woman price | Anyone who knows the market will see it is wrong | Replace with the new price book | Day 21 |
| 7 | No clinician anywhere near this | You cannot build maternity software without midwives and doctors | Recruit four advisers | Day 60 |
| 8 | The prototype is unchecked | May contain insecure code, other people's work, or real patient data | Pay for a code and security audit | Day 14 |
| 9 | Nobody in the UK has been asked | Your home market is untested | 15 interviews with midwives and maternity leads | Day 60 |
| 10 | Two businesses, one of you | Everything waits for you | Write down your time split. Get help with admin | Day 14 |

## The ten opportunities, best first

| # | Opportunity | Why it is good | First step |
| --- | --- | --- | --- |
| 1 | Sell your own advice | Cash in weeks, references, credibility | Publish three offers, start 40 conversations |
| 2 | MaternaLink as a care-coordination service | The product story, without the medical device problem | Write what it is for, get one clinician to agree |
| 3 | Work with the Nigerian incumbent, not against | Keeps the government relationship alive | Reply to Ekiti offering to complement, not replace |
| 4 | Grants | £50,000 to £500,000 without giving away shares | Check the Innovate UK and SBRI Healthcare calendars |
| 5 | Women's health and impact investors | Better terms and aligned expectations | Work the A-list after the blockers are cleared |
| 6 | Publish one research report | Authority, press, inbound interest | Outline it in week five |
| 7 | Training for midwives and health workers | Repeat income, low regulatory risk | Two pilot modules with an NGO |
| 8 | Consulting for companies entering the NHS or Africa | High margin, repeatable | Package two fixed-price sprints |
| 9 | A university research partnership | Turns the 2025 AI idea into fundable research | Approach a maternal health research group |
| 10 | Telecoms and insurers in Nigeria | Reach without government budgets | Keep on the partner list for year two |

## What creates value, and what creates risk

| Brings money in now | Builds credibility | Makes investors comfortable | Creates real risk |
| --- | --- | --- | --- |
| Advisory days, consulting projects, grant-funded work | Advisers, a published report, a real trial, a professional website | A registered company, clean ownership, sensible prices, a named pipeline | Prediction claims, health data without safeguards, using the prototype with real patients, unclear purpose |

## Words explained

| Word | What it means |
| --- | --- |
| Heads of terms | A short written summary of what two people have agreed, before the lawyers write the full contract |
| ICO | The Information Commissioner's Office, the UK regulator you must register with to handle personal data |
| Data protection impact assessment | A written check of what could go wrong with people's data, required before you handle health information |
| Hazard log | A list a health software team keeps of everything that could harm a patient, and what stops it |
| Medical device | Anything, including software, whose purpose is to diagnose, predict or treat. Tightly regulated |