# 05 — The money: what it costs, what you raise

What the three-year plan says, how much cash it needs, and how you raise it without being caught out.

## In one minute

Three versions of the next three years exist. None has happened. Nothing has been sold.

The careful version loses money slowly. The middle version spends about £1m building the product.

Retainers are the best money in the company. Your day rate barely changes anything.

You raise in four steps. Each step needs proof, not time passing.

You are not ready to meet an investor today. Fifteen things must be fixed first.

## What to do

| Action | Who | By when |
| --- | --- | --- |
| Take the 2025 predictive claims off every public page and date-stamp the removal | Founder | Day 3 |
| Clear the name, incorporate, open the bank account, appoint the accountant | Founder | Day 12 |
| Sign the MaternaLink ownership deed with David Agunede | Founder and solicitor | Day 30 (hard stop Day 60) |
| Apply for SEIS/EIS advance assurance | Accountant | Month 1–2 |
| Take no investor meeting until items 1 to 4 below are done and two of 5 to 7 | Founder | Day 61 |

## Three versions of the future

!Money coming in over three years in three scenarios (../diagrams/revenue-3yr.svg)

Caption: These are scenarios, not forecasts; the gap between them is mostly the product, not the services.

EBITDA below means profit before interest, tax and the cost of equipment. It is the plain measure of whether the trading is paying for itself.

|  | Careful | Middle | Ambitious |
| --- | --- | --- | --- |
| Three-year revenue | £412,514 | £1,474,289 | £5,249,714 |
| Three-year EBITDA | −£239,543 | −£1,032,201 | £113,985 |
| Peak cash needed before any funding | £228,872 | £1,058,035 | £144,705 |
| Break-even that lasts | Not reached in 36 months | Not reached in 36 months | Month 31 |
| Equity raised in the model | £250,000 | £2,400,000 | £3,500,000 |
| People employed at month 36 | 2 | 8 | 10 |

The middle version loses £1m on purpose. That money buys a product, evidence and a team of eight.

## Where the money comes from

!Where the money comes from in the middle case (../diagrams/revenue-mix.svg)

Caption: Services are most of the money for the first two years; the product only matters in year three.

| Source | Three-year revenue | Share |
| --- | --- | --- |
| Advisory | £423,748 | 29% |
| Consulting | £443,333 | 30% |
| E-learning | £220,208 | 15% |
| MaternaLink | £387,000 | 26% |
| Total | £1,474,289 |  |

MaternaLink earns nothing in year one. In year three it is £282,000, and still only 34% of that year.

## How much cash you need

!How much cash is needed before money comes in (../diagrams/cash-needed.svg)

Caption: The deepest point of the hole, counted with no investment and no grants at all.

|  | Careful | Middle | Ambitious |
| --- | --- | --- | --- |
| Cash needed by month 12 | About £4k | About £36k | About £5k |
| Cash needed by month 24 | About £86k | About £253k | About £64k |
| Cash needed by month 36 | £228,872 | £1,058,035 | £144,705 (peak at month 31) |
| Lowest the bank balance ever gets | £4,726 in month 5 | £6,099 in month 3 | £12,750 in month 2 |

The first 90 days are the tightest point in all three. The rule that follows: never hire the product lead before the money lands.

## What actually moves the numbers

| What you change | From, to | Three-year revenue | Three-year EBITDA |
| --- | --- | --- | --- |
| Retainers held in years two and three | 1 to 3 | −£94k / +£96k | −£91k / +£93k |
| Average size of a consulting project | £15k to £30k | −£111k / +£222k | −£72k / +£144k |
| MaternaLink pilot value a year | £40k to £150k | −£105k / +£225k | −£58k / +£124k |
| African price per woman per year | £3 to £12 | −£61k / +£122k | −£61k / +£122k |
| Founder day rate | £1,200 to £1,800 | −£5k / +£5k | −£5k / +£5k |

Three things to take from that table.

One retainer held for two years is worth about £91,000. That is more than any single MaternaLink assumption inside three years. Sell retainers first.

Bigger projects beat more projects. Your billable days are already spoken for, so the day rate is almost irrelevant. Capacity is the lever, not price.

When MaternaLink goes live matters more the faster you grow. A 12-month slip costs the middle case £132k of revenue, but it costs the ambitious case £775k of EBITDA and £642k of cash. So do not build the MaternaLink cost base until go-live has a contract date.

## Raising money in stages

!Grants, pre-seed, seed and Series A, and what each one needs (../diagrams/funding-stairs.svg)

Caption: Each step is opened by proof, not by time passing.

| Step | Amount | Who puts it in | What must be true first |
| --- | --- | --- | --- |
| Grants and services | No shares given up | Innovate UK, SBRI Healthcare, first paying clients | A registered company and a clinical partner letter |
| Pre-seed | £250k–£500k | SEIS/EIS angels, angel syndicates | Company incorporated; ownership deed executed; 2025 claims retired; advance assurance submitted; one signed services engagement; two named advisers |
| Seed | £1.5m–£3m | Health-tech and impact funds | Product built, security-tested and in a registered evaluation; one paid pilot signed; safety pack complete; team of three; services at £15k a month with two retainers; clean share register |
| Series A | £6m–£12m | Growth and impact funds, a strategic as a minority | Recurring MaternaLink revenue of £0.4m–£0.9m, or three UK sites plus one state programme; multi-site evaluation results; team of about ten |

Do not open any raise before the ownership agreement is signed and the old AI claims are withdrawn.

SEIS and EIS in plain words. SEIS is a tax scheme that gives people money back when they invest in a small British company. An investor gets 50% of what they put in taken off their income tax. EIS is the same idea for a slightly bigger company, at 30%. This is why UK angels will not invest without it. Never say "SEIS-approved"; say "advance assurance applied for" once that is true.

| Limit | Commonly cited figure | Label |
| --- | --- | --- |
| SEIS, per company, for its lifetime | £250,000 | TO VALIDATE |
| SEIS, per investor, per tax year | £200,000 | TO VALIDATE |
| SEIS company conditions | Trading under 3 years; assets under £350,000; fewer than 25 full-time staff | TO VALIDATE |
| EIS, per 12 months | £5,000,000 | TO VALIDATE |
| EIS, lifetime | £12,000,000 | TO VALIDATE |

TO VALIDATE means we do not know yet. Check every line with an accountant and against gov.uk before saying it to an investor. A £400k pre-seed cannot be all SEIS: it splits into £250k SEIS then £150k EIS.

## Are you ready?

!The 15 things to fix before an investor meeting (../diagrams/readiness.svg)

Caption: The first four items gate everything else, and none of them is done today.

| Done | What must be true | Owner | By when |
| --- | --- | --- | --- |
| [ ] | Company registered, bank account open, accountant appointed | Founder | Day 10 |
| [ ] | MaternaLink owned or licensed in writing | Founder and solicitor | Day 30 |
| [ ] | No unproven medical claims anywhere public | Founder | Day 3–14 |
| [ ] | Name and trademark checked and filed | Founder and trademark attorney | Day 5, filed Day 20 |
| [ ] | First revenue: one signed piece of work | Founder | Day 45 |
| [ ] | One hospital or NGO agrees in writing to a trial | Founder | Day 60 |
| [ ] | Two advisers confirmed, one clinical | Founder | Day 60 |
| [ ] | Prototype audited, written up, with an intended-use statement | Fractional product lead | Day 30 |
| [ ] | Financial model updated with real costs, round size chosen | Finance role | Day 60 |
| [ ] | Data room built | Founder | Day 45 |
| [ ] | Investor list verified and outreach ready | Founder | Day 55 |
| [ ] | Data registration, security certification booked, insurance quoted | Founder | Day 30 |
| [ ] | Your own time commitment written down, the other venture ring-fenced | Founder | Day 7 |
| [ ] | Fifteen discovery interviews written up, three quotes with consent | Founder | Day 60 |
| [ ] | One grant application submitted | Founder | Day 75 |

The rule. Take no first investor meeting until the first four are done and at least two of items 5, 6 and 7. A meeting taken too early costs you that fund for twelve months.

## What investors will ask, and the honest answer today

| Question | The answer now | The answer at day 90 |
| --- | --- | --- |
| Do you own MaternaLink? | Not yet in writing | Yes, the deed is signed |
| Is it a medical device? | Not as re-scoped, but the prototype needs changes | Intended use adopted, prototype changed, a regulatory opinion scoped |
| Any revenue? | None | The first advisory engagements |
| Any customer or pilot? | An earlier ministry conversation that went nowhere | One written pilot agreement, fifteen interviews documented |
| Who is on the team? | A solo founder and one collaborator | Founder, two advisers, a part-time technical lead and a safety officer identified |
| Why you? | The founder story, still to be written | The founder story plus evidence that you deliver |
| How much and what for? | £250k–£500k pre-seed | The same, with milestones tied to the model |

## What kills a raise

| What kills it | How an investor finds it | Fixed by |
| --- | --- | --- |
| Ownership of MaternaLink not written down | One question: who owns the code. Then the email signature on the old proposal | Day 30, hard stop Day 60 |
| Medical claims nobody has proved | Any copy of the 2025 deck, a web search, or the prototype's own words | Day 3 |
| No company registered | A Companies House search returns nothing | Day 12 |
| The old £300 per woman pricing | The proposal circulates; anyone with African health-tech experience knows the going rate | Day 21 to re-base, Day 60 for the decision |

Any one of these ends the conversation on the spot, and some investors will not come back.

## Words explained

| Word | What it means |
| --- | --- |
| EBITDA | Profit before interest, tax and the cost of equipment |
| Peak cash need | The deepest the bank balance would go with no investment and no grants at all |
| Pre-seed | The first outside money, usually from individuals rather than funds |
| Seed | The round that pays for the product and the first proper team |
| Series A | The round that pays for scaling something already working |
| SEIS and EIS | Tax schemes that give people money back when they invest in a small British company |
| Advance assurance | HMRC saying in advance that your company looks eligible for those schemes |
| Data room | One organised folder holding everything an investor will ask to see |
| TO VALIDATE | We do not know yet and must go and check |